## Sheet1
=Print_Area
NIST/NCCoE FFRDC Proposal | [48 empty] | ,m
[20 empty] | FFRDC Program Manager | Deputy FFRDC Program Manager | OCI Compliance Officer | Contracts Manager | Project Manager I | Project Manager II | Project Manager III | Cybersecurity Subject Matter Expert I | Cybersecurity Subject Matter Expert II | Cybersecurity Subject Matter Expert III | Cybersecurity Subject Matter Expert IV | Cybersecurity Security Engineer I | Cybersecurity Security Engineer II | Cybersecurity Security Engineer III | Cybersecurity Engineer I | Cybersecurity Engineer II | Cybersecurity Engineer III | Cybersecurity Development Subject Matter Expert I | Cybersecurity Development Subject Matter Expert II | Cybersecurity Development Subject Matter Expert III | Cybersecurity Development Subject Matter Expert IV | Senior Cybersecurity Engineer | IT Job I | IT Job II | IT Job III | IT Job IV | IT Job V | MTS I | MTS II | MTS III | MTS IV | MTS V | Analyst-SME I | Analyst-SME II | Analyst-SME III | Analyst-SME IV | Analyst-SME V | Analyst-SME VI | Analyst-SME VII | Talent Manager | Talent Mgt Specialist | Meetings and Events Coordinator | Training and Implementation Coordinator | Communications Strategist | Technology Partnerships Subject Matter Expert | Technology Partnerships SME I | Technology Partnerships SME II | Technology Partnerships SME III | Quality Manager i | Quality Assurance Engineer I | Quality Assurance Engineer II | Quality Assurance Engineer III | Quality Assurance Engineer IV | Administrative Officer - FFRDC | Accounting Manager / Project Control | Program Planning & Control Analyst | Staff Accountant I | Staff Accountant II | Facilities Administrator | Lead Services Asst | Services Assistant | Receptionist/ Visitor Control Clerk | Configuration Mgt Spec I | Configuration Mgt Spec II | Configuration Mgt Spec III | Configuration mgt Spec IV | Technical Publications Manager | Tech Writer/ Ed I | Tech Writer/ Ed II | Tech Writer/ Ed III | Tech Writer/ Ed IV | Creative Media Specialist | Creative Media Specialist I | Creative Media Specialist II | Graphics Specialist - I | Graphics Specialist - II | Facilities Subject Matter Expert | Administrative Specialist I | Administrative Specialist II | Administrative Specialist III
[20 empty] | 0101 | 0102 | 0103 | 0104 | 0106 | 0107 | 0108 | 0202 | 0203 | 0204 | 0205 | 0207 | 0208 | 0209 | 0211 | 0212 | 0213 | 0215 | 0216 | 0217 | 0218 | 0219 | 0302 | 0303 | 0304 | 0305 | 0306 | 0402 | 0403 | 0404 | 0405 | 0406 | 0408 | 0409 | 0410 | 0411 | 0412 | 0413 | 0414 | 0501 | 0502 | 0503 | 0504 | 0505 | 0601 | 0602 | 0603 | 0604 | 0701 | 0703 | 0704 | 0705 | 0706 | 0801 | 0802 | 0803 | 0805 | 0806 | 0807 | 0808 | 0809 | 0810 | 0902 | 0903 | 0904 | 0905 | 0906 | 0908 | 0910 | 0911 | 0912 | 0913 | 0914 | 0915 | 0917 | 0918 | 1001 | 1102 | 1103 | 1104 | ODC
WBS Line Number | WBS Levels | [10 empty] | Work Breakdown Structure |  |  |  | Field Type |  |  | Hrs
[16 empty] | Field Type |  |  | Total hrs by Task | 0101 | 0102 | 0103 | 0104 | 0106 | 0107 | 0108 | 0202 | 0203 | 0204 | 0205 | 0207 | 0208 | 0209 | 0211 | 0212 | 0213 | 0215 | 0216 | 0217 | 0218 | 0219 | 0302 | 0303 | 0304 | 0305 | 0306 | 0402 | 0403 | 0404 | 0405 | 0406 | 0408 | 0409 | 0410 | 0411 | 0412 | 0413 | 0414 | 0501 | 0502 | 0503 | 0504 | 0505 | 0601 | 0602 | 0603 | 0604 | 0701 | 0703 | 0704 | 0705 | 0706 | 0801 | 0802 | 0803 | 0805 | 0806 | 0807 | 0808 | 0809 | 0810 | 0902 | 0903 | 0904 | 0905 | 0906 | 0908 | 0910 | 0911 | 0912 | 0913 | 0914 | 0915 | 0917 | 0918 | 1001 | 1102 | 1103 | 1104 | ODC
ID | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | Description | WBS | SOW | UID | Type | Duration | Converted hrs | Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | ODC
1 | [11 empty] | NIST/NCCoE FFRDC Proposal | 1 | 1 | 5 | P | 1307 days |  | 0
1 | 01 | [10 empty] | Task Order 1 - Use Case Development and Implementation | 1.01 | 1.1 | 1 | C | 529 days |  | 43285.74
1 | 01 | 15 | [9 empty] | Task Order #1 Major Milestones | 1.01.15 | 1.1.15 | 6924 | S | 524 days |  | 0
1 | 01 | 15 | 01 | [8 empty] | Task Order 1 Award | 1.01.15.01 | 1.1.15.1 | 6925 | M | 0 days | 0 | 0
1 | 01 | 15 | 02 | [8 empty] | Task Order 1 Closure | 1.01.15.02 | 1.1.15.2 | 7001 | M | 0 days | 0 | 0
1 | 01 | 01 | [9 empty] | Phase 1 | 1.01.01 |  | 6939 | C |  |  | 9566
1 | 01 | 01 | 01 | [8 empty] | Requirements Definition (5.1) | 1.01.01.01 | 1.5.1 | 6688 | W |  |  | 9566 |  |  | 120 | [7 empty] | 624 |  |  | 1756 | 1600 |  |  |  |  | 1568 | 752 | [7 empty] | 1808 | 0 | [17 empty] | 144 | [19 empty] | 368 | [6 empty] | 102 |  |  | 724 |  | 0
1 | 01 | 01 | 01 | 01 | [7 empty] | Monthly Planning Conference Agenda and Conferences (5.1.1) | 1.01.01.01.01 | 1.5.1.1 | 6687 | S | 521 days |  | 0 |  |  | 0
1 | 01 | 01 | 01 | 01 | 01 | [6 empty] | Produce and Deliver Agenda OCT 2014 | 1.01.01.01.01.01 |  | 7011 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 02 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.02 |  | 7010 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 03 | [6 empty] | Produce and Deliver Minutes | 1.01.01.01.01.03 |  | 7009 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 04 | [6 empty] | Produce and Deliver Agenda NOV 2014 | 1.01.01.01.01.04 |  | 7078 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 05 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.05 |  | 7079 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 06 | [6 empty] | Produce and Deliver Minutes | 1.01.01.01.01.06 |  | 7080 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 07 | [6 empty] | Produce and Deliver Agenda DEC 2014 | 1.01.01.01.01.07 |  | 7081 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 08 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.08 |  | 7082 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 09 | [6 empty] | Produce and Deliver Minutes | 1.01.01.01.01.09 |  | 7083 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 10 | [6 empty] | Produce and Deliver Agenda JAN 2015 | 1.01.01.01.01.10 |  | 7084 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 11 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.11 |  | 7085 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 12 | [6 empty] | Produce and Deliver Minutes | 1.01.01.01.01.12 |  | 7086 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 13 | [6 empty] | Produce and Deliver Agenda FEB 2015 | 1.01.01.01.01.13 |  | 7087 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 14 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.14 |  | 7068 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 15 | [6 empty] | Produce and Deliver Minutes | 1.01.01.01.01.15 |  | 7069 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 16 | [6 empty] | Produce and Deliver Agenda MAR 2015 | 1.01.01.01.01.16 |  | 7070 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 17 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.17 |  | 7071 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 18 | [6 empty] | Produce and Deliver Minutes | 1.01.01.01.01.18 |  | 7072 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 19 | [6 empty] | Produce and Deliver Agenda APR 2015 | 1.01.01.01.01.19 |  | 7073 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 20 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.20 |  | 7074 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 21 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.21 |  | 7075 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 22 | [6 empty] | Produce and Deliver Agenda MAY 2015 | 1.01.01.01.01.22 |  | 7076 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 23 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.23 |  | 7077 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 24 | [6 empty] | Produce and Deliver Minutes | 1.01.01.01.01.24 |  | 7058 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 25 | [6 empty] | Produce and Deliver Agenda JUN 2015 | 1.01.01.01.01.25 |  | 7059 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 26 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.26 |  | 7060 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 27 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.27 |  | 7061 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 28 | [6 empty] | Produce and Deliver Agenda JUL 2015 | 1.01.01.01.01.28 |  | 7062 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 29 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.29 |  | 7063 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 30 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.30 |  | 7064 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 31 | [6 empty] | Produce and Deliver Agenda AUG 2015 | 1.01.01.01.01.31 |  | 7065 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 32 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.32 |  | 7066 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 33 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.33 |  | 7067 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 34 | [6 empty] | Produce and Deliver Agenda SEP 2015 | 1.01.01.01.01.34 |  | 7048 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 35 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.35 |  | 7049 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 36 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.36 |  | 7050 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 37 | [6 empty] | Produce and Deliver Agenda OCT 2015 | 1.01.01.01.01.37 |  | 7051 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 38 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.38 |  | 7052 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 39 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.39 |  | 7053 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 40 | [6 empty] | Produce and Deliver Agenda NOV 2015 | 1.01.01.01.01.40 |  | 7054 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 41 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.41 |  | 7055 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 42 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.42 |  | 7056 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 43 | [6 empty] | Produce and Deliver Agenda DEC 2015 | 1.01.01.01.01.43 |  | 7057 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 44 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.44 |  | 7038 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 45 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.45 |  | 7039 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 46 | [6 empty] | Produce and Deliver Agenda JAN 2016 | 1.01.01.01.01.46 |  | 7040 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 47 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.47 |  | 7041 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 48 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.48 |  | 7042 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 49 | [6 empty] | Produce and Deliver Agenda FEB 2016 | 1.01.01.01.01.49 |  | 7043 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 50 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.50 |  | 7044 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 51 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.51 |  | 7045 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 52 | [6 empty] | Produce and Deliver Agenda MAR 2016 | 1.01.01.01.01.52 |  | 7046 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 53 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.53 |  | 7047 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 54 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.54 |  | 7028 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 55 | [6 empty] | Produce and Deliver Agenda APR 2016 | 1.01.01.01.01.55 |  | 7029 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 56 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.56 |  | 7030 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 57 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.57 |  | 7031 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 58 | [6 empty] | Produce and Deliver Agenda MAY 2016 | 1.01.01.01.01.58 |  | 7032 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 59 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.59 |  | 7033 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 60 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.60 |  | 7034 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 61 | [6 empty] | Produce and Deliver Agenda JUN 2016 | 1.01.01.01.01.61 |  | 7035 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 62 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.62 |  | 7036 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 63 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.63 |  | 7037 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 64 | [6 empty] | Produce and Deliver Agenda JUL 2016 | 1.01.01.01.01.64 |  | 7027 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 65 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.65 |  | 7026 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 66 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.66 |  | 7025 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 67 | [6 empty] | Produce and Deliver Agenda AUG 2016 | 1.01.01.01.01.67 |  | 7024 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 68 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.68 |  | 7023 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 69 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.69 |  | 7022 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 01 | 70 | [6 empty] | Produce and Deliver Agenda SEP 2016 | 1.01.01.01.01.70 |  | 12294 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 71 | [6 empty] | Host Monthly Conference | 1.01.01.01.01.71 |  | 12295 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 01 | 72 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.72 |  | 12296 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 02 | [7 empty] | Conduct in-person meetings to review Cybersecurity Issues (5.1.2) | 1.01.01.01.02 | 1.5.1.2 | 6690 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 01 | [6 empty] | Conduct in-person meetings (qty 6) to review Cybersecurity Issues (5.1.2) NOV 2014 ( 6 meetings) | 1.01.01.01.02.01 |  | 8688 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 01 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.01.01 |  | 8689 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 01 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.01.02 |  | 8690 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 01 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.01.03 |  | 8691 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 01 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.01.04 |  | 8692 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 01 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.01.05 |  | 8693 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 01 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.01.06 |  | 8694 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 01 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.01.07 |  | 8695 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 01 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.01.08 |  | 8696 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 01 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.01.09 |  | 8697 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 01 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.01.10 |  | 8698 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 01 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.01.11 |  | 8699 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 01 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.01.12 |  | 8700 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | [6 empty] | Conduct in-person meetings (qty 7) to review Cybersecurity Issues (5.1.2) DEC 2014 ( 7 meetings) | 1.01.01.01.02.02 |  | 8701 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 02 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.02.01 |  | 8702 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.02.02 |  | 8703 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.02.03 |  | 8704 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.02.04 |  | 8705 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.02.05 |  | 8706 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.02.06 |  | 8707 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.02.07 |  | 8708 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.02.08 |  | 8709 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.02.09 |  | 8710 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.02.10 |  | 8711 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.02.11 |  | 8712 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.02.12 |  | 8713 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.02.13 |  | 8714 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 02 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.02.14 |  | 8715 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | [6 empty] | Conduct in-person meetings (qty 8) to review Cybersecurity Issues (5.1.2) JAN 2015 ( 8 meetings) | 1.01.01.01.02.03 |  | 8716 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 03 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.03.01 |  | 8717 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.03.02 |  | 8718 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.03.03 |  | 8719 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.03.04 |  | 8720 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.03.05 |  | 8721 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.03.06 |  | 8722 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.03.07 |  | 8723 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.03.08 |  | 8724 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.03.09 |  | 8725 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.03.10 |  | 8726 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.03.11 |  | 8727 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.03.12 |  | 8728 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.03.13 |  | 8729 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.03.14 |  | 8730 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.03.15 |  | 8731 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 03 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.03.16 |  | 8732 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | [6 empty] | Conduct in-person meetings (qty 9) to review Cybersecurity Issues (5.1.2) FEB 2015 ( 9 meetings) | 1.01.01.01.02.04 |  | 8733 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 04 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.04.01 |  | 8734 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.04.02 |  | 8735 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.04.03 |  | 8736 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.04.04 |  | 8737 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.04.05 |  | 8738 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.04.06 |  | 8739 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.04.07 |  | 8740 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.04.08 |  | 8741 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.04.09 |  | 8742 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.04.10 |  | 8743 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 11 | [5 empty] | execute a Monthly Building Block Team Development Conference Agenda (5.7) | 1.01.01.01.02.04.11 |  | 8744 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.04.12 |  | 8745 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.04.13 |  | 8746 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.04.14 |  | 8747 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.04.15 |  | 8748 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.04.16 |  | 8749 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.04.17 |  | 8750 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 04 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.04.18 |  | 8751 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) MAR 2015 ( 10 meetings) | 1.01.01.01.02.05 |  | 8752 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 05 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.05.01 |  | 8753 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.05.02 |  | 8754 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.05.03 |  | 8755 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.05.04 |  | 8756 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.05.05 |  | 8757 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.05.06 |  | 8758 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.05.07 |  | 8759 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.05.08 |  | 8760 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.05.09 |  | 8761 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.05.10 |  | 8762 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.05.11 |  | 8763 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.05.12 |  | 8764 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.05.13 |  | 8765 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.05.14 |  | 8766 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.05.15 |  | 8767 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.05.16 |  | 8768 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.05.17 |  | 8769 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.05.18 |  | 8770 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.05.19 |  | 8771 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 05 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.05.20 |  | 8772 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) APR 2015 (10 meetings) | 1.01.01.01.02.06 |  | 8773 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 06 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.06.01 |  | 8774 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.06.02 |  | 8775 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.06.03 |  | 8776 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.06.04 |  | 8777 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.06.05 |  | 8778 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.06.06 |  | 8779 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.06.07 |  | 8780 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.06.08 |  | 8781 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.06.09 |  | 8782 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.06.10 |  | 8783 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.06.11 |  | 8784 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.06.12 |  | 8785 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.06.13 |  | 8786 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.06.14 |  | 8787 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.06.15 |  | 8788 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.06.16 |  | 8789 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.06.17 |  | 8790 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.06.18 |  | 8791 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.06.19 |  | 8792 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 06 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.06.20 |  | 8793 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) MAY 2015 ( 10 meetings) | 1.01.01.01.02.07 |  | 8794 | S | 1 day | 0 | 0 | [10 empty] | 0 |  |  | 0 | 0 | [5 empty] | 0 | [7 empty] | 0 | 0 | [37 empty] | 0 | [6 empty] | 0 |  |  | 0
1 | 01 | 01 | 01 | 02 | 07 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.07.01 |  | 8795 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.07.02 |  | 8796 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.07.03 |  | 8797 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.07.04 |  | 8798 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.07.05 |  | 8799 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.07.06 |  | 8800 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.07.07 |  | 8801 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.07.08 |  | 8802 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.07.09 |  | 8803 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.07.10 |  | 8804 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.07.11 |  | 8805 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.07.12 |  | 8806 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.07.13 |  | 8807 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.07.14 |  | 8808 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.07.15 |  | 8809 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.07.16 |  | 8810 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.07.17 |  | 8811 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.07.18 |  | 8812 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.07.19 |  | 8813 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 07 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.07.20 |  | 8814 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) JUN 2015 ( 10 meetings) | 1.01.01.01.02.08 |  | 8815 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 08 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.08.01 |  | 8816 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.08.02 |  | 8817 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.08.03 |  | 8818 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.08.04 |  | 8819 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.08.05 |  | 8820 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.08.06 |  | 8821 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.08.07 |  | 8822 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.08.08 |  | 8823 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.08.09 |  | 8824 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.08.10 |  | 8825 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.08.11 |  | 8826 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.08.12 |  | 8827 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.08.13 |  | 8828 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.08.14 |  | 8829 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.08.15 |  | 8830 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.08.16 |  | 8831 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.08.17 |  | 8832 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.08.18 |  | 8833 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.08.19 |  | 8834 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 08 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.08.20 |  | 8835 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) JUL 2015 ( 10 meetings) | 1.01.01.01.02.09 |  | 8836 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 09 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.09.01 |  | 8837 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.09.02 |  | 8838 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.09.03 |  | 8839 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.09.04 |  | 8840 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.09.05 |  | 8841 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.09.06 |  | 8842 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.09.07 |  | 8843 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.09.08 |  | 8844 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.09.09 |  | 8845 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.09.10 |  | 8846 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.09.11 |  | 8847 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.09.12 |  | 8528 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.09.13 |  | 8529 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.09.14 |  | 8530 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.09.15 |  | 8531 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.09.16 |  | 8532 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.09.17 |  | 8533 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.09.18 |  | 8534 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.09.19 |  | 8535 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 09 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.09.20 |  | 8536 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) AUG 2015 ( 10 meetings) | 1.01.01.01.02.10 |  | 8537 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 10 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.10.1 |  | 8538 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.10.2 |  | 8539 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.10.3 |  | 8540 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.10.4 |  | 8541 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.10.5 |  | 8542 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.10.6 |  | 8543 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.10.7 |  | 8544 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.10.8 |  | 8545 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.10.9 |  | 8546 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.10.10 |  | 8547 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.10.11 |  | 8548 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.10.12 |  | 8549 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.10.13 |  | 8550 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.10.14 |  | 8551 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.10.15 |  | 8552 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.10.16 |  | 8553 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.10.17 |  | 8554 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.10.18 |  | 8555 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.10.19 |  | 8556 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 10 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.10.20 |  | 8557 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) SEP 2015 ( 10 meetings) | 1.01.01.01.02.11 |  | 8558 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 11 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.11.01 |  | 8559 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.11.02 |  | 8560 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.11.03 |  | 8561 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.11.04 |  | 8562 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.11.05 |  | 8563 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.11.06 |  | 8564 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.11.07 |  | 8565 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.11.08 |  | 8566 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.11.09 |  | 8567 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.11.10 |  | 8568 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.11.11 |  | 8569 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.11.12 |  | 8570 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.11.13 |  | 8571 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.11.14 |  | 8572 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.11.15 |  | 8573 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.11.16 |  | 8574 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.11.17 |  | 8575 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.11.18 |  | 8576 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.11.19 |  | 8577 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 11 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.11.20 |  | 8578 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) OCT 2015 ( 10 meetings) | 1.01.01.01.02.12 |  | 8579 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 12 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.12.01 |  | 8580 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.12.02 |  | 8581 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.12.03 |  | 8582 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.12.04 |  | 8583 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.12.05 |  | 8584 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.12.06 |  | 8585 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.12.07 |  | 8586 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.12.08 |  | 8587 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.12.09 |  | 8588 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.12.10 |  | 8589 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.12.11 |  | 8590 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.12.12 |  | 8591 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.12.13 |  | 8592 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.12.14 |  | 8593 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.12.15 |  | 8594 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.12.16 |  | 8595 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.12.17 |  | 8596 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.12.18 |  | 8597 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.12.19 |  | 8598 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 12 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.12.20 |  | 8599 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) NOV 2015 ( 10 meetings) | 1.01.01.01.02.13 |  | 8600 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 13 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.13.01 |  | 8601 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.13.02 |  | 8602 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.13.03 |  | 8603 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.13.04 |  | 8604 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.13.05 |  | 8605 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.13.06 |  | 8606 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.13.07 |  | 8607 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.13.08 |  | 8608 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.13.09 |  | 8609 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.13.10 |  | 8610 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.13.11 |  | 8611 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.13.12 |  | 8612 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.13.13 |  | 8613 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.13.14 |  | 8614 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.13.15 |  | 8615 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.13.16 |  | 8616 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.13.17 |  | 8617 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.13.18 |  | 8618 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.13.19 |  | 8619 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 13 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.13.20 |  | 8620 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) DEC 2015 ( 10 meetings) | 1.01.01.01.02.14 |  | 8621 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 14 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.14.01 |  | 8622 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.14.02 |  | 8623 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.14.03 |  | 8624 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.14.04 |  | 8625 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.14.05 |  | 8626 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.14.06 |  | 8627 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.14.07 |  | 8628 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.14.08 |  | 8629 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.14.09 |  | 8630 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.14.10 |  | 8631 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.14.11 |  | 8632 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.14.12 |  | 8633 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.14.13 |  | 8634 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.14.14 |  | 8635 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.14.15 |  | 8636 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.14.16 |  | 8637 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.14.17 |  | 8638 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.14.18 |  | 8639 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.14.19 |  | 8640 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 14 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.14.20 |  | 8641 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) JAN 2016 ( 10 meetings) | 1.01.01.01.02.15 |  | 8642 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 15 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.15.01 |  | 8643 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.15.02 |  | 8644 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.15.03 |  | 8645 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.15.04 |  | 8646 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.15.05 |  | 8647 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.15.06 |  | 8648 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.15.07 |  | 8649 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.15.08 |  | 8650 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.15.09 |  | 8651 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.15.10 |  | 8652 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.15.11 |  | 8653 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.15.12 |  | 8654 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.15.13 |  | 8655 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.15.14 |  | 8656 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.15.15 |  | 8657 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.15.16 |  | 8658 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.15.17 |  | 8659 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.15.18 |  | 8660 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.15.19 |  | 8661 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 15 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.15.20 |  | 8662 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) FEB 2016 ( 10 meetings) | 1.01.01.01.02.16 |  | 8663 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 16 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.16.01 |  | 8664 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.16.02 |  | 8665 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.16.03 |  | 8666 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.16.04 |  | 8667 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.16.05 |  | 8668 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.16.06 |  | 8669 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.16.07 |  | 8670 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.16.08 |  | 8671 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.16.09 |  | 8672 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.16.10 |  | 8673 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.16.11 |  | 8674 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.16.12 |  | 8675 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.16.13 |  | 8676 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.16.14 |  | 8677 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.16.15 |  | 8678 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.16.16 |  | 8679 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.16.17 |  | 8680 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.16.18 |  | 8681 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.16.19 |  | 8682 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 16 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.16.20 |  | 8683 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) MAR 2016 ( 10 meetings) | 1.01.01.01.02.17 |  | 8684 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 17 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.17.01 |  | 8685 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.17.02 |  | 8686 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.17.03 |  | 8687 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.17.04 |  | 8368 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.17.05 |  | 8369 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.17.06 |  | 8370 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.17.07 |  | 8371 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.17.08 |  | 8372 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.17.09 |  | 8373 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.17.10 |  | 8374 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.17.11 |  | 8375 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.17.12 |  | 8376 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.17.13 |  | 8377 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.17.14 |  | 8378 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.17.15 |  | 8379 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.17.16 |  | 8380 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.17.17 |  | 8381 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.17.18 |  | 8382 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.17.19 |  | 8383 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 17 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.17.20 |  | 8384 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) APR 2016 ( 10 meetings) | 1.01.01.01.02.18 |  | 8385 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 18 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.18.01 |  | 8386 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.18.02 |  | 8387 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.18.03 |  | 8388 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.18.04 |  | 8389 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.18.05 |  | 8390 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.18.06 |  | 8391 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.18.07 |  | 8392 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.18.08 |  | 8393 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.18.09 |  | 8394 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.18.10 |  | 8395 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.18.11 |  | 8396 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.18.12 |  | 8397 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.18.13 |  | 8398 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.18.14 |  | 8399 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.18.15 |  | 8400 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.18.16 |  | 8401 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.18.17 |  | 8402 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.18.18 |  | 8403 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.18.19 |  | 8404 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 18 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.18.20 |  | 8405 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) MAY 2016 ( 10 meetings) | 1.01.01.01.02.19 |  | 8406 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 19 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.19.01 |  | 8407 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.19.02 |  | 8408 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.19.03 |  | 8409 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.19.04 |  | 8410 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.19.05 |  | 8411 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.19.06 |  | 8412 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.19.07 |  | 8413 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.19.08 |  | 8414 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.19.09 |  | 8415 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.19.10 |  | 8416 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.19.11 |  | 8417 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.19.12 |  | 8418 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.19.13 |  | 8419 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.19.14 |  | 8420 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.19.15 |  | 8421 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.19.16 |  | 8422 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.19.17 |  | 8423 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.19.18 |  | 8424 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.19.19 |  | 8425 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 19 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.19.20 |  | 8426 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) JUN 2016 ( 10 meetings) | 1.01.01.01.02.20 |  | 8427 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 20 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.20.01 |  | 8428 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.20.02 |  | 8429 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.20.03 |  | 8430 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.20.04 |  | 8431 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.20.05 |  | 8432 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.20.06 |  | 8433 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.20.07 |  | 8434 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.20.08 |  | 8435 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.20.09 |  | 8436 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.20.10 |  | 8437 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.20.11 |  | 8438 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.20.12 |  | 8439 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.20.13 |  | 8440 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.20.14 |  | 8441 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.20.15 |  | 8442 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.20.16 |  | 8443 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.20.17 |  | 8444 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.20.18 |  | 8445 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.20.19 |  | 8446 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 20 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.20.20 |  | 8447 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) JUL 2016 ( 10 meetings) | 1.01.01.01.02.21 |  | 8448 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 21 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.21.01 |  | 8449 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.21.02 |  | 8450 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.21.03 |  | 8451 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.21.04 |  | 8452 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.21.05 |  | 8453 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.21.06 |  | 8454 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.21.07 |  | 8455 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.21.08 |  | 8456 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.21.09 |  | 8457 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.21.10 |  | 8458 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.21.11 |  | 8459 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.21.12 |  | 8460 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.21.13 |  | 8461 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.21.14 |  | 8462 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.21.15 |  | 8463 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.21.16 |  | 8464 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.21.17 |  | 8465 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.21.18 |  | 8466 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.21.19 |  | 8467 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 21 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.21.20 |  | 8468 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) AUG 2016 ( 10 meetings) | 1.01.01.01.02.22 |  | 8469 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 22 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.22.01 |  | 8470 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.22.02 |  | 8471 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.22.03 |  | 8472 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.22.04 |  | 8473 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.22.05 |  | 8474 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.22.06 |  | 8475 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.22.07 |  | 8476 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.22.08 |  | 8477 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.22.09 |  | 8478 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.22.10 |  | 8479 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.22.11 |  | 8480 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.22.12 |  | 8481 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.22.13 |  | 8482 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.22.14 |  | 8483 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.22.15 |  | 8484 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.22.16 |  | 8485 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.22.17 |  | 8486 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.22.18 |  | 8487 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.22.19 |  | 8488 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 22 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.22.20 |  | 8489 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) SEP 2016 ( 10 meetings) | 1.01.01.01.02.23 |  | 10923 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 02 | 23 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.23.01 |  | 10924 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.23.02 |  | 10925 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.23.03 |  | 10926 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.23.04 |  | 10927 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.23.05 |  | 10928 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.23.06 |  | 10929 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.23.07 |  | 10930 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.23.08 |  | 10931 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.23.09 |  | 10932 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.23.10 |  | 10933 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.23.11 |  | 10934 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.23.12 |  | 10935 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.23.13 |  | 10936 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.23.14 |  | 10937 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.23.15 |  | 10938 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.23.16 |  | 10939 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.23.17 |  | 10940 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.23.18 |  | 10941 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.02.23.19 |  | 10942 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 02 | 23 | 20 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.02.23.20 |  | 10943 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) | 1.01.01.01.03 | 1.5.1.3 | 6691 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 01 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) NOV 2014 ( 6 meetings) | 1.01.01.01.03.01 |  | 9260 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.01.01 |  | 9261 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.01.02 |  | 9262 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.01.03 |  | 9263 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.01.04 |  | 9264 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.01.05 |  | 9265 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.01.06 |  | 9266 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.01.07 |  | 9267 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.01.08 |  | 9268 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.01.09 |  | 9269 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.01.10 |  | 9270 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.01.11 |  | 9271 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 01 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.01.12 |  | 9272 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) DEC 2014 ( 7 meetings) | 1.01.01.01.03.02 |  | 9273 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 02 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.02.01 |  | 9274 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.02.02 |  | 9275 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.02.03 |  | 9276 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.02.04 |  | 9277 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.02.05 |  | 9278 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.02.06 |  | 9279 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.02.07 |  | 9238 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.02.08 |  | 9239 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.02.09 |  | 9240 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.02.10 |  | 9241 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.02.11 |  | 9242 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.02.12 |  | 9243 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.02.13 |  | 9244 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 02 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.02.14 |  | 9245 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) JAN 2015 ( 8 meetings) | 1.01.01.01.03.03 |  | 9246 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 03 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.03.01 |  | 9247 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.03.02 |  | 9248 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.03.03 |  | 9249 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.03.04 |  | 9250 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.03.05 |  | 9251 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.03.06 |  | 9252 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.03.07 |  | 9253 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.03.08 |  | 9254 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.03.09 |  | 9255 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.03.10 |  | 9256 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.03.11 |  | 9257 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.03.12 |  | 9258 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.03.13 |  | 9217 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.03.14 |  | 9218 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.03.15 |  | 9219 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 03 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.03.16 |  | 9220 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) FEB 2015 (9 meetings) | 1.01.01.01.03.04 |  | 9221 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 04 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.04.01 |  | 9222 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.04.02 |  | 9223 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.04.03 |  | 9224 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.04.04 |  | 9225 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.04.05 |  | 9226 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.04.06 |  | 9227 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.04.07 |  | 9228 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.04.08 |  | 9229 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.04.09 |  | 9230 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.04.10 |  | 9231 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.04.11 |  | 9232 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.04.12 |  | 9233 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.04.13 |  | 9234 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.04.14 |  | 9235 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.04.15 |  | 9236 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.04.16 |  | 9237 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.04.17 |  | 9196 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 04 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.04.18 |  | 9197 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) MAR 2015 ( 10 meetings) | 1.01.01.01.03.05 |  | 9198 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 05 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.05.01 |  | 9199 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.05.02 |  | 9200 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.05.03 |  | 9201 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.05.04 |  | 9202 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.05.05 |  | 9203 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.05.06 |  | 9204 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.05.07 |  | 9205 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.05.08 |  | 9206 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.05.09 |  | 9207 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.05.10 |  | 9208 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.05.11 |  | 9209 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.05.12 |  | 9210 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.05.13 |  | 9211 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.05.14 |  | 9212 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.05.15 |  | 9213 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.05.16 |  | 9214 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.05.17 |  | 9215 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.05.18 |  | 9216 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.05.19 |  | 9175 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 05 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.05.20 |  | 9176 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) APR 2015 ( 10 meetings) | 1.01.01.01.03.06 |  | 9409 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 06 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.06.01 |  | 9410 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.06.02 |  | 9411 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.06.03 |  | 9412 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.06.04 |  | 9413 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.06.05 |  | 9414 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.06.06 |  | 9415 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.06.07 |  | 9416 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.06.08 |  | 9417 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.06.09 |  | 9418 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.06.10 |  | 9419 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.06.11 |  | 9420 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.06.12 |  | 9397 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.06.13 |  | 9398 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.06.14 |  | 9399 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.06.15 |  | 9400 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.06.16 |  | 9401 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.06.17 |  | 9402 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.06.18 |  | 9403 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.06.19 |  | 9404 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 06 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.06.20 |  | 9405 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) MAY 2015 ( 10 meetings) | 1.01.01.01.03.07 |  | 9406 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 07 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.07.01 |  | 9407 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 02 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.07.02 |  | 9408 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.07.03 |  | 9385 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.07.04 |  | 9386 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.07.05 |  | 9387 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.07.06 |  | 9388 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.07.07 |  | 9389 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 08 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.07.08 |  | 9390 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.07.09 |  | 9391 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.07.10 |  | 9392 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.07.11 |  | 9393 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.07.12 |  | 9394 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.07.13 |  | 9395 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.07.14 |  | 9396 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.07.15 |  | 9373 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.07.16 |  | 9374 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.07.17 |  | 9375 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.07.18 |  | 9376 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.07.19 |  | 9377 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 07 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.07.20 |  | 9378 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) JUN 2015 ( 10 meetings) | 1.01.01.01.03.08 |  | 9379 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 08 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.08.01 |  | 9380 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.08.02 |  | 9381 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.08.03 |  | 9382 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.08.04 |  | 9383 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.08.05 |  | 9384 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 06 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.08.06 |  | 9361 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.08.07 |  | 9362 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.08.08 |  | 9363 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.08.09 |  | 9364 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.08.10 |  | 9365 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.08.11 |  | 9366 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.08.12 |  | 9367 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.08.13 |  | 9368 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.08.14 |  | 9369 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.08.15 |  | 9370 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.08.16 |  | 9371 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.08.17 |  | 9372 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.08.18 |  | 9349 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.08.19 |  | 9350 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 08 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.08.20 |  | 9351 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) JUL 2015 ( 10 meetings) | 1.01.01.01.03.09 |  | 9352 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 09 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.09.01 |  | 9353 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.09.02 |  | 9354 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.09.03 |  | 9355 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 04 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.09.04 |  | 9356 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.09.05 |  | 9357 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.09.06 |  | 9358 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.09.07 |  | 9359 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.09.08 |  | 9360 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.09.09 |  | 9337 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.09.10 |  | 9338 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.09.11 |  | 9339 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.09.12 |  | 9340 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.09.13 |  | 9341 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.09.14 |  | 9342 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.09.15 |  | 9343 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.09.16 |  | 9344 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.09.17 |  | 9345 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.09.18 |  | 9346 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.09.19 |  | 9347 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 09 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.09.20 |  | 9348 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) AUG 2015 ( 10 meetings) | 1.01.01.01.03.10 |  | 9325 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 10 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.10.01 |  | 9326 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.10.02 |  | 9327 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.10.03 |  | 9328 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.10.04 |  | 9329 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.10.05 |  | 9330 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.10.06 |  | 9331 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.10.07 |  | 9332 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.10.08 |  | 9333 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.10.09 |  | 9334 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 10 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.10.10 |  | 9335 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.10.11 |  | 9336 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.10.12 |  | 9313 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.10.13 |  | 9314 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.10.14 |  | 9315 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.10.15 |  | 9316 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.10.16 |  | 9317 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.10.17 |  | 9318 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.10.18 |  | 9319 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.10.19 |  | 9320 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 10 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.10.20 |  | 9321 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) SEP 2015 ( 10 meetings) | 1.01.01.01.03.11 |  | 9322 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 11 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.11.01 |  | 9323 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.11.02 |  | 9324 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.11.03 |  | 9301 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.11.04 |  | 9302 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.11.05 |  | 9303 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.11.06 |  | 9304 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.11.07 |  | 9305 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.11.08 |  | 9306 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.11.09 |  | 9307 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.11.10 |  | 9308 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.11.11 |  | 9309 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.11.12 |  | 9310 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.11.13 |  | 9311 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.11.14 |  | 9312 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.11.15 |  | 9294 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.11.16 |  | 9295 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.11.17 |  | 9296 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.11.18 |  | 9297 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.11.19 |  | 9298 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 11 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.11.20 |  | 9299 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) OCT 2015 ( 10 meetings) | 1.01.01.01.03.12 |  | 9300 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 12 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.12.01 |  | 9287 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.12.02 |  | 9288 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.12.03 |  | 9289 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.12.04 |  | 9290 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.12.05 |  | 9291 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.12.06 |  | 9292 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.12.07 |  | 9293 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.12.08 |  | 9280 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.12.09 |  | 9281 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.12.10 |  | 9282 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.12.11 |  | 9283 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.12.12 |  | 9284 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.12.13 |  | 9285 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.12.14 |  | 9286 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.12.15 |  | 9177 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.12.16 |  | 9178 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.12.17 |  | 9179 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.12.18 |  | 9180 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.12.19 |  | 9181 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 12 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.12.20 |  | 9182 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) NOV 2015 ( 10 meetings) | 1.01.01.01.03.13 |  | 9183 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 13 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.13.01 |  | 9184 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.13.02 |  | 9185 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.13.03 |  | 9186 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.13.04 |  | 9187 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.13.05 |  | 9188 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.13.06 |  | 9189 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.13.07 |  | 9190 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.13.08 |  | 9191 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.13.09 |  | 9192 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.13.10 |  | 9193 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.13.11 |  | 9194 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.13.12 |  | 9195 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.13.13 |  | 9154 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.13.14 |  | 9155 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.13.15 |  | 9156 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.13.16 |  | 9157 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.13.17 |  | 9158 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.13.18 |  | 9159 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.13.19 |  | 9160 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 13 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.13.20 |  | 9161 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) DEC 2015 ( 10 meetings) | 1.01.01.01.03.14 |  | 9162 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 14 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.14.01 |  | 9163 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.14.02 |  | 9164 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.14.03 |  | 9165 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.14.04 |  | 9166 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.14.05 |  | 9167 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.14.06 |  | 9168 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.14.07 |  | 9169 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.14.08 |  | 9170 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.14.09 |  | 9171 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.14.10 |  | 9172 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.14.11 |  | 9173 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.14.12 |  | 9174 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.14.13 |  | 9133 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.14.14 |  | 9134 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.14.15 |  | 9135 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.14.16 |  | 9136 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.14.17 |  | 9137 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.14.18 |  | 9138 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.14.19 |  | 9139 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 14 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.14.20 |  | 9140 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) JAN 2016 ( 10 meetings) | 1.01.01.01.03.15 |  | 9141 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 15 | 01 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.15.01 |  | 9142 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.15.02 |  | 9143 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.15.03 |  | 9144 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.15.04 |  | 9145 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.15.05 |  | 9146 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.15.06 |  | 9147 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.15.07 |  | 9148 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.15.08 |  | 9149 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.15.09 |  | 9150 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.15.10 |  | 9151 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.15.11 |  | 9152 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.15.12 |  | 9153 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.15.13 |  | 9112 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.15.14 |  | 9113 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.15.15 |  | 9114 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.15.16 |  | 9115 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.15.17 |  | 9116 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.15.18 |  | 9117 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.15.19 |  | 9118 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 15 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.15.20 |  | 9119 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) FEB 2016 ( 10 meetings) | 1.01.01.01.03.16 |  | 9120 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 16 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.16.01 |  | 9121 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.16.02 |  | 9122 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.16.03 |  | 9123 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.16.04 |  | 9124 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.16.05 |  | 9125 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.16.06 |  | 9126 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.16.07 |  | 9127 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.16.08 |  | 9128 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.16.09 |  | 9129 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.16.10 |  | 9130 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.16.11 |  | 9131 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.16.12 |  | 9132 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.16.13 |  | 9091 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.16.14 |  | 9092 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.16.15 |  | 9093 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.16.16 |  | 9094 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.16.17 |  | 9095 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.16.18 |  | 9096 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.16.19 |  | 9097 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 16 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.16.20 |  | 9098 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) MAR 2016 ( 10 meetings) | 1.01.01.01.03.17 |  | 9099 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 17 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.17.01 |  | 9100 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.17.02 |  | 9101 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.17.03 |  | 9102 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.17.04 |  | 9103 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.17.05 |  | 9104 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.17.06 |  | 9105 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.17.07 |  | 9106 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.17.08 |  | 9107 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.17.09 |  | 9108 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.17.10 |  | 9109 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.17.11 |  | 9110 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.17.12 |  | 9111 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.17.13 |  | 8991 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.17.14 |  | 8992 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.17.15 |  | 8993 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.17.16 |  | 8994 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.17.17 |  | 8995 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.17.18 |  | 8996 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.17.19 |  | 8997 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 17 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.17.20 |  | 8998 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) APR 2016 ( 10 meetings) | 1.01.01.01.03.18 |  | 8999 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 18 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.18.01 |  | 9000 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.18.02 |  | 9001 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.18.03 |  | 9002 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.18.04 |  | 9003 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.18.05 |  | 9004 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.18.06 |  | 9005 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.18.07 |  | 9006 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.18.08 |  | 9007 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.18.09 |  | 9008 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.18.10 |  | 9009 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.18.11 |  | 9010 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 12 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.18.12 |  | 9011 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.18.13 |  | 9012 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.18.14 |  | 9013 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.18.15 |  | 9014 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.18.16 |  | 9015 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.18.17 |  | 9016 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.18.18 |  | 9017 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.18.19 |  | 9018 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 18 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.18.20 |  | 9019 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) MAY 2016 ( 10 meetings) | 1.01.01.01.03.19 |  | 9020 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 19 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.19.01 |  | 9021 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.19.02 |  | 9022 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.19.03 |  | 9023 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.19.04 |  | 9024 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.19.05 |  | 9025 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.19.06 |  | 9026 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.19.07 |  | 9027 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.19.08 |  | 9028 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.19.09 |  | 9029 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.19.10 |  | 9030 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.19.11 |  | 9031 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.19.12 |  | 9032 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.19.13 |  | 9033 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.19.14 |  | 9034 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.19.15 |  | 9035 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.19.16 |  | 9036 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.19.17 |  | 9037 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.19.18 |  | 9038 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.19.19 |  | 9039 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 19 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.19.20 |  | 9040 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) JUN 2016 ( 10 meetings) | 1.01.01.01.03.20 |  | 9041 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 20 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.20.1 |  | 9042 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.20.2 |  | 9043 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.20.3 |  | 9044 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.20.4 |  | 9045 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.20.5 |  | 9046 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.20.6 |  | 9047 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.20.7 |  | 9048 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.20.8 |  | 9049 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.20.9 |  | 9050 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.20.10 |  | 9051 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.20.11 |  | 9052 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.20.12 |  | 9053 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.20.13 |  | 9054 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.20.14 |  | 9055 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.20.15 |  | 9056 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.20.16 |  | 9057 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.20.17 |  | 9058 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.20.18 |  | 9059 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.20.19 |  | 9060 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 20 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.20.20 |  | 9061 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) JUL 2016 ( 10 meetings) | 1.01.01.01.03.21 |  | 9062 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 21 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.21.01 |  | 9063 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.21.02 |  | 9064 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.21.03 |  | 9065 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.21.04 |  | 9066 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.21.05 |  | 9067 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.21.06 |  | 9068 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.21.07 |  | 9069 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.21.08 |  | 9070 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.21.09 |  | 9071 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.21.10 |  | 9072 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.21.11 |  | 9073 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.21.12 |  | 9074 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.21.13 |  | 9075 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 14 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.21.14 |  | 9076 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.21.15 |  | 9077 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 16 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.21.16 |  | 9078 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.21.17 |  | 9079 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 18 | [5 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.03.21.18 |  | 9080 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.21.19 |  | 9081 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 21 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.21.20 |  | 9082 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) AUG 2016 ( 10 meetings) | 1.01.01.01.03.22 |  | 9083 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 22 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.22.01 |  | 9084 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.22.02 |  | 9085 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.22.03 |  | 9086 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.22.04 |  | 9087 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.22.05 |  | 9088 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.22.06 |  | 9089 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.22.07 |  | 9090 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.22.08 |  | 8981 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.22.09 |  | 8982 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.22.10 |  | 8983 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.22.11 |  | 8984 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.22.12 |  | 8985 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.22.13 |  | 8986 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.22.14 |  | 8987 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.22.15 |  | 8988 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.22.16 |  | 8989 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.22.17 |  | 8990 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.22.18 |  | 8971 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.22.19 |  | 8972 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.22.20 |  | 8973 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 21 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.22.21 |  | 12245 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 22 | 22 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.22.22 |  | 12246 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | [6 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Technologies Providers (5.1.3) SEP 2016 ( 10 meetings) | 1.01.01.01.03.23 |  | 12248 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 03 | 23 | 01 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.23.01 |  | 12249 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 02 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.23.02 |  | 12250 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 03 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.23.03 |  | 12251 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 04 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.23.04 |  | 12252 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 05 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.23.05 |  | 12253 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 06 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.23.06 |  | 12254 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 07 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.23.07 |  | 12255 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 08 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.23.08 |  | 12256 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 09 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.23.09 |  | 12257 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 10 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.23.10 |  | 12258 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 11 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.23.11 |  | 12259 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 12 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.23.12 |  | 12260 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 13 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.23.13 |  | 12261 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 14 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.23.14 |  | 12262 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 15 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.23.15 |  | 12263 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 16 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.23.16 |  | 12264 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 17 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.23.17 |  | 12265 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 18 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.23.18 |  | 12266 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 19 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.23.19 |  | 12267 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 20 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.23.20 |  | 12268 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 21 | [5 empty] | Webcast on Cybersecurity Issues | 1.01.01.01.03.23.21 |  | 12269 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 03 | 23 | 22 | [5 empty] | Produce and Deliver Technology Capabilities Meeting Minutes Report | 1.01.01.01.03.23.22 |  | 12270 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | [7 empty] | Review Findings from Meetings (5.1.4) | 1.01.01.01.04 | 1.5.1.4 | 6692 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 04 | 01 | [6 empty] | Produce Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) | 1.01.01.01.04.01 | 1.5.1.4.1 | 6693 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 04 | 01 | 01 | [5 empty] | Produce 2014 OCT | 1.01.01.01.04.01.01 |  | 8870 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 02 | [5 empty] | Produce 2014 NOV | 1.01.01.01.04.01.02 |  | 8869 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 03 | [5 empty] | Produce 2014 DEC | 1.01.01.01.04.01.03 |  | 8868 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 04 | [5 empty] | Produce 2015 JAN | 1.01.01.01.04.01.04 |  | 8867 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 05 | [5 empty] | Produce 2015 FEB | 1.01.01.01.04.01.05 |  | 8866 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 06 | [5 empty] | Produce 2015 MAR | 1.01.01.01.04.01.06 |  | 8865 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 07 | [5 empty] | Produce 2015 APR | 1.01.01.01.04.01.07 |  | 8864 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 08 | [5 empty] | Produce 2015 MAY | 1.01.01.01.04.01.08 |  | 8863 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 09 | [5 empty] | Produce 2015 JUN | 1.01.01.01.04.01.09 |  | 8862 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 10 | [5 empty] | Produce 2015 JUL | 1.01.01.01.04.01.10 |  | 8861 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 11 | [5 empty] | Produce 2015 AUG | 1.01.01.01.04.01.11 |  | 8860 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 12 | [5 empty] | Produce 2015 SEP | 1.01.01.01.04.01.12 |  | 8859 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 13 | [5 empty] | Produce 2015 OCT | 1.01.01.01.04.01.13 |  | 8858 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 14 | [5 empty] | Produce 2015 NOV | 1.01.01.01.04.01.14 |  | 8857 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 15 | [5 empty] | Produce 2015 DEC | 1.01.01.01.04.01.15 |  | 8856 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 16 | [5 empty] | Produce 2016 JAN | 1.01.01.01.04.01.16 |  | 8855 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 17 | [5 empty] | Produce 2016 FEB | 1.01.01.01.04.01.17 |  | 8854 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 18 | [5 empty] | Produce 2016 MAR | 1.01.01.01.04.01.18 |  | 8853 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 19 | [5 empty] | Produce 2016 APR | 1.01.01.01.04.01.19 |  | 8852 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 20 | [5 empty] | Produce 2016 MAY | 1.01.01.01.04.01.20 |  | 8851 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 21 | [5 empty] | Produce 2016 JUN | 1.01.01.01.04.01.21 |  | 8850 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 22 | [5 empty] | Produce 2016 JUL | 1.01.01.01.04.01.22 |  | 8849 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 23 | [5 empty] | Produce 2016 AUG | 1.01.01.01.04.01.23 |  | 8848 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 01 | 24 | [5 empty] | Produce 2016 SEP | 1.01.01.01.04.01.24 |  | 9684 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 02 | [6 empty] | Receive COR Response on Monthly recommended Use Case (5.1.4.2) | 1.01.01.01.04.02 |  | 9656 | S | 1 day |  | 0
1 | 01 | 01 | 01 | 04 | 02 | 01 | [5 empty] | COR Approval of Use Case 1 Use Case - Oct 2014 (Use Case 1) | 1.01.01.01.04.02.01 |  | 9661 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 04 | 02 | 02 | [5 empty] | COR Approval of Use Case 2 Use Case - Nov 2014 (Use Case 2) | 1.01.01.01.04.02.02 |  | 9660 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 03 | [5 empty] | COR Approval of Use Case 3 Use Case - Dec 2014 (Use Case 3) | 1.01.01.01.04.02.03 |  | 9659 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 04 | [5 empty] | COR Approval of Use Case 4 Use Case - Jan 2015 (Use Case 4) | 1.01.01.01.04.02.04 |  | 9664 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 05 | [5 empty] | COR Approval of Use Case 5 Use Case - Feb 2015 (Use Case 5) | 1.01.01.01.04.02.05 |  | 9663 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 06 | [5 empty] | COR Approval of Use Case 6 Use Case - Mar 2015 (Use Case 6) | 1.01.01.01.04.02.06 |  | 9662 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 07 | [5 empty] | COR Approval of Use Case 7 Use Case - Apr 2015 (Use Case 7) | 1.01.01.01.04.02.07 |  | 9658 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 08 | [5 empty] | COR Approval of Use Case 8 Use Case - May - 2015 (Use Case 8) | 1.01.01.01.04.02.08 |  | 9670 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 09 | [5 empty] | COR Approval of Use Case 9 Use Case - Jun - 2015 (Use Case 9) | 1.01.01.01.04.02.09 |  | 9669 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 10 | [5 empty] | COR Approval of Use Case 10 Use Case - Jul 2015 (Use Case 10) | 1.01.01.01.04.02.10 |  | 9668 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 11 | [5 empty] | COR Approval of Use Case 11 Use Case - Aug - 2015 (Use Case 11) | 1.01.01.01.04.02.11 |  | 9667 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 12 | [5 empty] | COR Approval of Use Case 12 Use Case - Sep 2015 (Use Case 12) | 1.01.01.01.04.02.12 |  | 9666 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 13 | [5 empty] | COR Approval of Use Case 13 Use Case - Oct 2015 (Use Case 13) | 1.01.01.01.04.02.13 |  | 9682 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 14 | [5 empty] | COR Approval of Use Case 14 Use Case - Nov 2015 (Use Case 14) | 1.01.01.01.04.02.14 |  | 9681 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 15 | [5 empty] | COR Approval of Use Case 15 Use Case - Dec 2015 (Use Case 15) | 1.01.01.01.04.02.15 |  | 9680 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 16 | [5 empty] | COR Approval of Use Case 16 Use Case - Jan 2016 (Use Case 16) | 1.01.01.01.04.02.16 |  | 9679 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 17 | [5 empty] | COR Approval of Use Case 17 Use Case - Feb 2016 (Use Case 17) | 1.01.01.01.04.02.17 |  | 9678 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 18 | [5 empty] | COR Approval of Use Case 18 Use Case - Mar 2016 (Use Case 18) | 1.01.01.01.04.02.18 |  | 9677 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 19 | [5 empty] | COR Approval of Use Case 19 Use Case - Apr 2016 (Use Case 19) | 1.01.01.01.04.02.19 |  | 9676 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 20 | [5 empty] | COR Approval of Use Case 20 Use Case - May 2016 (Use Case 20) | 1.01.01.01.04.02.20 |  | 9675 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 21 | [5 empty] | COR Approval of Use Case 21 Use Case - Jun 2016 (Use Case 21) | 1.01.01.01.04.02.21 |  | 9674 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 22 | [5 empty] | COR Approval of Use Case 22 Use Case - Jul 2016 (Use Case 22) | 1.01.01.01.04.02.22 |  | 9673 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 23 | [5 empty] | COR Approval of Use Case 23 Use Case - Aug 2016 (Use Case 23) | 1.01.01.01.04.02.23 |  | 9672 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 04 | 02 | 24 | [5 empty] | COR Approval of Use Case 24 Use Case - Sep 2016 (Use Case 24) | 1.01.01.01.04.02.24 |  | 9671 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 05 | [7 empty] | Prepare and Execute the " Quarterly Use Case Requirements Conference Agenda (Conformant to NDD-1) (5.1.5) | 1.01.01.01.05 | 1.5.1.5 | 6694 | M | 0 days |  | 0
1 | 01 | 01 | 01 | 05 | 01 | [6 empty] | Prepare Quarterly Meeting Agenda and Conviene Meeting Nov 2014 | 1.01.01.01.05.01 | 1.5.1.5 | 8876 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 05 | 02 | [6 empty] | Prepare Quarterly Meeting Agenda and Conviene Meeting Mar 2015 | 1.01.01.01.05.02 | 1.5.1.5 | 8875 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 05 | 03 | [6 empty] | Prepare Quarterly Meeting Agenda and Conviene Meeting Jul 2015 | 1.01.01.01.05.03 | 1.5.1.5 | 8874 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 05 | 04 | [6 empty] | Prepare Quarterly Meeting Agenda and Conviene Meeting Nov 2015 | 1.01.01.01.05.04 | 1.5.1.5 | 8873 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 05 | 05 | [6 empty] | Prepare Quarterly Meeting Agenda and Conviene Meeting Mar 2016 | 1.01.01.01.05.05 | 1.5.1.5 | 8872 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 05 | 06 | [6 empty] | Prepare Quarterly Meeting Agenda and Conviene Meeting Jul 2016 | 1.01.01.01.05.06 | 1.5.1.5 | 8871 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 06 | [7 empty] | Prepare and Execute the " Quarterly Use Case Requirements Conference Minutes (Conformant to NDD-2) (5.1.6) | 1.01.01.01.06 | 1.5.1.6 | 6695 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 06 | 01 | [6 empty] | Prepare Quarterly Meeting Minutes for Nov 2014 | 1.01.01.01.06.01 |  | 8890 | T | 2 days | 16 | 18.6654 |  |  | 0.23415 | [7 empty] | 1.2176 |  |  | 3.4263 | 3.122 |  |  |  |  | 3.0595 | 1.4673 | [7 empty] | 3.5278 | [18 empty] | 0.28098 | [19 empty] | 0.71805 | [6 empty] | 0.19902 |  |  | 1.4127
1 | 01 | 01 | 01 | 06 | 02 | [6 empty] | Prepare Quarterly Meeting Minutes for Mar 2015 | 1.01.01.01.06.02 |  | 8889 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 06 | 03 | [6 empty] | Use Case Rejected Use Case 3, Use Case 5 | 1.01.01.01.06.03 |  | 9926 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 06 | 04 | [6 empty] | Prepare Quarterly Meeting Minutes for Jul 2015 | 1.01.01.01.06.04 |  | 8888 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 06 | 05 | [6 empty] | Use Use Case Rejected Use Case 7, Use Case 10 | 1.01.01.01.06.05 |  | 9928 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 06 | 06 | [6 empty] | Prepare Quarterly Meeting Minutes for Nov 2015 | 1.01.01.01.06.06 |  | 8887 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 06 | 07 | [6 empty] | Use Case Rejected Use Case 12 | 1.01.01.01.06.07 |  | 9929 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 06 | 08 | [6 empty] | Prepare Quarterly Meeting Minutes for Mar 2016 | 1.01.01.01.06.08 |  | 8886 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 06 | 09 | [6 empty] | Use Case Rejected Use Case 16 , Use Case 17 | 1.01.01.01.06.09 |  | 9930 | M | 0 days | 0 | 0
1 | 01 | 01 | 01 | 06 | 10 | [6 empty] | Prepare Quarterly Meeting Minutes for Jul 2016 | 1.01.01.01.06.10 |  | 8885 | T | 1 day | 8 | 9.3327 |  |  | 0.11707 | [7 empty] | 0.60878 |  |  | 1.7132 | 1.561 |  |  |  |  | 1.5298 | 0.73366 | [7 empty] | 1.7639 | [18 empty] | 0.14049 | [19 empty] | 0.35902 | [6 empty] | 0.099512 |  |  | 0.70634
1 | 01 | 01 | 01 | 06 | 11 | [6 empty] | Use Cases Rejected Use Case 23 , Use Case 24 | 1.01.01.01.06.11 |  | 9931 | M | 0 days | 0 | 0 |  |  | 0
| 01 | 01 | 01 | [8 empty] | Total Phase 1 | 1.01.01.01 |  |  | A |  | 8200 | 9566 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624 | 0 | 0 | 1756 | 1600 | 0 | 0 | 0 | 0 | 1568 | 752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 0 | 0 | 724 | 0 | 0 | 0 | 0
1 | 01 | 02 | [9 empty] | Phase 2 | 1.01.02 |  | 21880 | C | 490 days |  | 10686.52
1 | 01 | 02 | 01 | [8 empty] | Use Case Definitions (5.2) | 1.01.02.01 | 1.5.2 | 6696 | W | 490 days |  | 10686.52 | [9 empty] | 240 | 491 |  |  | 1856 | 1792 | 2112 |  |  |  | 1424 |  |  |  | 201.92 |  |  |  |  | 1744 | [21 empty] | 134.4 | [16 empty] | 336 | [6 empty] | 67.2 |  |  | 288
1 | 01 | 02 | 01 | 01 | [7 empty] | Create Use Case Definition Work Plan (5.2.1) | 1.01.02.01.01 | 1.5.2.1 | 6699 | S | 490 days |  | 0 | [9 empty] | 0 |  |  |  |  | 0
1 | 01 | 02 | 01 | 01 | 01 | [6 empty] | Use Case 1 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.01 | 1.5.2.1 | 9421 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 02 | [6 empty] | Use Case 2 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.02 |  | 9743 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 03 | [6 empty] | Use Case 4 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.03 |  | 9907 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 04 | 04 | [5 empty] | Use Case 5 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.04 |  | 9924 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 05 | [6 empty] | Use Case 6 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.05 |  | 9918 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 06 | [6 empty] | Use Case 8 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.06 |  | 9919 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 07 | [6 empty] | Use Case 9 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.07 |  | 9921 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 08 | [6 empty] | Use Case 11 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.08 |  | 9922 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 09 | [6 empty] | Use Case 13 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.09 |  | 9933 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 10 | [6 empty] | Use Case 14 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.10 |  | 9935 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 11 | [6 empty] | Use Case 15 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.11 |  | 9934 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 12 | [6 empty] | Use Case 18 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.12 |  | 9936 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 13 | [6 empty] | Use Case 19 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.13 |  | 9937 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 14 | [6 empty] | Use Case 20 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.14 |  | 9938 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 15 | [6 empty] | Use Case 22 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.15 |  | 9939 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 01 | 16 | [6 empty] | Use Case 24 Develop a Use Case Work Plan Definitions | 1.01.02.01.01.16 |  | 9940 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 02 | [7 empty] | Conduct Use Case Technology Meeting (5.2.2) | 1.01.02.01.02 | 1.5.2.2 | 6700 | S | 132 days |  | 3.0551 | [9 empty] | 0 | [5 empty] | 3.0551
1 | 01 | 02 | 01 | 02 | 01 | [6 empty] | Meetings spanning 2 months (5.2.2.1) | 1.01.02.01.02.01 | 1.5.2.2 | 6701 | S | 132 days |  | 3.0551 | [9 empty] | 0 | [5 empty] | 3.0551
1 | 01 | 02 | 01 | 02 | 01 | 01 | [5 empty] | Use Case 1 Work Plan Discussion Meetings | 1.01.02.01.02.01.01 |  | 9422 | S | 47 days |  | 3.0551 | [9 empty] | 0 | [5 empty] | 3.0551
1 | 01 | 02 | 01 | 02 | 01 | 01 | 01 |  |  |  |  | Use Case 1 Workplan Discussion Mtg #1 | 1.01.02.01.02.01.01.01 |  | 9459 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 02 |  |  |  |  | Use Case 1 Mtg #1 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.02 |  | 9460 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 03 |  |  |  |  | Use Case 1 Worplan Discussion Mtg #2 | 1.01.02.01.02.01.01.03 |  | 9461 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 04 |  |  |  |  | Use Case 1 Mtg #2 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.04 |  | 9462 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 05 |  |  |  |  | Use Case 1 Workplan Discussion Mtg #3 | 1.01.02.01.02.01.01.05 |  | 9463 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 06 |  |  |  |  | Use Case 1 Mtg #3 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.06 |  | 9464 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 07 |  |  |  |  | Use Case 1 Workplan Discussion Mtg #4 | 1.01.02.01.02.01.01.07 |  | 9465 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 08 |  |  |  |  | Use Case 1 Mtg #4 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.08 |  | 9466 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 09 |  |  |  |  | Use Case 1 Workplan Discussion Mtg #5 | 1.01.02.01.02.01.01.09 |  | 9467 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 10 |  |  |  |  | Use Case 1 Mtg #5 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.10 |  | 9468 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 11 |  |  |  |  | Use Case 1 Workplan Discussion Mtg #6 | 1.01.02.01.02.01.01.11 |  | 9469 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 12 |  |  |  |  | Use Case 1 Mtg #6 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.12 |  | 9470 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 13 |  |  |  |  | Use Case 1 Workplan Discussion Mtg #7 | 1.01.02.01.02.01.01.13 |  | 9471 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 14 |  |  |  |  | Use Case 1 Mtg #7 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.14 |  | 9472 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 15 |  |  |  |  | Use Case 1 Workplan Discussion Mtg #8 | 1.01.02.01.02.01.01.15 |  | 9473 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 16 |  |  |  |  | Use Case 1 Mtg #8 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.16 |  | 9474 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 17 |  |  |  |  | Use Case 1 Workplan Discussion Mtg #9 | 1.01.02.01.02.01.01.17 |  | 9475 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 18 |  |  |  |  | Use Case 1 Mtg #9 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.18 |  | 9476 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 19 |  |  |  |  | Use Case 1 Workplan Discussion Mtg #10 | 1.01.02.01.02.01.01.19 |  | 9477 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 20 |  |  |  |  | Use Case 1 Mtg #10 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.20 |  | 9478 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 21 |  |  |  |  | Use Case 1 Workplan Discussion Mtg #11 | 1.01.02.01.02.01.01.21 |  | 9479 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 22 |  |  |  |  | Use Case 1 Mtg #11 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.22 |  | 9480 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 23 |  |  |  |  | Use Case 1 Workplan Discussion Mtg #12 | 1.01.02.01.02.01.01.23 |  | 9481 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 01 | 24 |  |  |  |  | Use Case 1 Mtg #12 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.01.24 |  | 9482 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | [5 empty] | Use Case 2 Work Plan Discussion Meetings | 1.01.02.01.02.01.02 |  | 9746 | S | 41 days |  | 3.0551 | [9 empty] | 0 | [5 empty] | 3.0551
x | 01 | 02 | 01 | 02 | 01 | 02 | 01 |  |  |  |  | Use Case 2 Workplan Discussion Mtg #1 | 1.01.02.01.02.01.02.01 |  | 9747 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 02 |  |  |  |  | Use Case 2 Mtg #1 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.02.02 |  | 9748 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 03 |  |  |  |  | Use Case 2 Worplan Discussion Mtg #2 | 1.01.02.01.02.01.02.03 |  | 9749 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 04 |  |  |  |  | Use Case 2 Mtg #2 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.02.04 |  | 9750 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 05 |  |  |  |  | Use Case 2 Worplan Discussion Mtg #3 | 1.01.02.01.02.01.02.05 |  | 9751 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 06 |  |  |  |  | Use Case 2 Mtg #3 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.02.06 |  | 9752 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 07 |  |  |  |  | Use Case 2 Worplan Discussion Mtg #4 | 1.01.02.01.02.01.02.07 |  | 9753 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 08 |  |  |  |  | Use Case 2 Mtg #4 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.02.08 |  | 9754 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 09 |  |  |  |  | Use Case 2 Worplan Discussion Mtg #5 | 1.01.02.01.02.01.02.09 |  | 9755 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 10 |  |  |  |  | Use Case 2 Mtg #5 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.02.10 |  | 9756 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 11 |  |  |  |  | Use Case 2 Worplan Discussion Mtg #6 | 1.01.02.01.02.01.02.11 |  | 9757 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 12 |  |  |  |  | Use Case 2 Mtg #6 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.02.12 |  | 9758 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 13 |  |  |  |  | Use Case 2 Worplan Discussion Mtg #7 | 1.01.02.01.02.01.02.13 |  | 9759 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 14 |  |  |  |  | Use Case 2 Mtg #7 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.02.14 |  | 9760 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 15 |  |  |  |  | Use Case 2 Worplan Discussion Mtg #8 | 1.01.02.01.02.01.02.15 |  | 9761 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 16 |  |  |  |  | Use Case 2 Mtg #8 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.02.16 |  | 9762 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 17 |  |  |  |  | Use Case 2 Worplan Discussion Mtg #9 | 1.01.02.01.02.01.02.17 |  | 9763 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 18 |  |  |  |  | Use Case 2 Mtg #9 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.02.18 |  | 9764 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 19 |  |  |  |  | Use Case 2 Worplan Discussion Mtg #10 | 1.01.02.01.02.01.02.19 |  | 9765 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 02 | 20 |  |  |  |  | Use Case 2 Mtg #10 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.02.20 |  | 9766 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | [5 empty] | Use Case 4 Work Plan Discussion Meetings | 1.01.02.01.02.01.03 |  | 10709 | S | 38 days |  | 0 | [9 empty] | 0 | [5 empty] | 0
1 | 01 | 02 | 01 | 02 | 01 | 03 | 01 |  |  |  |  | Use Case 4 Workplan Discussion Mtg #1 | 1.01.02.01.02.01.03.01 |  | 10710 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 02 |  |  |  |  | Use Case 4 Mtg #1 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.03.02 |  | 10711 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 03 |  |  |  |  | Use Case 4 Worplan Discussion Mtg #2 | 1.01.02.01.02.01.03.03 |  | 10712 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 04 |  |  |  |  | Use Case 4 Mtg #2 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.03.04 |  | 10713 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 05 |  |  |  |  | Use Case 4 Worplan Discussion Mtg #3 | 1.01.02.01.02.01.03.05 |  | 10714 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 06 |  |  |  |  | Use Case 4 Mtg #3 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.03.06 |  | 10715 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 07 |  |  |  |  | Use Case 4 Worplan Discussion Mtg #4 | 1.01.02.01.02.01.03.07 |  | 10716 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 08 |  |  |  |  | Use Case 4 Mtg #4 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.03.08 |  | 10717 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 09 |  |  |  |  | Use Case 4 Worplan Discussion Mtg #5 | 1.01.02.01.02.01.03.09 |  | 10718 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 10 |  |  |  |  | Use Case 4 Mtg #5 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.03.10 |  | 10719 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 11 |  |  |  |  | Use Case 4 Worplan Discussion Mtg #6 | 1.01.02.01.02.01.03.11 |  | 10720 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 12 |  |  |  |  | Use Case 4 Mtg #6 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.03.12 |  | 10721 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 13 |  |  |  |  | Use Case 4 Worplan Discussion Mtg #7 | 1.01.02.01.02.01.03.13 |  | 10722 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 14 |  |  |  |  | Use Case 4 Mtg #7 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.03.14 |  | 10723 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 15 |  |  |  |  | Use Case 4 Worplan Discussion Mtg #8 | 1.01.02.01.02.01.03.15 |  | 10724 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 16 |  |  |  |  | Use Case 4 Mtg #8 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.03.16 |  | 10725 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 17 |  |  |  |  | Use Case 4 Worplan Discussion Mtg #9 | 1.01.02.01.02.01.03.17 |  | 10726 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 03 | 18 |  |  |  |  | Use Case 4 Mtg #9 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.03.18 |  | 10727 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | [5 empty] | Use Case 6 Work Plan Discussion Meetings | 1.01.02.01.02.01.04 |  | 10742 | S | 40 days |  | 0 | [9 empty] | 0 | [5 empty] | 0
1 | 01 | 02 | 01 | 02 | 01 | 04 | 01 |  |  |  |  | Use Case 6 Workplan Discussion Mtg #1 | 1.01.02.01.02.01.04.01 |  | 10743 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 02 |  |  |  |  | Use Case 6 Mtg #1 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.04.02 |  | 10744 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 03 |  |  |  |  | Use Case 6 Worplan Discussion Mtg #2 | 1.01.02.01.02.01.04.03 |  | 10745 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 04 |  |  |  |  | Use Case 6 Mtg #2 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.04.04 |  | 10746 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 05 |  |  |  |  | Use Case 6 Worplan Discussion Mtg #3 | 1.01.02.01.02.01.04.05 |  | 10747 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 06 |  |  |  |  | Use Case 6 Mtg #3 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.04.06 |  | 10748 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 07 |  |  |  |  | Use Case 6 Worplan Discussion Mtg #4 | 1.01.02.01.02.01.04.07 |  | 10749 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 08 |  |  |  |  | Use Case 6 Mtg #4 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.04.08 |  | 10750 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 09 |  |  |  |  | Use Case 6 Worplan Discussion Mtg #5 | 1.01.02.01.02.01.04.09 |  | 10751 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 10 |  |  |  |  | Use Case 6 Mtg #5 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.04.10 |  | 10752 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 11 |  |  |  |  | Use Case 6 Worplan Discussion Mtg #6 | 1.01.02.01.02.01.04.11 |  | 10753 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 12 |  |  |  |  | Use Case 6 mtg #6 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.04.12 |  | 10754 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 13 |  |  |  |  | Use Case 6 Worplan Discussion Mtg #7 | 1.01.02.01.02.01.04.13 |  | 10755 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 14 |  |  |  |  | Use Case 6 Mtg #7 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.04.14 |  | 10756 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 15 |  |  |  |  | Use Case 6 Worplan Discussion Mtg #8 | 1.01.02.01.02.01.04.15 |  | 10757 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 02 | 01 | 04 | 16 |  |  |  |  | Use Case 6 Mtg #8 Deliver Use Case Requirements Meeting Report | 1.01.02.01.02.01.04.16 |  | 10758 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | [7 empty] | Conduct meetings to define further each approved use Case by the COR and Deliver to the COR the Meeting Minutes | 1.01.02.01.03 |  | 9644 | S | 197 days |  | 0 | [9 empty] | 0 | [5 empty] | 0
1 | 01 | 02 | 01 | 03 | 01 | [6 empty] | Use Case 1 Meetings spanning 3 months (5.2.3) | 1.01.02.01.03.01 |  | 9645 | S | 64 days |  | 0 | [9 empty] | 0 | [5 empty] | 0
1 | 01 | 02 | 01 | 03 | 01 | 01 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #1 | 1.01.02.01.03.01.01 |  | 9646 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 02 | [5 empty] | Use Case 1 Mtg #1 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.02 |  | 9647 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 03 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #2 | 1.01.02.01.03.01.03 |  | 9648 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 04 | [5 empty] | Use Case 1 Mtg #2 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.04 |  | 9649 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 05 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #3 | 1.01.02.01.03.01.05 |  | 9650 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 06 | [5 empty] | Use Case 1 Mtg #3 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.06 |  | 9651 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 07 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #4 | 1.01.02.01.03.01.07 |  | 9652 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 08 | [5 empty] | Use Case 1 Mtg #4 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.08 |  | 9635 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 09 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #5 | 1.01.02.01.03.01.09 |  | 9636 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 10 | [5 empty] | Use Case 1 Mtg #5 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.10 |  | 9637 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 11 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #6 | 1.01.02.01.03.01.11 |  | 9638 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 12 | [5 empty] | Use Case 1 Mtg #16 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.12 |  | 9639 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 13 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #7 | 1.01.02.01.03.01.13 |  | 9640 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 14 | [5 empty] | Use Case 1 Mtg #7 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.14 |  | 9641 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 15 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #8 | 1.01.02.01.03.01.15 |  | 9642 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 16 | [5 empty] | Use Case 1 Mtg #8 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.16 |  | 9643 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 17 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #9 | 1.01.02.01.03.01.17 |  | 9626 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 18 | [5 empty] | Use Case 1 Mtg #9 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.18 |  | 9627 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 19 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #10 | 1.01.02.01.03.01.19 |  | 9628 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 20 | [5 empty] | Use Case 1 Mtg #10 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.20 |  | 9629 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 21 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #11 | 1.01.02.01.03.01.21 |  | 9630 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 22 | [5 empty] | Use Case 1 Mtg #11 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.22 |  | 9631 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 23 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #12 | 1.01.02.01.03.01.23 |  | 9632 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 24 | [5 empty] | Use Case 1 Mtg #12 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.24 |  | 9633 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 25 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #13 | 1.01.02.01.03.01.25 |  | 9634 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 26 | [5 empty] | Use Case 1 Mtg #13 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.26 |  | 9617 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 27 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #14 | 1.01.02.01.03.01.27 |  | 9618 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 28 | [5 empty] | Use Case 1 Mtg #14 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.28 |  | 9619 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 29 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #15 | 1.01.02.01.03.01.29 |  | 9620 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 30 | [5 empty] | Use Case 1 Mtg #15 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.30 |  | 9621 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 31 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #16 | 1.01.02.01.03.01.31 |  | 9622 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 32 | [5 empty] | Use Case 1 Mtg #16 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.32 |  | 9623 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 33 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #17 | 1.01.02.01.03.01.33 |  | 9624 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 34 | [5 empty] | Use Case 1 Mtg #17 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.34 |  | 9625 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 35 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #18 | 1.01.02.01.03.01.35 |  | 9608 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 36 | [5 empty] | Use Case 1 Mtg #18 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.36 |  | 9609 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 37 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #19 | 1.01.02.01.03.01.37 |  | 9610 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 38 | [5 empty] | Use Case 1 Mtg #19 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.38 |  | 9611 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 39 | [5 empty] | Use Case 1 Further Definition Meeting Mtg #20 | 1.01.02.01.03.01.39 |  | 9612 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 01 | 40 | [5 empty] | Use Case 1 Mtg #20 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.01.40 |  | 9613 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | [6 empty] | Use Case 2 Meetings spanning 3 months (5.2.3) | 1.01.02.01.03.02 |  | 9780 | S | 61 days |  | 0 | [9 empty] | 0 | [5 empty] | 0
1 | 01 | 02 | 01 | 03 | 02 | 01 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #1 | 1.01.02.01.03.02.01 |  | 9781 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 02 | [5 empty] | Use Case 2 Mtg #1 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.02 |  | 9782 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 03 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #2 | 1.01.02.01.03.02.03 |  | 9783 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 04 | [5 empty] | Use Case 2 Mtg #2 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.04 |  | 9784 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 05 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #3 | 1.01.02.01.03.02.05 |  | 9785 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 06 | [5 empty] | Use Case 2 Mtg #3 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.06 |  | 9786 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 07 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #4 | 1.01.02.01.03.02.07 |  | 9787 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 08 | [5 empty] | Use Case 2 Mtg #4 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.08 |  | 9788 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 09 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #5 | 1.01.02.01.03.02.09 |  | 9789 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 10 | [5 empty] | Use Case 2 Mtg #5 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.10 |  | 9790 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 11 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #6 | 1.01.02.01.03.02.11 |  | 9791 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 12 | [5 empty] | Use Case 2 Mtg #16 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.12 |  | 9792 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 13 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #7 | 1.01.02.01.03.02.13 |  | 9793 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 14 | [5 empty] | Use Case 2 Mtg #7 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.14 |  | 9794 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 15 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #8 | 1.01.02.01.03.02.15 |  | 9795 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 16 | [5 empty] | Use Case 2 Mtg #8 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.16 |  | 9796 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 17 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #9 | 1.01.02.01.03.02.17 |  | 9797 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 18 | [5 empty] | Use Case 2 Mtg #9 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.18 |  | 9798 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 19 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #10 | 1.01.02.01.03.02.19 |  | 9799 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 20 | [5 empty] | Use Case 2 Mtg #10 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.20 |  | 9800 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 21 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #11 | 1.01.02.01.03.02.21 |  | 9801 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 22 | [5 empty] | Use Case 2 Mtg #11 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.22 |  | 9802 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 23 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #12 | 1.01.02.01.03.02.23 |  | 9803 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 24 | [5 empty] | Use Case 2 Mtg #12 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.24 |  | 9804 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 25 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #13 | 1.01.02.01.03.02.25 |  | 9805 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 26 | [5 empty] | Use Case 2 Mtg #13 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.26 |  | 9806 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 27 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #14 | 1.01.02.01.03.02.27 |  | 9807 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 28 | [5 empty] | Use Case 2 Mtg #14 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.28 |  | 9808 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 29 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #15 | 1.01.02.01.03.02.29 |  | 9809 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 30 | [5 empty] | Use Case 2 Mtg #15 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.30 |  | 9810 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 31 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #16 | 1.01.02.01.03.02.31 |  | 9811 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 32 | [5 empty] | Use Case 2 Mtg #16 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.32 |  | 9812 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 33 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #17 | 1.01.02.01.03.02.33 |  | 9813 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 34 | [5 empty] | Use Case 2 Mtg #17 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.34 |  | 9814 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 35 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #18 | 1.01.02.01.03.02.35 |  | 9815 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 36 | [5 empty] | Use Case 2 Mtg #18 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.36 |  | 9816 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 37 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #19 | 1.01.02.01.03.02.37 |  | 9817 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 38 | [5 empty] | Use Case 2 Mtg #19 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.38 |  | 9818 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 39 | [5 empty] | Use Case 2 Further Definition Meeting Mtg #20 | 1.01.02.01.03.02.39 |  | 9819 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 02 | 40 | [5 empty] | Use Case 2 Mtg #20 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.02.40 |  | 9820 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | [6 empty] | Use Case 4 Meetings spanning 3 months (5.2.3) | 1.01.02.01.03.03 |  | 10776 | S | 61 days |  | 0 | [9 empty] | 0 | [5 empty] | 0
1 | 01 | 02 | 01 | 03 | 03 | 01 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #1 | 1.01.02.01.03.03.01 |  | 10777 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 02 | [5 empty] | Use Case 4 Mtg #1 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.02 |  | 10778 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 03 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #2 | 1.01.02.01.03.03.03 |  | 10779 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 04 | [5 empty] | Use Case 4 Mtg #4 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.04 |  | 10780 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 05 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #3 | 1.01.02.01.03.03.05 |  | 10781 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 06 | [5 empty] | Use Case 4 Mtg #3 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.06 |  | 10782 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 07 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #4 | 1.01.02.01.03.03.07 |  | 10783 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 08 | [5 empty] | Use Case 4 Mtg #4 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.08 |  | 10784 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 09 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #5 | 1.01.02.01.03.03.09 |  | 10785 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 10 | [5 empty] | Use Case 4 Mtg #5 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.10 |  | 10786 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 11 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #6 | 1.01.02.01.03.03.11 |  | 10787 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 12 | [5 empty] | Use Case 4 Mtg #16 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.12 |  | 10788 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 13 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #7 | 1.01.02.01.03.03.13 |  | 10789 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 14 | [5 empty] | Use Case 4 Mtg #7 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.14 |  | 10790 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 15 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #8 | 1.01.02.01.03.03.15 |  | 10791 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 16 | [5 empty] | Use Case 4 Mtg #8 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.16 |  | 10792 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 17 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #9 | 1.01.02.01.03.03.17 |  | 10793 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 18 | [5 empty] | Use Case 4 Mtg #9 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.18 |  | 10794 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 19 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #10 | 1.01.02.01.03.03.19 |  | 10795 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 20 | [5 empty] | Use Case 4 Mtg #10 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.20 |  | 10796 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 21 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #11 | 1.01.02.01.03.03.21 |  | 10797 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 22 | [5 empty] | Use Case 4 Mtg #11 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.22 |  | 10798 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 23 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #12 | 1.01.02.01.03.03.23 |  | 10799 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 24 | [5 empty] | Use Case 4 Mtg #12 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.24 |  | 10800 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 25 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #13 | 1.01.02.01.03.03.25 |  | 10801 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 26 | [5 empty] | Use Case 4 Mtg #13 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.26 |  | 10802 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 27 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #14 | 1.01.02.01.03.03.27 |  | 10803 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 28 | [5 empty] | Use Case 4 Mtg #14 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.28 |  | 10804 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 29 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #15 | 1.01.02.01.03.03.29 |  | 10805 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 30 | [5 empty] | Use Case 4 Mtg #15 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.30 |  | 10806 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 31 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #16 | 1.01.02.01.03.03.31 |  | 10807 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 32 | [5 empty] | Use Case 4 Mtg #16 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.32 |  | 10808 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 33 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #17 | 1.01.02.01.03.03.33 |  | 10809 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 34 | [5 empty] | Use Case 4 Mtg #17 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.34 |  | 10810 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 35 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #18 | 1.01.02.01.03.03.35 |  | 10811 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 36 | [5 empty] | Use Case 4 Mtg #18 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.36 |  | 10812 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 37 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #19 | 1.01.02.01.03.03.37 |  | 10813 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 38 | [5 empty] | Use Case 4 Mtg #19 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.38 |  | 10814 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 39 | [5 empty] | Use Case 4 Further Definition Meeting Mtg #20 | 1.01.02.01.03.03.39 |  | 10815 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 03 | 40 | [5 empty] | Use Case 4 Mtg #20 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.03.40 |  | 10816 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | [6 empty] | Use Case 6 Meetings spanning 3 months (5.2.3) | 1.01.02.01.03.04 |  | 10819 | S | 65 days |  | 0 | [9 empty] | 0 | [5 empty] | 0
1 | 01 | 02 | 01 | 03 | 04 | 01 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #1 | 1.01.02.01.03.04.01 |  | 10820 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 02 | [5 empty] | Use Case 6 Mtg #6 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.02 |  | 10821 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 03 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #2 | 1.01.02.01.03.04.03 |  | 10822 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 04 | [5 empty] | Use Case 6 Mtg #2 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.04 |  | 10823 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 05 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #3 | 1.01.02.01.03.04.05 |  | 10824 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 06 | [5 empty] | Use Case 6 Mtg #3 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.06 |  | 10825 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 07 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #4 | 1.01.02.01.03.04.07 |  | 10826 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 08 | [5 empty] | Use Case 6 Mtg #4 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.08 |  | 10827 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 09 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #5 | 1.01.02.01.03.04.09 |  | 10828 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 10 | [5 empty] | Use Case 6 Mtg #5 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.10 |  | 10829 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 11 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #6 | 1.01.02.01.03.04.11 |  | 10830 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 12 | [5 empty] | Use Case 6 Mtg #16 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.12 |  | 10831 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 13 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #7 | 1.01.02.01.03.04.13 |  | 10832 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 14 | [5 empty] | Use Case 6 Mtg #7 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.14 |  | 10833 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 15 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #8 | 1.01.02.01.03.04.15 |  | 10834 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 16 | [5 empty] | Use Case .6 Mtg #8 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.16 |  | 10835 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 17 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #9 | 1.01.02.01.03.04.17 |  | 10836 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 18 | [5 empty] | Use Case 6 Mtg #9 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.18 |  | 10837 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 19 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #10 | 1.01.02.01.03.04.19 |  | 10838 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 20 | [5 empty] | Use Case 6 Mtg #10 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.20 |  | 10839 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 21 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #11 | 1.01.02.01.03.04.21 |  | 10840 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 22 | [5 empty] | Use Case 6 Mtg #11 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.22 |  | 10841 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 23 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #12 | 1.01.02.01.03.04.23 |  | 10842 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 24 | [5 empty] | Use Case 6 Mtg #12 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.24 |  | 10843 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 25 | [5 empty] | Use Case 6 Further Definition Meeting Mtg #13 | 1.01.02.01.03.04.25 |  | 10844 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 03 | 04 | 26 | [5 empty] | Use Case 6 Mtg #13 Deliver Use Case Technology Meeting Report | 1.01.02.01.03.04.26 |  | 10845 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 04 | [7 empty] | Develop Draft Use Case Description (5.2.4) | 1.01.02.01.04 | 1.5.2.4 | 3 | S | 163 days |  | 0 | [9 empty] | 0 | [5 empty] | 0
1 | 01 | 02 | 01 | 04 | 01 | [6 empty] | Use Case 1 Develop Use Case Description (5.2.4.1) | 1.01.02.01.04.01 | 1.5.2.4.1 | 6703 | T | 4 wks | 160 | 237.1051 | [9 empty] | 5.5814 |  |  |  | 43.1628 | 41.6744 | 49.1163 |  |  |  | 33.1163 |  |  |  | 4.6958 |  |  |  |  | 40.5581 | [21 empty] | 3.1256 | [16 empty] | 7.814 | [6 empty] | 1.5628 |  |  | 6.6977
1 | 01 | 02 | 01 | 04 | 02 | [6 empty] | Use Case 2 Develop Use Case Description (5.2.4.1) | 1.01.02.01.04.02 | 1.5.2.4.1 | 9823 | T | 4 wks | 160 | 237.1051 | [9 empty] | 5.5814 |  |  |  | 43.1628 | 41.6744 | 49.1163 |  |  |  | 33.1163 |  |  |  | 4.6958 |  |  |  |  | 40.5581 | [21 empty] | 3.1256 | [16 empty] | 7.814 | [6 empty] | 1.5628 |  |  | 6.6977
1 | 01 | 02 | 01 | 04 | 03 | [6 empty] | Use Case 4 Develop Use Case Description (5.2.4.1) | 1.01.02.01.04.03 | 1.5.2.4.1 | 10864 | T | 4 wks | 160 | 237.1051 | [9 empty] | 5.5814 |  |  |  | 43.1628 | 41.6744 | 49.1163 |  |  |  | 33.1163 |  |  |  | 4.6958 |  |  |  |  | 40.5581 | [21 empty] | 3.1256 | [16 empty] | 7.814 | [6 empty] | 1.5628 |  |  | 6.6977
1 | 01 | 02 | 01 | 04 | 04 | [6 empty] | Use Case 6 Develop Use Case Description (5.2.4.1) | 1.01.02.01.04.04 | 1.5.2.4.1 | 10865 | T | 4 wks | 160 | 237.1051 | [9 empty] | 5.5814 |  |  |  | 43.1628 | 41.6744 | 49.1163 |  |  |  | 33.1163 |  |  |  | 4.6958 |  |  |  |  | 40.5581 | [21 empty] | 3.1256 | [16 empty] | 7.814 | [6 empty] | 1.5628 |  |  | 6.6977
1 | 01 | 02 | 01 | 04 | 05 | [6 empty] | Use Case 1 Government Review of Use Case Description (5.2.4.2) | 1.01.02.01.04.05 | 1.5.2.4.2 | 4 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 04 | 06 | [6 empty] | Use Case 2 Government Review of Use Case Description (5.2.4.2) | 1.01.02.01.04.06 | 1.5.2.4.2 | 9825 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 04 | 07 | [6 empty] | Use Case 4 Government Review of Use Case Description (5.2.4.2) | 1.01.02.01.04.07 | 1.5.2.4.2 | 10874 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 04 | 08 | [6 empty] | Use Case 6 Government Review of Use Case Description (5.2.4.2) | 1.01.02.01.04.08 | 1.5.2.4.2 | 10875 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 04 | 09 | [6 empty] | Use Case 1 Submit Response to Government Review Questions of Use Case Description (5.2.4.3) | 1.01.02.01.04.09 |  | 9653 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 04 | 10 | [6 empty] | Use Case 2 Submit Response to Government Review Questions of Use Case Description (5.2.4.3) | 1.01.02.01.04.10 |  | 9827 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 04 | 11 | [6 empty] | Use Case 4 Submit Response to Government Review Questions of Use Case Description (5.2.4.3) | 1.01.02.01.04.11 |  | 10878 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 04 | 12 | [6 empty] | Use Case 6 Submit Response to Government Review Questions of Use Case Description (5.2.4.3) | 1.01.02.01.04.12 |  | 10879 | T | 5 days | 40 | 59.2763 | [9 empty] | 1.3953 |  |  |  | 10.7907 | 10.4186 | 12.2791 |  |  |  | 8.2791 |  |  |  | 1.174 |  |  |  |  | 10.1395 | [21 empty] | 0.7814 | [16 empty] | 1.9535 | [6 empty] | 0.3907 |  |  | 1.6744
1 | 01 | 02 | 01 | 05 | [7 empty] | Publish Draft Use Case Description (5.2.5) | 1.01.02.01.05 | 1.5.2.5 | 6704 | S | 163 days |  | 0 | [9 empty] | 0 | [5 empty] | 0
1 | 01 | 02 | 01 | 05 | 01 | [6 empty] | Use Case 1 Publish Draft Use Case Description Announcement (5.2.5.1) | 1.01.02.01.05.01 | 1.5.2.5.1 | 6705 | T | 30 edays | 240 | 355.6577 | [9 empty] | 8.3721 |  |  |  | 64.7442 | 62.5116 | 73.6744 |  |  |  | 49.6744 |  |  |  | 7.0437 |  |  |  |  | 60.8372 | [21 empty] | 4.6884 | [16 empty] | 11.7209 | [6 empty] | 2.3442 |  |  | 10.0465
1 | 01 | 02 | 01 | 05 | 02 | [6 empty] | Use Case 2 Publish Draft Use Case Description Announcement (5.2.5.1) | 1.01.02.01.05.02 | 1.5.2.5.1 | 9829 | T | 30 edays | 240 | 355.6577 | [9 empty] | 8.3721 |  |  |  | 64.7442 | 62.5116 | 73.6744 |  |  |  | 49.6744 |  |  |  | 7.0437 |  |  |  |  | 60.8372 | [21 empty] | 4.6884 | [16 empty] | 11.7209 | [6 empty] | 2.3442 |  |  | 10.0465
1 | 01 | 02 | 01 | 05 | 03 | [6 empty] | Use Case 4 Publish Draft Use Case Description Announcement (5.2.5.1) | 1.01.02.01.05.03 | 1.5.2.5.1 | 10871 | T | 30 edays | 240 | 355.6577 | [9 empty] | 8.3721 |  |  |  | 64.7442 | 62.5116 | 73.6744 |  |  |  | 49.6744 |  |  |  | 7.0437 |  |  |  |  | 60.8372 | [21 empty] | 4.6884 | [16 empty] | 11.7209 | [6 empty] | 2.3442 |  |  | 10.0465
1 | 01 | 02 | 01 | 05 | 04 | [6 empty] | Use Case 6 Publish Draft Use Case Description Announcement (5.2.5.1) | 1.01.02.01.05.04 | 1.5.2.5.1 | 10880 | T | 30 edays | 240 | 355.6577 | [9 empty] | 8.3721 |  |  |  | 64.7442 | 62.5116 | 73.6744 |  |  |  | 49.6744 |  |  |  | 7.0437 |  |  |  |  | 60.8372 | [21 empty] | 4.6884 | [16 empty] | 11.7209 | [6 empty] | 2.3442 |  |  | 10.0465
1 | 01 | 02 | 01 | 05 | 05 | [6 empty] | Use Case 1 Execute Comment Resolution Conference Agenda (5.2.5.2) | 1.01.02.01.05.05 | 1.5.2.5.2 | 6706 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 05 | 06 | [6 empty] | Use Case 2 Execute Comment Resolution Conference Agenda (5.2.5.2) | 1.01.02.01.05.06 | 1.5.2.5.2 | 9831 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 05 | 07 | [6 empty] | Use Case 4 Execute Comment Resolution Conference Agenda (5.2.5.2) | 1.01.02.01.05.07 | 1.5.2.5.2 | 10883 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 05 | 08 | [6 empty] | Use Case 6 Execute Comment Resolution Conference Agenda (5.2.5.2) | 1.01.02.01.05.08 | 1.5.2.5.2 | 10884 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 05 | 09 | [6 empty] | Use Case 1 Execute Comment Resolution Conference (5.2.5.3) | 1.01.02.01.05.09 | 1.5.2.5.3 | 6708 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 05 | 10 | [6 empty] | Use Case 2 Execute Comment Resolution Conference (5.2.5.3) | 1.01.02.01.05.10 | 1.5.2.5.3 | 9833 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 05 | 11 | [6 empty] | Use Case 4 Execute Comment Resolution Conference (5.2.5.3) | 1.01.02.01.05.11 | 1.5.2.5.3 | 10887 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 05 | 12 | [6 empty] | Use Case 6 Execute Comment Resolution Conference (5.2.5.3) | 1.01.02.01.05.12 | 1.5.2.5.3 | 10888 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 05 | 13 | [6 empty] | Use Case 1 Publish Comment Resolution Conference Minutes (5.2.5.4) | 1.01.02.01.05.13 | 1.5.2.5.4 | 6707 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 05 | 14 | [6 empty] | Use Case 2 Publish Comment Resolution Conference Minutes (5.2.5.4) | 1.01.02.01.05.14 | 1.5.2.5.4 | 9837 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 05 | 15 | [6 empty] | Use Case 4 Publish Comment Resolution Conference Minutes (5.2.5.4) | 1.01.02.01.05.15 | 1.5.2.5.4 | 10891 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 05 | 16 | [6 empty] | Use Case 6 Publish Comment Resolution Conference Minutes (5.2.5.4) | 1.01.02.01.05.16 | 1.5.2.5.4 | 10892 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 06 | [7 empty] | Use Case 1 Publish Final Use Case Description (5.2.6) | 1.01.02.01.06 | 1.5.2.6 | 6709 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 07 | [7 empty] | Use Case 2 Publish Final Use Case Description (5.2.6) | 1.01.02.01.07 | 1.5.2.6 | 9835 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 08 | [7 empty] | Use Case 4 Publish Final Use Case Description (5.2.6) | 1.01.02.01.08 | 1.5.2.6 | 10893 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 09 | [7 empty] | Use Case 6 Publish Final Use Case Description (5.2.6) | 1.01.02.01.09 | 1.5.2.6 | 10894 | T | 1 day | 8 | 11.8553 | [9 empty] | 0.27907 |  |  |  | 2.1581 | 2.0837 | 2.4558 |  |  |  | 1.6558 |  |  |  | 0.23479 |  |  |  |  | 2.0279 | [21 empty] | 0.15628 | [16 empty] | 0.3907 | [6 empty] | 0.07814 |  |  | 0.33488
1 | 01 | 02 | 01 | 10 | [7 empty] | Use Case 1 Receipt of Letters of Intent from Interested Industry Solution Providers | 1.01.02.01.10 |  | 9654 | T | 30 edays | 240 | 355.6577 | [9 empty] | 8.3721 |  |  |  | 64.7442 | 62.5116 | 73.6744 |  |  |  | 49.6744 |  |  |  | 7.0437 |  |  |  |  | 60.8372 | [21 empty] | 4.6884 | [16 empty] | 11.7209 | [6 empty] | 2.3442 |  |  | 10.0465
1 | 01 | 02 | 01 | 11 | [7 empty] | Use Case 2 Receipt of Letters of Intent from Interested Industry Solution Providers | 1.01.02.01.11 |  | 9839 | T | 30 edays | 240 | 355.6577 | [9 empty] | 8.3721 |  |  |  | 64.7442 | 62.5116 | 73.6744 |  |  |  | 49.6744 |  |  |  | 7.0437 |  |  |  |  | 60.8372 | [21 empty] | 4.6884 | [16 empty] | 11.7209 | [6 empty] | 2.3442 |  |  | 10.0465
1 | 01 | 02 | 01 | 12 | [7 empty] | Use Case 4 Receipt of Letters of Intent from Interested Industry Solution Providers | 1.01.02.01.12 |  | 10897 | T | 30 edays | 240 | 355.6577 | [9 empty] | 8.3721 |  |  |  | 64.7442 | 62.5116 | 73.6744 |  |  |  | 49.6744 |  |  |  | 7.0437 |  |  |  |  | 60.8372 | [21 empty] | 4.6884 | [16 empty] | 11.7209 | [6 empty] | 2.3442 |  |  | 10.0465
1 | 01 | 02 | 01 | 13 | [7 empty] | Use Case 6 Receipt of Letters of Intent from Interested Industry Solution Providers | 1.01.02.01.13 |  | 10898 | T | 30 edays | 240 | 355.6577 | [9 empty] | 8.3721 |  |  |  | 64.7442 | 62.5116 | 73.6744 |  |  |  | 49.6744 |  |  |  | 7.0437 |  |  |  |  | 60.8372 | [21 empty] | 4.6884 | [16 empty] | 11.7209 | [6 empty] | 2.3442 |  |  | 10.0465
1 | 01 | 02 | 01 | 14 | [7 empty] | Use Case 1 Deliver Use Case Definition Report (5.2.7) | 1.01.02.01.14 | 1.5.2.7 | 6710 | T | 45 days | 360 | 533.4865 | [9 empty] | 12.5581 |  |  |  | 97.1163 | 93.7674 | 110.5116 |  |  |  | 74.5116 |  |  |  | 10.5656 |  |  |  |  | 91.2558 | [21 empty] | 7.0326 | [16 empty] | 17.5814 | [6 empty] | 3.5163 |  |  | 15.0698
1 | 01 | 02 | 01 | 15 | [7 empty] | Use Case 2 Deliver Use Case Definition Report (5.2.7) | 1.01.02.01.15 | 1.5.2.7 | 9841 | T | 45 days | 360 | 533.4865 | [9 empty] | 12.5581 |  |  |  | 97.1163 | 93.7674 | 110.5116 |  |  |  | 74.5116 |  |  |  | 10.5656 |  |  |  |  | 91.2558 | [21 empty] | 7.0326 | [16 empty] | 17.5814 | [6 empty] | 3.5163 |  |  | 15.0698
1 | 01 | 02 | 01 | 16 | [7 empty] | Use Case 4 Deliver Use Case Definition Report (5.2.7) | 1.01.02.01.16 | 1.5.2.7 | 10901 | T | 45 days | 360 | 533.4865 | [9 empty] | 12.5581 |  |  |  | 97.1163 | 93.7674 | 110.5116 |  |  |  | 74.5116 |  |  |  | 10.5656 |  |  |  |  | 91.2558 | [21 empty] | 7.0326 | [16 empty] | 17.5814 | [6 empty] | 3.5163 |  |  | 15.0698
1 | 01 | 02 | 01 | 17 | [7 empty] | Use Case 6 Deliver Use Case Definition Report (5.2.7) | 1.01.02.01.17 | 1.5.2.7 | 10902 | T | 45 days | 360 | 533.4865 | [9 empty] | 12.5581 |  |  |  | 97.1163 | 93.7674 | 110.5116 |  |  |  | 74.5116 |  |  |  | 10.5656 |  |  |  |  | 91.2558 | [21 empty] | 7.0326 | [16 empty] | 17.5814 | [6 empty] | 3.5163 |  |  | 15.0698
| 01 | 02 | 01 | [8 empty] | Total Phase 2 | 1.01.02.01 |  |  | A |  | 6880 | 10686.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 491 | 0 | 0 | 1856 | 1792 | 2112 | 0 | 0 | 0 | 1424 | 0 | 0 | 0 | 201.92 | 0 | 0 | 0 | 0 | 1744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 67.2 | 0 | 0 | 288 | 0 | 0 | 0
1 | 01 | 03 | [9 empty] | Phase 3 | 1.01.03 |  | 6940 | C | 356 days |  | 23033.22
1 | 01 | 03 | 01 | [8 empty] | Team Development (5.3) | 1.01.03.01 | 1.5.3 | 6711 | W | 252 days |  | 8238.82 |  |  | 1327.33 | [7 empty] | 423 |  |  |  |  | 3496 | [30 empty] | 1327.33 | 1665.16
1 | 01 | 03 | 01 | 01 | [7 empty] | Use Case 1 Develop Use Case Team Development Workplan (5.3.1) | 1.01.03.01.01 | 1.5.3.1 | 6716 | T | 2 days | 16 | 121.1591 |  |  | 19.5196 | [7 empty] | 6.2206 |  |  |  |  | 51.4118 | [30 empty] | 19.5196 | 24.4876
1 | 01 | 03 | 01 | 02 | [7 empty] | Use Case 2 Develop Use Case Team Development Workplan (5.3.1) | 1.01.03.01.02 | 1.5.3.1 | 9843 | T | 2 days | 16 | 121.1591 |  |  | 19.5196 | [7 empty] | 6.2206 |  |  |  |  | 51.4118 | [30 empty] | 19.5196 | 24.4876
1 | 01 | 03 | 01 | 03 | [7 empty] | Use Case 4 Develop Use Case Team Development Workplan (5.3.1) | 1.01.03.01.03 | 1.5.3.1 | 10905 | T | 2 days | 16 | 121.1591 |  |  | 19.5196 | [7 empty] | 6.2206 |  |  |  |  | 51.4118 | [30 empty] | 19.5196 | 24.4876
1 | 01 | 03 | 01 | 04 | [7 empty] | Use Case 6 Develop Use Case Team Development Workplan (5.3.1) | 1.01.03.01.04 | 1.5.3.1 | 10906 | T | 2 days | 16 | 121.1591 |  |  | 19.5196 | [7 empty] | 6.2206 |  |  |  |  | 51.4118 | [30 empty] | 19.5196 | 24.4876
1 | 01 | 03 | 01 | 05 | [7 empty] | Use Case 1 Prepare and execute a Monthly Team Development Conference Agenda (5.3.2) | 1.01.03.01.05 | 1.5.3.2 | 6717 | S | 4 days |  | 0
1 | 01 | 03 | 01 | 05 | 01 | [6 empty] | Use Case 1 Prepare Agenda (5.3.2.1) | 1.01.03.01.05.01 | 1.5.3.2.1 | 6718 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 05 | 02 | [6 empty] | Use Case 1 Conduct Conference (5.3.2.2) | 1.01.03.01.05.02 | 1.5.3.2.2 | 6719 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 05 | 03 | [6 empty] | Use Case 1 Publish Monthly Team Development Conference Minutes (5.3.2.3) | 1.01.03.01.05.03 | 1.5.3.2.3 | 6724 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 06 | [7 empty] | Use Case 2 Prepare and execute a Monthly Team Development Conference Agenda (5.3.2) | 1.01.03.01.06 | 1.5.3.2 | 9845 | S | 9 days |  | 0
1 | 01 | 03 | 01 | 06 | 01 | [6 empty] | Use Case 2 Prepare Agenda (5.3.2.1) | 1.01.03.01.06.01 | 1.5.3.2.1 | 9846 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 06 | 02 | [6 empty] | Use Case 2 Conduct Conference (5.3.2.2) | 1.01.03.01.06.02 | 1.5.3.2.2 | 9847 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 06 | 03 | [6 empty] | Use Case 2 Publish Monthly Team Development Conference Minutes (5.3.2.3) | 1.01.03.01.06.03 | 1.5.3.2.3 | 9848 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 07 | [7 empty] | Use Case 4 Prepare and execute a Monthly Team Development Conference Agenda (5.3.2) | 1.01.03.01.07 | 1.5.3.2 | 10917 | S | 10 days |  | 0
1 | 01 | 03 | 01 | 07 | 01 | [6 empty] | Use Case 4 Prepare Agenda (5.3.2.1) | 1.01.03.01.07.01 | 1.5.3.2.1 | 10918 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 07 | 02 | [6 empty] | Use Case 4 Conduct Conference (5.3.2.2) | 1.01.03.01.07.02 | 1.5.3.2.2 | 10919 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 07 | 03 | [6 empty] | Use Case 4 Publish Monthly Team Development Conference Minutes (5.3.2.3) | 1.01.03.01.07.03 | 1.5.3.2.3 | 10920 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 08 | [7 empty] | Use Case 6 Prepare and execute a Monthly Team Development Conference Agenda (5.3.2) | 1.01.03.01.08 | 1.5.3.2 | 10915 | S | 10 days |  | 0
1 | 01 | 03 | 01 | 08 | 01 | [6 empty] | Use Case 6 Prepare Agenda (5.3.2.1) | 1.01.03.01.08.01 | 1.5.3.2.1 | 10910 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 08 | 02 | [6 empty] | Use Case 6 Conduct Conference (5.3.2.2) | 1.01.03.01.08.02 | 1.5.3.2.2 | 10911 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 08 | 03 | [6 empty] | Use Case 6 Publish Monthly Team Development Conference Minutes (5.3.2.3) | 1.01.03.01.08.03 | 1.5.3.2.3 | 10912 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 09 | [7 empty] | Use Case 1 Conduct one on one Interviews with Cybersecurity Technology Providers (5.3.3) | 1.01.03.01.09 |  | 9689 | S | 4 days |  | 0
1 | 01 | 03 | 01 | 09 | 01 | [6 empty] | Conduct Conference | 1.01.03.01.09.01 |  | 9687 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 09 | 02 | [6 empty] | Use Case 1 Deliver the Team Development Meeting Minutes Report to the COR | 1.01.03.01.09.02 |  | 9686 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 10 | [7 empty] | Use Case 2 Conduct one on one Interviews with Cybersecurity Technology Providers (5.3.3) | 1.01.03.01.10 |  | 9851 | S | 4 days | 0 | 0 | [15 empty] | 0 | [30 empty] | 0 | 0
1 | 01 | 03 | 01 | 10 | 01 | [6 empty] | Conduct Conference | 1.01.03.01.10.01 |  | 9853 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 10 | 02 | [6 empty] | Use Case 2 Deliver the Team Development Meeting Minutes Report to the COR | 1.01.03.01.10.02 |  | 9854 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 11 | [7 empty] | Use Case 4 Conduct one on one Interviews with Cybersecurity Technology Providers (5.3.3) | 1.01.03.01.11 |  | 10947 | S | 4 days | 0 | 0 | [15 empty] | 0 | [30 empty] | 0 | 0
1 | 01 | 03 | 01 | 11 | 01 | [6 empty] | Conduct Conference | 1.01.03.01.11.01 |  | 10949 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 11 | 02 | [6 empty] | Use Case 4 Deliver the Team Development Meeting Minutes Report to the COR | 1.01.03.01.11.02 |  | 10950 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 12 | [7 empty] | Use Case 6 Conduct one on one Interviews with Cybersecurity Technology Providers (5.3.3) | 1.01.03.01.12 |  | 10953 | S | 4 days |  | 0
1 | 01 | 03 | 01 | 12 | 01 | [6 empty] | Conduct Conference | 1.01.03.01.12.01 |  | 10955 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 12 | 02 | [6 empty] | Use Case 6 Deliver the Team Development Meeting Minutes Report to the COR | 1.01.03.01.12.02 |  | 10956 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 13 | [7 empty] | Use Case 1 Conduct one on one Interviews with Cybersecurity Technology Providers that have provided letters of interest (5.3.4) 5 mtgs | 1.01.03.01.13 |  | 9690 | S | 9 days |  | 0
1 | 01 | 03 | 01 | 13 | 01 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.13.01 | 1.5.3.4 | 6726 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 13 | 02 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.13.02 | 1.5.3.4.1 | 6727 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 13 | 03 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.13.03 | 1.5.3.4 | 21896 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 13 | 04 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.13.04 | 1.5.3.4.1 | 21897 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 13 | 05 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.13.05 | 1.5.3.4 | 21898 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 13 | 06 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.13.06 | 1.5.3.4.1 | 21899 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 13 | 07 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.13.07 | 1.5.3.4 | 21900 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 13 | 08 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.13.08 | 1.5.3.4.1 | 21901 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 13 | 09 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.13.09 | 1.5.3.4 | 21902 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 13 | 10 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.13.10 | 1.5.3.4.1 | 21903 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 14 | [7 empty] | Use Case 2 Conduct one on one Interviews with Cybersecurity Technology Providers that have provided letters of interest (5.3.4) 5 mtgs | 1.01.03.01.14 |  | 9857 | S | 9 days | 0 | 0 | [15 empty] | 0 | [30 empty] | 0 | 0
1 | 01 | 03 | 01 | 14 | 01 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.14.01 | 1.5.3.4 | 9858 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 14 | 02 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.14.02 | 1.5.3.4.1 | 9859 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 14 | 03 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.14.03 | 1.5.3.4 | 21912 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 14 | 04 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.14.04 | 1.5.3.4.1 | 21913 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 14 | 05 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.14.05 | 1.5.3.4 | 21914 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 14 | 06 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.14.06 | 1.5.3.4.1 | 21915 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 14 | 07 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.14.07 | 1.5.3.4 | 21916 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 14 | 08 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.14.08 | 1.5.3.4.1 | 21917 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 14 | 09 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.14.09 | 1.5.3.4 | 21918 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 14 | 10 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.14.10 | 1.5.3.4.1 | 21919 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 15 | [7 empty] | Use Case 4 Conduct one on one Interviews with Cybersecurity Technology Providers that have provided letters of interest (5.3.4) | 1.01.03.01.15 |  | 11094 | S | 10 days |  | 0
1 | 01 | 03 | 01 | 15 | 01 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.15.01 | 1.5.3.4 | 11095 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 15 | 02 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.15.02 | 1.5.3.4.1 | 11096 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 15 | 03 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.15.03 | 1.5.3.4 | 21928 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 15 | 04 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.15.04 | 1.5.3.4.1 | 21929 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 15 | 05 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.15.05 | 1.5.3.4 | 21930 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 15 | 06 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.15.06 | 1.5.3.4.1 | 21931 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 15 | 07 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.15.07 | 1.5.3.4 | 21932 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 15 | 08 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.15.08 | 1.5.3.4.1 | 21933 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 15 | 09 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.15.09 | 1.5.3.4 | 21934 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 15 | 10 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.15.10 | 1.5.3.4.1 | 21935 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 16 | [7 empty] | Use Case 6 Conduct one on one Interviews with Cybersecurity Technology Providers that have provided letters of interest (5.3.4) | 1.01.03.01.16 |  | 11098 | S | 10 days | 0 | 0 | [15 empty] | 0 | [30 empty] | 0
1 | 01 | 03 | 01 | 16 | 01 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.16.01 | 1.5.3.4 | 11099 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 16 | 02 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.16.02 | 1.5.3.4.1 | 11100 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 16 | 03 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.16.03 | 1.5.3.4 | 21946 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 16 | 04 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.16.04 | 1.5.3.4.1 | 21947 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 16 | 05 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.16.05 | 1.5.3.4 | 21948 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 16 | 06 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.16.06 | 1.5.3.4.1 | 21949 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 16 | 07 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.16.07 | 1.5.3.4 | 21950 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 16 | 08 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.16.08 | 1.5.3.4.1 | 21951 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 16 | 09 | [6 empty] | Conduct in-person meetings with Interested Parties (5.3.4.1) | 1.01.03.01.16.09 | 1.5.3.4 | 21952 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 16 | 10 | [6 empty] | Produce and Deliver to the COR the Team Development Meeting Minutes Report (5.3.4.2) | 1.01.03.01.16.10 | 1.5.3.4.1 | 21953 | T | 1 day | 8 | 60.5796 |  |  | 9.7598 | [7 empty] | 3.1103 |  |  |  |  | 25.7059 | [30 empty] | 9.7598 | 12.2438
1 | 01 | 03 | 01 | 17 | [7 empty] | Use Case 1 Develop Agreements between NCCoE and Cybersecurity Providers (5.3.5) | 1.01.03.01.17 | 1.5.3.5 | 6728 | T | 10 days | 80 | 605.7956 |  |  | 97.5978 | [7 empty] | 31.1029 |  |  |  |  | 257.0588 | [30 empty] | 97.5978 | 122.4382
1 | 01 | 03 | 01 | 18 | [7 empty] | Use Case 2 Develop Agreements between NCCoE and Cybersecurity Providers (5.3.5) | 1.01.03.01.18 | 1.5.3.5 | 9864 | T | 10 days | 80 | 605.7956 |  |  | 97.5978 | [7 empty] | 31.1029 |  |  |  |  | 257.0588 | [30 empty] | 97.5978 | 122.4382
1 | 01 | 03 | 01 | 19 | [7 empty] | Use Case 4 Develop Agreements between NCCoE and Cybersecurity Providers (5.3.5) | 1.01.03.01.19 | 1.5.3.5 | 10963 | T | 10 days | 80 | 605.7956 |  |  | 97.5978 | [7 empty] | 31.1029 |  |  |  |  | 257.0588 | [30 empty] | 97.5978 | 122.4382
1 | 01 | 03 | 01 | 20 | [7 empty] | Use Case 6 Develop Agreements between NCCoE and Cybersecurity Providers (5.3.5) | 1.01.03.01.20 | 1.5.3.5 | 10964 | T | 10 days | 80 | 605.7956 |  |  | 97.5978 | [7 empty] | 31.1029 |  |  |  |  | 257.0588 | [30 empty] | 97.5978 | 122.4382
1 | 01 | 03 | 01 | 21 | [7 empty] | Use Case 1 Develop and Deliver to the COR the Roster of use Case Development and Demonstration Collaborators (5.3.6) | 1.01.03.01.21 | 1.5.3.6 | 6729 | T | 2 days | 16 | 121.1591 |  |  | 19.5196 | [7 empty] | 6.2206 |  |  |  |  | 51.4118 | [30 empty] | 19.5196 | 24.4876
1 | 01 | 03 | 01 | 22 | [7 empty] | Use Case 2 Develop and Deliver to the COR the Roster of use Case Development and Demonstration Collaborators (5.3.6) | 1.01.03.01.22 | 1.5.3.6 | 9862 | T | 2 days | 16 | 121.1591 |  |  | 19.5196 | [7 empty] | 6.2206 |  |  |  |  | 51.4118 | [30 empty] | 19.5196 | 24.4876
1 | 01 | 03 | 01 | 23 | [7 empty] | Use Case 4 Develop and Deliver to the COR the Roster of use Case Development and Demonstration Collaborators (5.3.6) | 1.01.03.01.23 | 1.5.3.6 | 10967 | T | 2 days | 16 | 121.1591 |  |  | 19.5196 | [7 empty] | 6.2206 |  |  |  |  | 51.4118 | [30 empty] | 19.5196 | 24.4876
1 | 01 | 03 | 01 | 24 | [7 empty] | Use Case 6 Develop and Deliver to the COR the Roster of use Case Development and Demonstration Collaborators (5.3.6) | 1.01.03.01.24 | 1.5.3.6 | 10968 | T | 2 days | 16 | 121.1591 |  |  | 19.5196 | [7 empty] | 6.2206 |  |  |  |  | 51.4118 | [30 empty] | 19.5196 | 24.4876
1 | 01 | 03 | 01 | 25 | [7 empty] | Use Case 1 COR Approves the Roster of Use Case Development and Demonstration Collaborators | 1.01.03.01.25 |  | 21884 | T | 5 days | 40 | 302.8978 |  |  | 48.7989 | [7 empty] | 15.5515 |  |  |  |  | 128.5294 | [30 empty] | 48.7989 | 61.2191
1 | 01 | 03 | 01 | 26 | [7 empty] | Use Case 2 COR Approves the Roster of Use Case Development and Demonstration Collaborators | 1.01.03.01.26 |  | 21885 | T | 5 days | 40 | 302.8978 |  |  | 48.7989 | [7 empty] | 15.5515 |  |  |  |  | 128.5294 | [30 empty] | 48.7989 | 61.2191
1 | 01 | 03 | 01 | 27 | [7 empty] | Use Case 4 COR Approves the Roster of Use Case Development and Demonstration Collaborators | 1.01.03.01.27 |  | 21886 | T | 5 days | 40 | 302.8978 |  |  | 48.7989 | [7 empty] | 15.5515 |  |  |  |  | 128.5294 | [30 empty] | 48.7989 | 61.2191
1 | 01 | 03 | 01 | 28 | [7 empty] | Use Case 6 COR Approves the Roster of Use Case Development and Demonstration Collaborators | 1.01.03.01.28 |  | 21887 | T | 5 days | 40 | 302.8978 |  |  | 48.7989 | [7 empty] | 15.5515 |  |  |  |  | 128.5294 | [30 empty] | 48.7989 | 61.2191
| 01 | 03 | 01 | [8 empty] | Total Hours | 1.01.03.01 |  |  | A |  | 1088 | 8238.82 | 0 | 0 | 1327.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423 | 0 | 0 | 0 | 0 | 3496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1327.33 | 1665.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 01 | 03 | 02 | [8 empty] | Use Case Builds (5.4) | 1.01.03.02 |  | 22211 | W | 252 days |  | 14751.4 | [9 empty] | 1146 | 1720 |  | 2285 | 0 | [6 empty] | 2864 | 0 |  | 4310.4 | [22 empty] | 583 | 0 | [19 empty] | 1843
1 | 01 | 03 | 02 | 01 | [7 empty] | Use Case Build (5.4) Use Case 1 | 1.01.03.02.01 | 1.5.4 | 6730 | S | 108 days |  | 0 | [23 empty] | 0 | [22 empty] | 0
1 | 01 | 03 | 02 | 01 | 01 | [6 empty] | Use Case 1 Execute a Monthly Use Case Build Conference Agenda (5.4.1) 30 meetings per | 1.01.03.02.01.01 | 1.5.4.1 | 6731 | S | 7 days |  | 0 | [23 empty] | 0 | [22 empty] | 0
1 | 01 | 03 | 02 | 01 | 01 | 01 | [5 empty] | Create Agenda (5.4.1.1) | 1.01.03.02.01.01.01 | 1.5.4.1.1 | 6732 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 01 | 02 | [5 empty] | Conduct Conference (5.4.1.2) | 1.01.03.02.01.01.02 | 1.5.4.1.2 | 6733 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 01 | 03 | [5 empty] | Use Case 1 Develop and Deliver the Monthly Use Case Build Conference Minutes Report (5.4.1.3) | 1.01.03.02.01.01.03 | 1.5.4.1.3 | 6734 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | [6 empty] | Use Case 1 Conduct in-person meetings on Use Case Build issues (5.4.2) 10 instead of 30 | 1.01.03.02.01.02 | 1.5.4.2 | 6735 | S | 31 days |  | 0 | [23 empty] | 0 | [22 empty] | 0
1 | 01 | 03 | 02 | 01 | 02 | 01 | [5 empty] | Mtg 1 | 1.01.03.02.01.02.01 |  | 9691 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 02 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.01.02.02 |  | 9692 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 03 | [5 empty] | Mtg 2 | 1.01.03.02.01.02.03 |  | 9711 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 04 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.01.02.04 |  | 9712 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 05 | [5 empty] | Mtg 3 | 1.01.03.02.01.02.05 |  | 9713 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 06 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.01.02.06 |  | 9714 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 07 | [5 empty] | Mtg 4 | 1.01.03.02.01.02.07 |  | 9715 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 08 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.01.02.08 |  | 9716 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 09 | [5 empty] | Mtg 5 | 1.01.03.02.01.02.09 |  | 9717 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 10 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.01.02.10 |  | 9718 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 11 | [5 empty] | Mtg 6 | 1.01.03.02.01.02.11 |  | 9719 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 12 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.01.02.12 |  | 9720 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 13 | [5 empty] | Mtg 7 | 1.01.03.02.01.02.13 |  | 9721 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 14 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.01.02.14 |  | 9722 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 15 | [5 empty] | Mtg 8 | 1.01.03.02.01.02.15 |  | 9723 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 16 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.01.02.16 |  | 9724 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 17 | [5 empty] | Mtg 9 | 1.01.03.02.01.02.17 |  | 9725 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 18 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.01.02.18 |  | 9726 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 19 | [5 empty] | Mtg 10 | 1.01.03.02.01.02.19 |  | 9727 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 02 | 20 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.01.02.20 |  | 9728 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 03 | [6 empty] | Use Case 1 Develop and Deliver Draft Use Case Build Plan (5.4.3) | 1.01.03.02.01.03 | 1.5.4.3 | 6736 | T | 2 wks | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 01 | 04 | [6 empty] | Use Case 1 Government Acceptance of Use Case Build Plan (IMP) | 1.01.03.02.01.04 |  | 9731 | T | 10 days | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 01 | 05 | [6 empty] | Use Case 1 Develop and Deliver Final Use Case Build Plan (5.4.3) | 1.01.03.02.01.05 |  | 9734 | T | 1 wk | 5 | 20.9062 | [9 empty] | 1.6241 | 2.4376 |  | 3.2384 | 0 | [6 empty] | 4.059 | 0 |  | 6.1088 | [22 empty] | 0.82625 | 0 | [19 empty] | 2.612
1 | 01 | 03 | 02 | 01 | 06 | [6 empty] | Use Case 1 Use Case Build (5.4.4) | 1.01.03.02.01.06 |  | 9738 | T | 3 wks | 120 | 501.7483 | [9 empty] | 38.9796 | 58.5034 |  | 77.7211 | 0 | [6 empty] | 97.415 | 0 |  | 146.6122 | [22 empty] | 19.8299 | 0 | [19 empty] | 62.6871
1 | 01 | 03 | 02 | 01 | 07 | [6 empty] | Use Case 1 Deliver a draft Use Case Development Report and Demonstration Script (5.4.4) | 1.01.03.02.01.07 | 1.5.4.4 | 6737 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 08 | [6 empty] | Use Case 1 Government Approval of the Draft Use Case Development Report and Demonstration Script | 1.01.03.02.01.08 |  | 9732 | T | 5 days | 40 | 167.2494 | [9 empty] | 12.9932 | 19.5011 |  | 25.907 | 0 | [6 empty] | 32.4717 | 0 |  | 48.8707 | [22 empty] | 6.61 | 0 | [19 empty] | 20.8957
1 | 01 | 03 | 02 | 01 | 09 | [6 empty] | Use Case 1 Develop and Deliver a Final Use Case Development Report and Demonstration Script (5.4.4) | 1.01.03.02.01.09 |  | 9736 | T | 10 days | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 01 | 10 | [6 empty] | Government Approval of Final Use Case Development Report and Demonstration Script | 1.01.03.02.01.10 |  | 9735 | T | 5 days | 40 | 167.2494 | [9 empty] | 12.9932 | 19.5011 |  | 25.907 | 0 | [6 empty] | 32.4717 | 0 |  | 48.8707 | [22 empty] | 6.61 | 0 | [19 empty] | 20.8957
1 | 01 | 03 | 02 | 01 | 11 | [6 empty] | Use Case 1 Deliver a Use Case Demonstration Schedule (5.4.5) | 1.01.03.02.01.11 | 1.5.4.5 | 6738 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 12 | [6 empty] | Use Case 1 Conduct Use Case Demonstration (5.4.5.2) | 1.01.03.02.01.12 | 1.5.4.5.2 | 6740 | T | 1 wk | 5 | 20.9062 | [9 empty] | 1.6241 | 2.4376 |  | 3.2384 | 0 | [6 empty] | 4.059 | 0 |  | 6.1088 | [22 empty] | 0.82625 | 0 | [19 empty] | 2.612
1 | 01 | 03 | 02 | 01 | 13 | [6 empty] | Use Case 1 Develop and Deliver Security Platform Demonstration Report (5.4.5.3) | 1.01.03.02.01.13 | 1.5.4.5.3 | 6741 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 01 | 14 | [6 empty] | Use Case 1 Develop and Deliver the Draft Usecase Documentation Report (5.4.6) | 1.01.03.02.01.14 | 1.5.4.6 | 6742 | T | 15 days | 120 | 501.7483 | [9 empty] | 38.9796 | 58.5034 |  | 77.7211 | 0 | [6 empty] | 97.415 | 0 |  | 146.6122 | [22 empty] | 19.8299 | 0 | [19 empty] | 62.6871
1 | 01 | 03 | 02 | 01 | 15 | [6 empty] | Use Case 1 Government Approval of the Draft Use Case Documentation Report | 1.01.03.02.01.15 |  | 9739 | T | 15 days | 120 | 501.7483 | [9 empty] | 38.9796 | 58.5034 |  | 77.7211 | 0 | [6 empty] | 97.415 | 0 |  | 146.6122 | [22 empty] | 19.8299 | 0 | [19 empty] | 62.6871
1 | 01 | 03 | 02 | 01 | 16 | [6 empty] | Use Case 1 Develop and Deliver Final Use Case Documentation Report (IMP) | 1.01.03.02.01.16 |  | 9740 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | [7 empty] | Use Case Build (5.4) Use Case 2 | 1.01.03.02.02 | 1.5.4 | 9866 | S | 104 days |  | 0 | [23 empty] | 0 | [22 empty] | 0
1 | 01 | 03 | 02 | 02 | 01 | [6 empty] | Use Case 2 Execute a Monthly Use Case Build Conference Agenda (5.4.1) 30 meetings per | 1.01.03.02.02.01 | 1.5.4.1 | 9867 | S | 7 days |  | 0 | [23 empty] | 0 | [22 empty] | 0
1 | 01 | 03 | 02 | 02 | 01 | 01 | [5 empty] | Create Agenda (5.4.1.1) | 1.01.03.02.02.01.01 | 1.5.4.1.1 | 9868 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 01 | 02 | [5 empty] | Conduct Conference (5.4.1.2) | 1.01.03.02.02.01.02 | 1.5.4.1.2 | 9869 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 01 | 03 | [5 empty] | Use Case 2 Develop and Deliver the Monthly Use Case Build Conference Minutes Report (5.4.1.3) | 1.01.03.02.02.01.03 | 1.5.4.1.3 | 9870 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | [6 empty] | Use Case 2 Conduct in-person meetings on Use Case Build issues (5.4.2) 10 instead of 30 | 1.01.03.02.02.02 | 1.5.4.2 | 9871 | S | 31 days |  | 0 | [23 empty] | 0 | [22 empty] | 0
1 | 01 | 03 | 02 | 02 | 02 | 01 | [5 empty] | Mtg 1 | 1.01.03.02.02.02.01 |  | 9872 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 02 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.02.02.02 |  | 9873 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 03 | [5 empty] | Mtg 2 | 1.01.03.02.02.02.03 |  | 9874 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 04 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.02.02.04 |  | 9875 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 05 | [5 empty] | Mtg 3 | 1.01.03.02.02.02.05 |  | 9876 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 06 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.02.02.06 |  | 9877 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 07 | [5 empty] | Mtg 4 | 1.01.03.02.02.02.07 |  | 9878 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 08 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.02.02.08 |  | 9879 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 09 | [5 empty] | Mtg 5 | 1.01.03.02.02.02.09 |  | 9880 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 10 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.02.02.10 |  | 9881 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 11 | [5 empty] | Mtg 6 | 1.01.03.02.02.02.11 |  | 9882 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 12 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.02.02.12 |  | 9883 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 13 | [5 empty] | Mtg 7 | 1.01.03.02.02.02.13 |  | 9884 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 14 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.02.02.14 |  | 9885 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 15 | [5 empty] | Mtg 8 | 1.01.03.02.02.02.15 |  | 9886 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 16 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.02.02.16 |  | 9887 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 17 | [5 empty] | Mtg 9 | 1.01.03.02.02.02.17 |  | 9888 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 18 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.02.02.18 |  | 9889 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 19 | [5 empty] | Mtg 10 | 1.01.03.02.02.02.19 |  | 9890 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 02 | 20 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.02.02.20 |  | 9891 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 03 | [6 empty] | Use Case 2 Develop and Deliver Draft Use Case Build Plan (5.4.3) | 1.01.03.02.02.03 | 1.5.4.3 | 9892 | T | 2 wks | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 02 | 04 | [6 empty] | Government Acceptance of Use Case Build Plan | 1.01.03.02.02.04 |  | 9893 | T | 10 days | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 02 | 05 | [6 empty] | Develop and Deliver Final Use Case Build Plan (5.4.3) | 1.01.03.02.02.05 |  | 9894 | T | 1 wk | 5 | 20.9062 | [9 empty] | 1.6241 | 2.4376 |  | 3.2384 | 0 | [6 empty] | 4.059 | 0 |  | 6.1088 | [22 empty] | 0.82625 | 0 | [19 empty] | 2.612
1 | 01 | 03 | 02 | 02 | 06 | [6 empty] | Use Case Build (5.4.4) | 1.01.03.02.02.06 |  | 9895 | T | 3 wks | 120 | 501.7483 | [9 empty] | 38.9796 | 58.5034 |  | 77.7211 | 0 | [6 empty] | 97.415 | 0 |  | 146.6122 | [22 empty] | 19.8299 | 0 | [19 empty] | 62.6871
1 | 01 | 03 | 02 | 02 | 07 | [6 empty] | Use Case 2 Deliver a draft Use Case Development Report and Demonstration Script (5.4.4) | 1.01.03.02.02.07 | 1.5.4.4 | 9896 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 08 | [6 empty] | Use Case 2 Government Approval of the Draft Use Case Development Report and Demonstration Script | 1.01.03.02.02.08 |  | 9897 | T | 5 days | 40 | 167.2494 | [9 empty] | 12.9932 | 19.5011 |  | 25.907 | 0 | [6 empty] | 32.4717 | 0 |  | 48.8707 | [22 empty] | 6.61 | 0 | [19 empty] | 20.8957
1 | 01 | 03 | 02 | 02 | 09 | [6 empty] | Use Case 2 Develop and Deliver a Final Use Case Development Report and Demonstration Script (5.4.4) | 1.01.03.02.02.09 |  | 9898 | T | 10 days | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 02 | 10 | [6 empty] | Government Approval of Final Use Case Development Report and Demonstration Script | 1.01.03.02.02.10 |  | 9899 | T | 5 days | 40 | 167.2494 | [9 empty] | 12.9932 | 19.5011 |  | 25.907 | 0 | [6 empty] | 32.4717 | 0 |  | 48.8707 | [22 empty] | 6.61 | 0 | [19 empty] | 20.8957
1 | 01 | 03 | 02 | 02 | 11 | [6 empty] | Use Case 2 Deliver a Use Case Demonstration Schedule (5.4.5) | 1.01.03.02.02.11 | 1.5.4.5 | 9900 | T | 2 days | 16 | 66.8998 | [9 empty] | 5.1973 | 7.8005 |  | 10.3628 | 0 | [6 empty] | 12.9887 | 0 |  | 19.5483 | [22 empty] | 2.644 | 0 | [19 empty] | 8.3583
1 | 01 | 03 | 02 | 02 | 12 | [6 empty] | Use Case 2 Conduct Use Case Demonstration (5.4.5.2) | 1.01.03.02.02.12 | 1.5.4.5.2 | 9901 | T | 1 wk | 5 | 20.9062 | [9 empty] | 1.6241 | 2.4376 |  | 3.2384 | 0 | [6 empty] | 4.059 | 0 |  | 6.1088 | [22 empty] | 0.82625 | 0 | [19 empty] | 2.612
1 | 01 | 03 | 02 | 02 | 13 | [6 empty] | Use Case 2 Develop and Deliver Security Platform Demonstration Report (5.4.5.3) | 1.01.03.02.02.13 | 1.5.4.5.3 | 9902 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 02 | 14 | [6 empty] | Use Case 2 Develop and Deliver the Draft Usecase Documentation Report (5.4.6) | 1.01.03.02.02.14 | 1.5.4.6 | 9903 | T | 2 wks | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 02 | 15 | [6 empty] | Use Case 2 Government Approval of the Draft Use Case Documentation Report | 1.01.03.02.02.15 |  | 9904 | T | 15 days | 120 | 501.7483 | [9 empty] | 38.9796 | 58.5034 |  | 77.7211 | 0 | [6 empty] | 97.415 | 0 |  | 146.6122 | [22 empty] | 19.8299 | 0 | [19 empty] | 62.6871
1 | 01 | 03 | 02 | 02 | 16 | [6 empty] | Use Case 2 Develop and Deliver Final Use Case Documentation Report (IMP) | 1.01.03.02.02.16 |  | 9905 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | [7 empty] | Use Case Build (5.4) Use Case 4 | 1.01.03.02.03 | 1.5.4 | 10971 | S | 104 days |  | 0 | [23 empty] | 0 | [22 empty] | 0
1 | 01 | 03 | 02 | 03 | 01 | [6 empty] | Use Case 4 Execute a Monthly Use Case Build Conference Agenda (5.4.1) 30 meetings per | 1.01.03.02.03.01 | 1.5.4.1 | 10972 | S | 7 days |  | 0 | [23 empty] | 0 | [22 empty] | 0
1 | 01 | 03 | 02 | 03 | 01 | 01 | [5 empty] | Create Agenda (5.4.1.1) | 1.01.03.02.03.01.01 | 1.5.4.1.1 | 10973 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 01 | 02 | [5 empty] | Conduct Conference (5.4.1.2) | 1.01.03.02.03.01.02 | 1.5.4.1.2 | 10974 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 01 | 03 | [5 empty] | Use Case 4 Develop and Deliver the Monthly Use Case Build Conference Minutes Report (5.4.1.3) | 1.01.03.02.03.01.03 | 1.5.4.1.3 | 10975 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | [6 empty] | Use Case 4 Conduct in-person meetings on Use Case Build issues (5.4.2) 10 instead of 30 | 1.01.03.02.03.02 | 1.5.4.2 | 10976 | S | 31 days |  | 0 | [23 empty] | 0 | [22 empty] | 0
1 | 01 | 03 | 02 | 03 | 02 | 01 | [5 empty] | Mtg 1 | 1.01.03.02.03.02.01 |  | 10977 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 02 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.03.02.02 |  | 10978 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 03 | [5 empty] | Mtg 2 | 1.01.03.02.03.02.03 |  | 10979 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 04 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.03.02.04 |  | 10980 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 05 | [5 empty] | Mtg 3 | 1.01.03.02.03.02.05 |  | 10981 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 06 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.03.02.06 |  | 10982 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 07 | [5 empty] | Mtg 4 | 1.01.03.02.03.02.07 |  | 10983 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 08 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.03.02.08 |  | 10984 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 09 | [5 empty] | Mtg 5 | 1.01.03.02.03.02.09 |  | 10985 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 10 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.03.02.10 |  | 10986 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 11 | [5 empty] | Mtg 6 | 1.01.03.02.03.02.11 |  | 10987 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 12 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.03.02.12 |  | 10988 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 13 | [5 empty] | Mtg 7 | 1.01.03.02.03.02.13 |  | 10989 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 14 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.03.02.14 |  | 10990 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 15 | [5 empty] | Mtg 8 | 1.01.03.02.03.02.15 |  | 10991 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 16 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.03.02.16 |  | 10992 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 17 | [5 empty] | Mtg 9 | 1.01.03.02.03.02.17 |  | 10993 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 18 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.03.02.18 |  | 10994 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 19 | [5 empty] | Mtg 10 | 1.01.03.02.03.02.19 |  | 10995 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 02 | 20 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.03.02.20 |  | 10996 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 03 | [6 empty] | Use Case 4 Develop and Deliver Draft Use Case Build Plan (5.4.3) | 1.01.03.02.03.03 | 1.5.4.3 | 10997 | T | 2 wks | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 03 | 04 | [6 empty] | Use Case 4 Government Acceptance of Use Case Build Plan | 1.01.03.02.03.04 |  | 10998 | T | 10 days | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 03 | 05 | [6 empty] | Use Case 4 Develop and Deliver Final Use Case Build Plan (5.4.3) | 1.01.03.02.03.05 |  | 10999 | T | 1 wk | 5 | 20.9062 | [9 empty] | 1.6241 | 2.4376 |  | 3.2384 | 0 | [6 empty] | 4.059 | 0 |  | 6.1088 | [22 empty] | 0.82625 | 0 | [19 empty] | 2.612
1 | 01 | 03 | 02 | 03 | 06 | [6 empty] | Use Case 4 Use Case Build (5.4.4) | 1.01.03.02.03.06 |  | 11000 | T | 3 wks | 120 | 501.7483 | [9 empty] | 38.9796 | 58.5034 |  | 77.7211 | 0 | [6 empty] | 97.415 | 0 |  | 146.6122 | [22 empty] | 19.8299 | 0 | [19 empty] | 62.6871
1 | 01 | 03 | 02 | 03 | 07 | [6 empty] | Use Case 4 Deliver a draft Use Case Development Report and Demonstration Script (5.4.4) | 1.01.03.02.03.07 | 1.5.4.4 | 11001 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 08 | [6 empty] | Use Case 4 Government Approval of the Draft Use Case Development Report and Demonstration Script | 1.01.03.02.03.08 |  | 11002 | T | 5 days | 40 | 167.2494 | [9 empty] | 12.9932 | 19.5011 |  | 25.907 | 0 | [6 empty] | 32.4717 | 0 |  | 48.8707 | [22 empty] | 6.61 | 0 | [19 empty] | 20.8957
1 | 01 | 03 | 02 | 03 | 09 | [6 empty] | Use Case 4 Develop and Deliver a Final Use Case Development Report and Demonstration Script (5.4.4) | 1.01.03.02.03.09 |  | 11003 | T | 10 days | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 03 | 10 | [6 empty] | Use Case 4 Government Approval of Final Use Case Development Report and Demonstration Script | 1.01.03.02.03.10 |  | 11004 | T | 5 days | 40 | 167.2494 | [9 empty] | 12.9932 | 19.5011 |  | 25.907 | 0 | [6 empty] | 32.4717 | 0 |  | 48.8707 | [22 empty] | 6.61 | 0 | [19 empty] | 20.8957
1 | 01 | 03 | 02 | 03 | 11 | [6 empty] | Use Case 4 Deliver a Use Case Demonstration Schedule (5.4.5) | 1.01.03.02.03.11 | 1.5.4.5 | 11005 | T | 2 days | 16 | 66.8998 | [9 empty] | 5.1973 | 7.8005 |  | 10.3628 | 0 | [6 empty] | 12.9887 | 0 |  | 19.5483 | [22 empty] | 2.644 | 0 | [19 empty] | 8.3583
1 | 01 | 03 | 02 | 03 | 12 | [6 empty] | Use Case 4 Conduct Use Case Demonstration (5.4.5.2) | 1.01.03.02.03.12 | 1.5.4.5.2 | 11006 | T | 1 wk | 5 | 20.9062 | [9 empty] | 1.6241 | 2.4376 |  | 3.2384 | 0 | [6 empty] | 4.059 | 0 |  | 6.1088 | [22 empty] | 0.82625 | 0 | [19 empty] | 2.612
1 | 01 | 03 | 02 | 03 | 13 | [6 empty] | Use Case 4 Develop and Deliver Security Platform Demonstration Report (5.4.5.3) | 1.01.03.02.03.13 | 1.5.4.5.3 | 11007 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 03 | 14 | [6 empty] | Use Case 4 Develop and Deliver the Draft Usecase Documentation Report (5.4.6) | 1.01.03.02.03.14 | 1.5.4.6 | 11008 | T | 2 wks | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 03 | 15 | [6 empty] | Use Case 4 Government Approval of the Draft Use Case Documentation Report | 1.01.03.02.03.15 |  | 11009 | T | 15 days | 120 | 501.7483 | [9 empty] | 38.9796 | 58.5034 |  | 77.7211 | 0 | [6 empty] | 97.415 | 0 |  | 146.6122 | [22 empty] | 19.8299 | 0 | [19 empty] | 62.6871
1 | 01 | 03 | 02 | 03 | 16 | [6 empty] | Use Case 4 Develop and Deliver Final Use Case Documentation Report (IMP) | 1.01.03.02.03.16 |  | 11010 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | [7 empty] | Use Case Build (5.4) Use Case 6 | 1.01.03.02.04 | 1.5.4 | 11053 | S | 104 days |  | 0 | [23 empty] | 0 | [22 empty] | 0
1 | 01 | 03 | 02 | 04 | 01 | [6 empty] | Use Case 6 Execute a Monthly Use Case Build Conference Agenda (5.4.1) 30 meetings per | 1.01.03.02.04.01 | 1.5.4.1 | 11054 | S | 7 days |  | 0 | [23 empty] | 0 | [22 empty] | 0
1 | 01 | 03 | 02 | 04 | 01 | 01 | [5 empty] | Create Agenda (5.4.1.1) | 1.01.03.02.04.01.01 | 1.5.4.1.1 | 11055 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 01 | 02 | [5 empty] | Conduct Conference (5.4.1.2) | 1.01.03.02.04.01.02 | 1.5.4.1.2 | 11056 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 01 | 03 | [5 empty] | Use Case 6 Develop and Deliver the Monthly Use Case Build Conference Minutes Report (5.4.1.3) | 1.01.03.02.04.01.03 | 1.5.4.1.3 | 11057 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | [6 empty] | Use Case 6 Conduct in-person meetings on Use Case Build issues (5.4.2) 10 instead of 30 | 1.01.03.02.04.02 | 1.5.4.2 | 11058 | S | 31 days |  | 0 | [46 empty] | 0
1 | 01 | 03 | 02 | 04 | 02 | 01 | [5 empty] | Mtg 1 | 1.01.03.02.04.02.01 |  | 11059 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 02 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.04.02.02 |  | 11060 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 03 | [5 empty] | Mtg 2 | 1.01.03.02.04.02.03 |  | 11061 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 04 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.04.02.04 |  | 11062 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 05 | [5 empty] | Mtg 3 | 1.01.03.02.04.02.05 |  | 11063 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 06 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.04.02.06 |  | 11064 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 07 | [5 empty] | Mtg 4 | 1.01.03.02.04.02.07 |  | 11065 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 08 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.04.02.08 |  | 11066 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 09 | [5 empty] | Mtg 5 | 1.01.03.02.04.02.09 |  | 11067 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 10 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.04.02.10 |  | 11068 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 11 | [5 empty] | Mtg 6 | 1.01.03.02.04.02.11 |  | 11069 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 12 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.04.02.12 |  | 11070 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 13 | [5 empty] | Mtg 7 | 1.01.03.02.04.02.13 |  | 11071 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 14 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.04.02.14 |  | 11072 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 15 | [5 empty] | Mtg 8 | 1.01.03.02.04.02.15 |  | 11073 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 16 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.04.02.16 |  | 11074 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 17 | [5 empty] | Mtg 9 | 1.01.03.02.04.02.17 |  | 11075 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 18 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.04.02.18 |  | 11076 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 19 | [5 empty] | Mtg 10 | 1.01.03.02.04.02.19 |  | 11077 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 02 | 20 | [5 empty] | Use Case Build Meeting Minutes | 1.01.03.02.04.02.20 |  | 11078 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 03 | [6 empty] | Use Case 6 Develop and Deliver Draft Use Case Build Plan (5.4.3) | 1.01.03.02.04.03 | 1.5.4.3 | 11079 | T | 2 wks | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 04 | 04 | [6 empty] | Government Acceptance of Use Case Build Plan | 1.01.03.02.04.04 |  | 11080 | T | 10 days | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 04 | 05 | [6 empty] | Develop and Deliver Final Use Case Build Plan (5.4.3) | 1.01.03.02.04.05 |  | 11081 | T | 1 wk | 5 | 20.9062 | [9 empty] | 1.6241 | 2.4376 |  | 3.2384 | 0 | [6 empty] | 4.059 | 0 |  | 6.1088 | [22 empty] | 0.82625 | 0 | [19 empty] | 2.612
1 | 01 | 03 | 02 | 04 | 06 | [6 empty] | Use Case Build (5.4.4) | 1.01.03.02.04.06 |  | 11082 | T | 3 wks | 120 | 501.7483 | [9 empty] | 38.9796 | 58.5034 |  | 77.7211 | 0 | [6 empty] | 97.415 | 0 |  | 146.6122 | [22 empty] | 19.8299 | 0 | [19 empty] | 62.6871
1 | 01 | 03 | 02 | 04 | 07 | [6 empty] | Use Case 6 Deliver a draft Use Case Development Report and Demonstration Script (5.4.4) | 1.01.03.02.04.07 | 1.5.4.4 | 11083 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 08 | [6 empty] | Use Case 6 Government Approval of the Draft Use Case Development Report and Demonstration Script | 1.01.03.02.04.08 |  | 11084 | T | 5 days | 40 | 167.2494 | [9 empty] | 12.9932 | 19.5011 |  | 25.907 | 0 | [6 empty] | 32.4717 | 0 |  | 48.8707 | [22 empty] | 6.61 | 0 | [19 empty] | 20.8957
1 | 01 | 03 | 02 | 04 | 09 | [6 empty] | Use Case 6 Develop and Deliver a Final Use Case Development Report and Demonstration Script (5.4.4) | 1.01.03.02.04.09 |  | 11085 | T | 10 days | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 04 | 10 | [6 empty] | Government Approval of Final Use Case Development Report and Demonstration Script | 1.01.03.02.04.10 |  | 11086 | T | 5 days | 40 | 167.2494 | [9 empty] | 12.9932 | 19.5011 |  | 25.907 | 0 | [6 empty] | 32.4717 | 0 |  | 48.8707 | [22 empty] | 6.61 | 0 | [19 empty] | 20.8957
1 | 01 | 03 | 02 | 04 | 11 | [6 empty] | Use Case 6 Deliver a Use Case Demonstration Schedule (5.4.5) | 1.01.03.02.04.11 | 1.5.4.5 | 11087 | T | 2 days | 16 | 66.8998 | [9 empty] | 5.1973 | 7.8005 |  | 10.3628 | 0 | [6 empty] | 12.9887 | 0 |  | 19.5483 | [22 empty] | 2.644 | 0 | [19 empty] | 8.3583
1 | 01 | 03 | 02 | 04 | 12 | [6 empty] | Conduct Use Case Demonstration (5.4.5.2) | 1.01.03.02.04.12 | 1.5.4.5.2 | 11088 | T | 1 wk | 5 | 20.9062 | [9 empty] | 1.6241 | 2.4376 |  | 3.2384 | 0 | [6 empty] | 4.059 | 0 |  | 6.1088 | [22 empty] | 0.82625 | 0 | [19 empty] | 2.612
1 | 01 | 03 | 02 | 04 | 13 | [6 empty] | Use Case 6 Develop and Deliver Security Platform Demonstration Report (5.4.5.3) | 1.01.03.02.04.13 | 1.5.4.5.3 | 11089 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
1 | 01 | 03 | 02 | 04 | 14 | [6 empty] | Develop and Deliver the Draft Usecase Documentation Report (5.4.6) | 1.01.03.02.04.14 | 1.5.4.6 | 11090 | T | 2 wks | 80 | 334.4989 | [9 empty] | 25.9864 | 39.0023 |  | 51.8141 | 0 | [6 empty] | 64.9433 | 0 |  | 97.7415 | [22 empty] | 13.22 | 0 | [19 empty] | 41.7914
1 | 01 | 03 | 02 | 04 | 15 | [6 empty] | Government Approval of the Draft Use Case Documentation Report | 1.01.03.02.04.15 |  | 11091 | T | 15 days | 120 | 501.7483 | [9 empty] | 38.9796 | 58.5034 |  | 77.7211 | 0 | [6 empty] | 97.415 | 0 |  | 146.6122 | [22 empty] | 19.8299 | 0 | [19 empty] | 62.6871
1 | 01 | 03 | 02 | 04 | 16 | [6 empty] | Use Case 6 Develop and Deliver Final Use Case Documentation Report (IMP) | 1.01.03.02.04.16 |  | 11092 | T | 1 day | 8 | 33.4499 | [9 empty] | 2.5986 | 3.9002 |  | 5.1814 | 0 | [6 empty] | 6.4943 | 0 |  | 9.7741 | [22 empty] | 1.322 | 0 | [19 empty] | 4.1791
| 01 | 03 | 02 | [8 empty] | Total Hours | 1.01.03.02 |  |  | A |  | 3528 | 14751.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1146 | 1720 | 0 | 2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2864 | 0 | 0 | 4310.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 01 | 04 | [9 empty] | Project Management and Status Reporting (6.0) | 1.01.04 | 1.6. | 6743 | W | 15 days |  | 43 | [10 empty] | 14 |  |  | 8 | [6 empty] | 8 | [26 empty] | 8 | [19 empty] | 5
1 | 01 | 04 | 01 | [8 empty] | Attend Kickoff Meeting (6.1) | 1.01.04.01 | 1.6.1 | 6746 | T | 1 day | 8 | 32 | [10 empty] | 8 |  |  | 8 | [6 empty] | 8 | [26 empty] | 8
1 | 01 | 04 | 02 | [8 empty] | Complete Project Workplan (6.2) | 1.01.04.02 | 1.6.2 | 6745 | T | 15 days | 120 | 10.25 | 0.25 | [9 empty] | 5.5 | [56 empty] | 4.5
| 01 | 04 | [9 empty] | Total Hours | 1.01.04 |  |  | A |  |  | 42.25 | 0.25 | 0 | 0 | [5 empty] | 0 |  | 13.5 |  |  | 8 | 0 | 0 |  |  |  |  | 8 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 8 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 4.5 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 01 | 05 | [9 empty] | Deliverables (7.0) | 1.01.05 | 1.07 | 6744 | S | 529 days |  | 0
1 | 01 | 05 | 01 | [8 empty] | Attend Kickoff Meeting at NIST (7.1) | 1.01.05.01 | 1.7.1 | 6747 | M | 0 days |  | 0
1 | 01 | 05 | 02 | [8 empty] | Project Work Plan (7.2) | 1.01.05.02 | 1.7.2 | 6748 | M | 0 days |  | 0
1 | 01 | 05 | 03 | [8 empty] | Monthly Planning Conference Agenda (7.3) | 1.01.05.03 | 1.7.3 | 6749 | S | 500 days |  | 0
1 | 01 | 05 | 03 | 01 | [7 empty] | Produce and Deliver Agenda OCT 2014 | 1.01.05.03.01 |  | 12290 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 02 | [7 empty] | Produce and Deliver Agenda NOV 2014 | 1.01.05.03.02 |  | 12289 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 03 | [7 empty] | Produce and Deliver Agenda Dec 2014 | 1.01.05.03.03 |  | 12288 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 04 | [7 empty] | Produce and Deliver Agenda Jan 2015 | 1.01.05.03.04 |  | 12287 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 05 | [7 empty] | Produce and Deliver Agenda Feb 2015 | 1.01.05.03.05 |  | 12286 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 06 | [7 empty] | Produce and Deliver Agenda Mar 2015 | 1.01.05.03.06 |  | 12285 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 07 | [7 empty] | Produce and Deliver Agenda Apr 2015 | 1.01.05.03.07 |  | 12284 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 08 | [7 empty] | Produce and Deliver Agenda May 2015 | 1.01.05.03.08 |  | 12283 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 09 | [7 empty] | Produce and Deliver Agenda Jun 2-015 | 1.01.05.03.09 |  | 12282 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 10 | [7 empty] | Produce and Deliver Agenda Jul 2015 | 1.01.05.03.10 |  | 12281 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 11 | [7 empty] | Produce and Deliver Agenda Aug 2015 | 1.01.05.03.11 |  | 12280 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 12 | [7 empty] | Produce and Deliver Agenda Sep 2015 | 1.01.05.03.12 |  | 12279 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 13 | [7 empty] | Produce and Deliver Agenda Oct 2015 | 1.01.05.03.13 |  | 12278 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 14 | [7 empty] | Produce and Deliver Agenda Nov 2015 | 1.01.05.03.14 |  | 12277 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 15 | [7 empty] | Produce and Deliver Agenda Dec 2015 | 1.01.05.03.15 |  | 12276 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 16 | [7 empty] | Produce and Deliver Agenda Jan 20016 | 1.01.05.03.16 |  | 12275 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 17 | [7 empty] | Produce and Deliver Agenda Feb 2016 | 1.01.05.03.17 |  | 12274 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 18 | [7 empty] | Produce and Deliver Agenda Mar 2016 | 1.01.05.03.18 |  | 12273 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 19 | [7 empty] | Produce and Deliver Agenda Apr 2016 | 1.01.05.03.19 |  | 12272 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 20 | [7 empty] | Produce and Deliver Agenda May 2016 | 1.01.05.03.20 |  | 12271 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 21 | [7 empty] | Produce and Deliver Agenda Jun 2016 | 1.01.05.03.21 | 1.7.4 | 6750 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 22 | [7 empty] | Produce and Deliver Agenda Jul 2016 | 1.01.05.03.22 | 1.7.5 | 6751 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 23 | [7 empty] | Produce and Deliver Agenda Aug 2016 | 1.01.05.03.23 | 1.7.6 | 6752 | M | 0 days |  | 0
1 | 01 | 05 | 03 | 24 | [7 empty] | Produce and Deliver Agenda Sep 2016 | 1.01.05.03.24 | 1.7.7 | 6753 | M | 0 days |  | 0
1 | 01 | 05 | 04 | [8 empty] | Quarterly Use Case Requirements Conference Agenda (7.8) | 1.01.05.04 | 1.7.8 | 6754 | S | 435 days |  | 0
1 | 01 | 05 | 04 | 01 | [7 empty] | Quarterly Use Case Requirements Conference Agenda Nov 2014 (7.8) | 1.01.05.04.01 |  | 21964 | M | 0 days |  | 0
1 | 01 | 05 | 04 | 02 | [7 empty] | Quarterly Use Case Requirements Conference Agenda Mar 2015 (7.8) | 1.01.05.04.02 |  | 21963 | M | 0 days |  | 0
1 | 01 | 05 | 04 | 03 | [7 empty] | Quarterly Use Case Requirements Conference Agenda Jul 2015 (7.8) | 1.01.05.04.03 |  | 21965 | M | 0 days |  | 0
1 | 01 | 05 | 04 | 04 | [7 empty] | Quarterly Use Case Requirements Conference Agenda Nov 2015 (7.8) | 1.01.05.04.04 |  | 21966 | M | 0 days |  | 0
1 | 01 | 05 | 04 | 05 | [7 empty] | Quarterly Use Case Requirements Conference Agenda Mar 2016 (7.8) | 1.01.05.04.05 |  | 21967 | M | 0 days |  | 0
1 | 01 | 05 | 04 | 06 | [7 empty] | Quarterly Use Case Requirements Conference Agenda Jul 2016 (7.8) | 1.01.05.04.06 |  | 21968 | M | 0 days |  | 0
1 | 01 | 05 | 05 | [8 empty] | Quarterly Use Case Requirements Conference Minutes (7.9) | 1.01.05.05 | 1.7.9 | 6756 | S | 435 days |  | 0
1 | 01 | 05 | 05 | 01 | [7 empty] | Quarterly Use Case Requirements Conference Minutes Nov 2014 (7.9) | 1.01.05.05.01 | 1.7.9 | 21975 | M | 0 days |  | 0
1 | 01 | 05 | 05 | 02 | [7 empty] | Quarterly Use Case Requirements Conference Minutes Mar 2015 (7.9) | 1.01.05.05.02 | 1.7.9 | 21976 | M | 0 days |  | 0
1 | 01 | 05 | 05 | 03 | [7 empty] | Quarterly Use Case Requirements Conference Minutes Jul 2015 (7.9) | 1.01.05.05.03 | 1.7.9 | 21977 | M | 0 days |  | 0
1 | 01 | 05 | 05 | 04 | [7 empty] | Quarterly Use Case Requirements Conference Minutes Nov 2015 (7.9) | 1.01.05.05.04 | 1.7.9 | 21978 | M | 0 days |  | 0
1 | 01 | 05 | 05 | 05 | [7 empty] | Quarterly Use Case Requirements Conference Minutes Mar 2016 (7.9) | 1.01.05.05.05 | 1.7.9 | 21979 | M | 0 days |  | 0
1 | 01 | 05 | 05 | 06 | [7 empty] | Quarterly Use Case Requirements Conference Minutes Jul 2016 (7.9) | 1.01.05.05.06 | 1.7.9 | 21980 | M | 0 days |  | 0
1 | 01 | 05 | 06 | [8 empty] | Use Case Definition Work Plans (7.10) | 1.01.05.06 | 1.7.10 | 6757 | S | 485 days |  | 0
1 | 01 | 05 | 06 | 01 | [7 empty] | Use Case 1 Develop a Use Case Work Plan Definitions | 1.01.05.06.01 |  | 21985 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 02 | [7 empty] | Use Case 2 Develop a Use Case Work Plan Definitions | 1.01.05.06.02 |  | 21984 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 03 | [7 empty] | Use Case 4 Develop a Use Case Work Plan Definitions | 1.01.05.06.03 |  | 21983 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 04 | [7 empty] | Use Case 5 Develop a Use Case Work Plan Definitions | 1.01.05.06.04 |  | 21986 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 05 | [7 empty] | Use Case 6 Develop a Use Case Work Plan Definitions | 1.01.05.06.05 |  | 21987 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 06 | [7 empty] | Use Case 8 Develop a Use Case Work Plan Definitions | 1.01.05.06.06 |  | 21988 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 07 | [7 empty] | Use Case 9 Develop a Use Case Work Plan Definitions | 1.01.05.06.07 |  | 21989 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 08 | [7 empty] | Use Case 11 Develop a Use Case Work Plan Definitions | 1.01.05.06.08 |  | 21990 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 09 | [7 empty] | Use Case 13 Develop a Use Case Work Plan Definitions | 1.01.05.06.09 |  | 21991 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 10 | [7 empty] | Use Case 14 Develop a Use Case Work Plan Definitions | 1.01.05.06.10 |  | 21992 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 11 | [7 empty] | Use Case 15 Develop a Use Case Work Plan Definitions | 1.01.05.06.11 |  | 21993 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 12 | [7 empty] | Use Case 18 Develop a Use Case Work Plan Definitions | 1.01.05.06.12 |  | 21997 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 13 | [7 empty] | Use Case 19 Develop a Use Case Work Plan Definitions | 1.01.05.06.13 |  | 21998 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 14 | [7 empty] | Use Case 20 Develop a Use Case Work Plan Definitions | 1.01.05.06.14 |  | 21999 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 15 | [7 empty] | Use Case 22 Develop a Use Case Work Plan Definitions | 1.01.05.06.15 |  | 22000 | M | 0 days |  | 0
1 | 01 | 05 | 06 | 16 | [7 empty] | Use Case 24 Develop a Use Case Work Plan Definitions | 1.01.05.06.16 |  | 22001 | M | 0 days |  | 0
1 | 01 | 05 | 07 | [8 empty] | Use Case Requirements Meeting report (7.11) | 1.01.05.07 | 1.7.11 | 6758 | S | 500 days |  | 0
1 | 01 | 05 | 07 | 01 | [7 empty] | Oct 2014 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.01 | 1.7.11 | 22017 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 02 | [7 empty] | Nov 2014 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.02 | 1.7.11 | 22018 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 03 | [7 empty] | Dec 2014 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.03 | 1.7.11 | 22019 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 04 | [7 empty] | Jan 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.04 | 1.7.11 | 22020 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 05 | [7 empty] | Feb 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.05 | 1.7.11 | 22021 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 06 | [7 empty] | Mar 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.06 | 1.7.11 | 22022 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 07 | [7 empty] | Apr 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.07 | 1.7.11 | 22024 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 08 | [7 empty] | May 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.08 | 1.7.11 | 22023 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 09 | [7 empty] | Jun 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.09 | 1.7.11 | 22025 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 10 | [7 empty] | Jul 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.10 | 1.7.11 | 22026 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 11 | [7 empty] | Aug 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.11 | 1.7.11 | 22027 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 12 | [7 empty] | Sep 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.12 | 1.7.11 | 22028 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 13 | [7 empty] | Oct 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.13 | 1.7.11 | 22029 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 14 | [7 empty] | Nov 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.14 | 1.7.11 | 22030 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 15 | [7 empty] | Dec 2015 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.15 | 1.7.11 | 22031 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 16 | [7 empty] | Jan 2016 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.16 | 1.7.11 | 22032 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 17 | [7 empty] | Feb 2016 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.17 | 1.7.11 | 22033 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 18 | [7 empty] | Mar 2016 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.18 | 1.7.11 | 22034 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 19 | [7 empty] | Apr 2016 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.19 | 1.7.11 | 22035 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 20 | [7 empty] | May 2016 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.20 | 1.7.11 | 22036 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 21 | [7 empty] | Jun 2016 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.21 | 1.7.11 | 22037 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 22 | [7 empty] | Jul 2016 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.22 | 1.7.11 | 22038 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 23 | [7 empty] | Aug 2016 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.23 | 1.7.11 | 22039 | M | 0 days |  | 0
1 | 01 | 05 | 07 | 24 | [7 empty] | Sep 2016 Monthly Requirements Assessment Report (Conformant to NDD-5) (5.1.4.1) (7.11) | 1.01.05.07.24 | 1.7.11 | 22040 | M | 0 days |  | 0
1 | 01 | 05 | 08 | [8 empty] | Use Case Technology Meeting Report (7.12) | 1.01.05.08 | 1.7.12 | 6759 | M | 0 days |  | 0
1 | 01 | 05 | 09 | [8 empty] | Draft Use case Descriptions (7.13) | 1.01.05.09 | 1.7.13 | 6760 | M | 0 days |  | 0
1 | 01 | 05 | 10 | [8 empty] | Draft Use Case Description Announcements (7.14) | 1.01.05.10 | 1.7.14 | 6761 | M | 0 days |  | 0
1 | 01 | 05 | 11 | [8 empty] | Common Resolution Conference Agenda (7.15) | 1.01.05.11 | 1.7.15 | 6762 | M | 0 days |  | 0
1 | 01 | 05 | 12 | [8 empty] | Comment Resolution Conference minutes (7.16) | 1.01.05.12 | 1.7.16 | 6763 | M | 0 days |  | 0
1 | 01 | 05 | 13 | [8 empty] | Final Use Case Description (7.17) | 1.01.05.13 | 1.7.17 | 6764 | M | 0 days |  | 0
1 | 01 | 05 | 14 | [8 empty] | Request Letters of Interest (7.18) | 1.01.05.14 | 1.7.18 | 6765 | M | 0 days |  | 0
1 | 01 | 05 | 15 | [8 empty] | Use Case Definition Report (7.19) | 1.01.05.15 | 1.7.19 | 6766 | M | 0 days |  | 0
1 | 01 | 05 | 16 | [8 empty] | Use Case Team Development Work Plan (7.20) | 1.01.05.16 | 1.7.20 | 6767 | M | 0 days |  | 0
1 | 01 | 05 | 17 | [8 empty] | Monthly Team Development Conference Agenda (7.21) | 1.01.05.17 | 1.7.21 | 6768 | M | 0 days |  | 0
1 | 01 | 05 | 18 | [8 empty] | Monthly Team Development Conference Minutes (7.22) | 1.01.05.18 | 1.7.22 | 6769 | M | 0 days |  | 0
1 | 01 | 05 | 19 | [8 empty] | Team Development Meeting Minutes (7.23) | 1.01.05.19 | 1.7.23 | 6770 | M | 0 days |  | 0
1 | 01 | 05 | 20 | [8 empty] | Agreements (7.24) | 1.01.05.20 | 1.7.24 | 6771 | M | 0 days |  | 0
1 | 01 | 05 | 21 | [8 empty] | Roster of Use Case Development and Demonstration Collaborators (7.25) | 1.01.05.21 | 1.7.25 | 6772 | M | 0 days |  | 0
1 | 01 | 05 | 22 | [8 empty] | Monthly Use Case Build Conference Agenda (7.26) | 1.01.05.22 | 1.7.26 | 6773 | M | 0 days |  | 0
1 | 01 | 05 | 23 | [8 empty] | Monthly Use Case Build Conference Minutes (7.27) | 1.01.05.23 | 1.7.27 | 6774 | M | 0 days |  | 0
1 | 01 | 05 | 24 | [8 empty] | Use Case Build Meeting Minutes (7.28) | 1.01.05.24 | 1.7.28 | 6775 | M | 0 days |  | 0
1 | 01 | 05 | 25 | [8 empty] | Use Case Build Plan (7.29) | 1.01.05.25 | 1.7.29 | 6776 | M | 0 days |  | 0
1 | 01 | 05 | 26 | [8 empty] | Draft Use Case Development Report and Demonstration Script (7.30) | 1.01.05.26 | 1.7.30 | 6784 | M | 0 days |  | 0
1 | 01 | 05 | 27 | [8 empty] | Final Use Case Development Report and Demonstration Script (7.31) | 1.01.05.27 | 1.7.31 | 6786 | M | 0 days |  | 0
1 | 01 | 05 | 28 | [8 empty] | Use Case Demonstration Schedule (7.32) | 1.01.05.28 | 1.7.32 | 6787 | M | 0 days |  | 0
1 | 01 | 05 | 29 | [8 empty] | Security Platform Demonstration Report (7.33) | 1.01.05.29 | 1.7.33 | 6788 | M | 0 days |  | 0
1 | 01 | 05 | 30 | [8 empty] | Use Case Demonstration Reports (7.34) | 1.01.05.30 | 1.7.34 | 6789 | M | 0 days |  | 0
1 | 01 | 06 | [9 empty] | Government Furnished Property,Material,Equipment or Information (GFP,GFM,GFE,GFF) (8.0) | 1.01.06 | 1.08 | 6790 | T | 525 days |  | 0
1 | 01 | 07 | [9 empty] | Security (9.0) | 1.01.07 | 1.09 | 6791 | T | 525 days |  | 0
1 | 01 | 08 | [9 empty] | Key Personnel (10.0) | 1.01.08 | 1.1 | 6792 | S | 525 days |  | 0
1 | 01 | 08 | 01 | [8 empty] | Cybersecurity Subject Matter Expert Designated | 1.01.08.01 | 1.10.1 | 6803 | T | 525 days |  | 0
1 | 01 | 08 | 02 | [8 empty] | Cybersecurity Subject Matter Expert Designated | 1.01.08.02 | 1.10.2 | 6802 | T | 525 days |  | 0
1 | 01 | 08 | 03 | [8 empty] | Technology Partnerships Subject Matter Expert Designated | 1.01.08.03 | 1.10.3 | 6801 | T | 525 days |  | 0
1 | 01 | 08 | 04 | [8 empty] | Cybersecurity Security Engineer Designated | 1.01.08.04 | 1.10.4 | 6800 | T | 525 days |  | 0
1 | 01 | 09 | [9 empty] | Travel (11.0) | 1.01.09 | 1.11 | 6793 | T | 525 days |  | 0
1 | 01 | 10 | [9 empty] | Place of performance (12.0) | 1.01.10 | 1.12 | 6794 | T | 525 days |  | 0
1 | 01 | 11 | [9 empty] | Perior of Performance (13.0) | 1.01.11 | 1.13 | 6795 | T | 525 days |  | 0
1 | 01 | 12 | [9 empty] | Risk Levels (14.0) | 1.01.12 | 1.14 | 6796 | T | 525 days |  | 0
| 01 | [10 empty] | TOTAL TASK ORDER 1 | 1.01 |  | Unique ID | A1 |  |  | 43284.99 | 0.25 | 0 | 1447.33 | 0 | 0 | 0 | 0 | 0 | 0 | 1386 | 3271.5 | 0 | 2285 | 3620 | 3392 | 5608 | 0 | 0 | 0 | 2992 | 3624 | 0 | 0 | 4512.32 | 0 | 0 | 0 | 0 | 3552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1910.33 | 1817.16 | 0 | 0 | 134.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551.5 | 0 | 0 | 0 | 0 | 0 | 0 | 169.2 | 0 | 0 | 1012 | 0 | 0 | 0
1 | 02 | [10 empty] | Task Order 2 - Building Block Development and Demonstration | 1.02 | 2 | 6797 | C | 0 |  | 29096.6658
1 | 02 | 15 | [9 empty] | Task Order #2 Major Milestones | 1.02.15 | 2.15 | 6926 | S | 524 days |  | 0
1 | 02 | 15 | 01 | [8 empty] | Task Order 2 Award | 1.02.15.01 | 2.15.1 | 7002 | M | 0 days |  | 0
1 | 02 | 15 | 02 | [8 empty] | Task Order 2 Closure | 1.02.15.02 | 2.15.2 | 7003 | M | 0 days |  | 0
1 | 02 | 01 | [9 empty] | Phase 1 Requirements (5.0) | 1.02.01 | 2.5 | 6814 | C | 520 days |  | 6612.7
1 | 02 | 01 | 01 | [8 empty] | Monthly Building Block Planning and Management Conference Agenda (5.1) | 1.02.01.01 | 1.5.1.1 | 9942 | W | 515 days |  | 3506.7 |  |  | 60 | [7 empty] | 993 |  |  | 1561 | [6 empty] | 445 | [26 empty] | 414 | [29 empty] | 33.7
1 | 02 | 01 | 01 | 01 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Oct 2014 | 1.02.01.01.01 |  | 9943 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 02 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.02 |  | 9944 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 03 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Oct 2014 | 1.02.01.01.03 |  | 9945 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 04 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Nov 2014 | 1.02.01.01.04 |  | 9946 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 05 | [7 empty] | Host MBBPMC Monthly Conference | 1.02.01.01.05 |  | 9947 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 06 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Nov 2014 | 1.02.01.01.06 |  | 9948 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 07 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Dec 2014 | 1.02.01.01.07 |  | 9949 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 08 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.08 |  | 9950 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 09 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Dec 2014 | 1.02.01.01.09 |  | 9951 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 10 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jan 2015 | 1.02.01.01.10 |  | 9952 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 11 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.11 |  | 9953 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 12 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Ian 2015 | 1.02.01.01.12 |  | 9954 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 13 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Feb 2015 | 1.02.01.01.13 |  | 9955 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 14 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.14 |  | 9956 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 15 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Feb 2015 | 1.02.01.01.15 |  | 9957 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 16 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Mar 2015 | 1.02.01.01.16 |  | 9958 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 17 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.17 |  | 9959 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 18 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Mar 2015 | 1.02.01.01.18 |  | 9960 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 19 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Apr 2015 | 1.02.01.01.19 |  | 9961 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 20 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.20 |  | 9962 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 21 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Apr 2015 | 1.02.01.01.21 |  | 9963 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 22 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for May 2015 | 1.02.01.01.22 |  | 9964 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 23 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.23 |  | 9965 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 24 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes May 2015 | 1.02.01.01.24 |  | 9966 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 25 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jun 2015 | 1.02.01.01.25 |  | 9967 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 26 | [7 empty] | Host Monthly Conference | 1.02.01.01.26 |  | 9968 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 27 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jun 2015 | 1.02.01.01.27 |  | 9969 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 28 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jul 2015 | 1.02.01.01.28 |  | 9970 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 29 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.29 |  | 9971 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 30 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes July 2015 | 1.02.01.01.30 |  | 9972 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 31 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Aug 2015 | 1.02.01.01.31 |  | 9973 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 32 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.32 |  | 9974 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 33 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Aug 2015 | 1.02.01.01.33 |  | 9975 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 34 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Sep 2015 | 1.02.01.01.34 |  | 9976 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 35 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.35 |  | 9977 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 36 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Sep 2015 | 1.02.01.01.36 |  | 9978 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 37 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Oct 2015 | 1.02.01.01.37 |  | 9979 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 38 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.38 |  | 9980 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 39 | [7 empty] | Produce and Deliver Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Oct 2015 | 1.02.01.01.39 |  | 9981 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 40 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Nov 2015 | 1.02.01.01.40 |  | 9982 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 41 | [7 empty] | Host Monthly Conference | 1.02.01.01.41 |  | 9983 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 42 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Nov 2015 | 1.02.01.01.42 |  | 9984 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 43 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Dec 2015 | 1.02.01.01.43 |  | 9985 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 44 | [7 empty] | Host Monthly Conference | 1.02.01.01.44 |  | 9986 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 45 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Dec 2015 | 1.02.01.01.45 |  | 9987 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 46 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jan 2016 | 1.02.01.01.46 |  | 9988 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 47 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.47 |  | 9989 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 48 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jan 2016 | 1.02.01.01.48 |  | 9990 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 49 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Feb 2016 | 1.02.01.01.49 |  | 9991 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 50 | [7 empty] | Host Monthly Conference | 1.02.01.01.50 |  | 9992 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 51 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Feb 2016 | 1.02.01.01.51 |  | 9993 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 52 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Mar 2016 | 1.02.01.01.52 |  | 9994 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 53 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.53 |  | 9995 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 54 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Mar 2016 | 1.02.01.01.54 |  | 9996 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 55 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Apr 2016 | 1.02.01.01.55 |  | 9997 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 56 | [7 empty] | Host Monthly Conference | 1.02.01.01.56 |  | 9998 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 57 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Apr 2016 | 1.02.01.01.57 |  | 9999 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 58 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for May 2016 | 1.02.01.01.58 |  | 10000 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 59 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.59 |  | 10001 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 60 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes May 2016 | 1.02.01.01.60 |  | 10002 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 61 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jun 2016 | 1.02.01.01.61 |  | 10003 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 62 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.62 |  | 10004 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 63 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jun 2016 | 1.02.01.01.63 |  | 10005 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 64 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jul 2016 | 1.02.01.01.64 |  | 10006 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 65 | [7 empty] | Host Monthly Conference | 1.02.01.01.65 |  | 10007 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 66 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jul 2016 | 1.02.01.01.66 |  | 10008 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 67 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Aug 2016 | 1.02.01.01.67 |  | 10009 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 68 | [7 empty] | Host Monthly MBBPMC Conference | 1.02.01.01.68 |  | 10010 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 69 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Aug 2016 | 1.02.01.01.69 |  | 10011 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 70 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Sep 2016 | 1.02.01.01.70 |  | 10651 | T | 2 days | 16 | 73.0563 |  |  | 1.25 | [7 empty] | 20.6875 |  |  | 32.5208 | [6 empty] | 9.2708 | [26 empty] | 8.625 | [29 empty] | 0.70208
1 | 02 | 01 | 01 | 71 | [7 empty] | Host Monthly Conference | 1.02.01.01.71 |  | 10652 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
1 | 02 | 01 | 01 | 72 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Sep 2016 | 1.02.01.01.72 |  | 10653 | T | 1 day | 8 | 36.5281 |  |  | 0.625 | [7 empty] | 10.3438 |  |  | 16.2604 | [6 empty] | 4.6354 | [26 empty] | 4.3125 | [29 empty] | 0.35104
| 02 | 01 | 01 | [8 empty] | Total Hours | 1.02.01.01 |  |  | A |  | 768 | 3506.7 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 993 | 0 | 0 | 1561 | 0 | 0 | 0 | 0 | 0 | 0 | 445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.7 | 0 | 0 | 0
1 | 02 | 01 | 02 | [8 empty] | Conduct in-person meetings to review Cybersecurity Issues with Cybersecurity Providers (5.2) | 1.02.01.02 | 1.5.1.2 | 10012 | W | 497 days |  | 3106 | [14 empty] | 0 | 2715 | [30 empty] | 365 | 0 | [29 empty] | 26
1 | 02 | 01 | 02 | 01 | [7 empty] | Conduct in-person meetings (qty 6) to review Cybersecurity Issues (5.2.2) NOV 2014 ( 6 meetings) | 1.02.01.02.01 |  | 10013 | S | 21 days |  | 0 | [15 empty] | 0
1 | 02 | 01 | 02 | 01 | 01 | [6 empty] | Webcast #1 on Cybersecurity Issues | 1.02.01.02.01.01 |  | 10014 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 01 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.01.02 |  | 10015 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 01 | 03 | [6 empty] | Webcast #2 on Cybersecurity Issues | 1.02.01.02.01.03 |  | 10016 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 01 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.01.04 |  | 10017 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 01 | 05 | [6 empty] | Webcast #3 on Cybersecurity Issues | 1.02.01.02.01.05 |  | 10018 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 01 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.01.06 |  | 10019 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 01 | 07 | [6 empty] | Webcast #4 on Cybersecurity Issues | 1.02.01.02.01.07 |  | 10020 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 01 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.01.08 |  | 10021 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 01 | 09 | [6 empty] | Webcast #5 on Cybersecurity Issues | 1.02.01.02.01.09 |  | 10022 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 01 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.01.10 |  | 10023 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 01 | 11 | [6 empty] | Webcast #6 on Cybersecurity Issues | 1.02.01.02.01.11 |  | 10024 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 01 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.01.12 |  | 10025 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | [7 empty] | Conduct in-person meetings (qty 7) to review Cybersecurity Issues (5.2.2) DEC 2014 ( 7 meetings) | 1.02.01.02.02 |  | 10026 | S | 29 days |  | 0
1 | 02 | 01 | 02 | 02 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.02.01 |  | 10027 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #1 | 1.02.01.02.02.02 |  | 10028 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.02.03 |  | 10029 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #2 | 1.02.01.02.02.04 |  | 10030 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.02.05 |  | 10031 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #3 | 1.02.01.02.02.06 |  | 10032 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.02.07 |  | 10033 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #4 | 1.02.01.02.02.08 |  | 10034 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.02.09 |  | 10035 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #5 | 1.02.01.02.02.10 |  | 10036 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.02.11 |  | 10037 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #6 | 1.02.01.02.02.12 |  | 10038 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.02.13 |  | 10039 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 02 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #7 | 1.02.01.02.02.14 |  | 10040 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | [7 empty] | Conduct in-person meetings (qty 8) to review Cybersecurity Issues (5.2.2) JAN 2015 ( 8 meetings) | 1.02.01.02.03 |  | 10041 | S | 22 days |  | 0
1 | 02 | 01 | 02 | 03 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.03.01 |  | 10042 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #1 | 1.02.01.02.03.02 |  | 10043 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.03.03 |  | 10044 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #2 | 1.02.01.02.03.04 |  | 10045 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.03.05 |  | 10046 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #3 | 1.02.01.02.03.06 |  | 10047 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.03.07 |  | 10048 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #4 | 1.02.01.02.03.08 |  | 10049 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.03.09 |  | 10050 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #5 | 1.02.01.02.03.10 |  | 10051 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.03.11 |  | 10052 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #6 | 1.02.01.02.03.12 |  | 10053 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.03.13 |  | 10054 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #7 | 1.02.01.02.03.14 |  | 10055 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.03.15 |  | 10056 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 03 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes #8 | 1.02.01.02.03.16 |  | 10057 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | [7 empty] | Conduct in-person meetings (qty 9) to review Cybersecurity Issues (5.2.2) FEB 2015 ( 9 meetings) | 1.02.01.02.04 |  | 10058 | S | 18 days |  | 0
1 | 02 | 01 | 02 | 04 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.04.01 |  | 10059 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.04.02 |  | 10060 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.04.03 |  | 10061 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.04.04 |  | 10062 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.04.05 |  | 10063 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.04.06 |  | 10064 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.04.07 |  | 10065 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.04.08 |  | 10066 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.04.09 |  | 10067 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.04.10 |  | 10068 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.04.11 |  | 10069 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.04.12 |  | 10070 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.04.13 |  | 10071 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.04.14 |  | 10072 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.04.15 |  | 10073 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.04.16 |  | 10074 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.04.17 |  | 10075 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 04 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.04.18 |  | 10076 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) MAR 2015 ( 10 meetings) | 1.02.01.02.05 |  | 10077 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 05 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.05.01 |  | 10078 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.05.02 |  | 10079 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.05.03 |  | 10080 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.05.04 |  | 10081 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.05.05 |  | 10082 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.05.06 |  | 10083 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.05.07 |  | 10084 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.05.08 |  | 10085 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.05.09 |  | 10086 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.05.10 |  | 10087 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.05.11 |  | 10088 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.05.12 |  | 10089 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.05.13 |  | 10090 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.05.14 |  | 10091 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.05.15 |  | 10092 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.05.16 |  | 10093 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.05.17 |  | 10094 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.05.18 |  | 10095 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.05.19 |  | 10096 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 05 | 20 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.05.20 |  | 10097 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) APR 2015 (10 meetings) | 1.02.01.02.06 |  | 10098 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 06 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.06.01 |  | 10099 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.06.02 |  | 10100 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.06.03 |  | 10101 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.06.04 |  | 10102 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.06.05 |  | 10103 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.06.06 |  | 10104 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.06.07 |  | 10105 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.06.08 |  | 10106 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.06.09 |  | 10107 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.06.10 |  | 10108 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.06.11 |  | 10109 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.06.12 |  | 10110 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.06.13 |  | 10111 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.06.14 |  | 10112 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.06.15 |  | 10113 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.06.16 |  | 10114 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.06.17 |  | 10115 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.06.18 |  | 10116 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.06.19 |  | 10117 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 06 | 20 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.06.20 |  | 10118 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) MAY 2015 ( 10 meetings) | 1.02.01.02.07 |  | 10119 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 07 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.07.01 |  | 10120 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.07.02 |  | 10121 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.07.03 |  | 10122 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.07.04 |  | 10123 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.07.05 |  | 10124 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.07.06 |  | 10125 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.07.07 |  | 10126 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.07.08 |  | 10127 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.07.09 |  | 10128 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.07.10 |  | 10129 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.07.11 |  | 10130 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.07.12 |  | 10131 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.07.13 |  | 10132 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.07.14 |  | 10133 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.07.15 |  | 10134 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.07.16 |  | 10135 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.07.17 |  | 10136 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.07.18 |  | 10137 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.07.19 |  | 10138 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 07 | 20 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.07.20 |  | 10139 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) JUN 2015 ( 10 meetings) | 1.02.01.02.08 |  | 10140 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 08 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.08.01 |  | 10141 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 02 | [6 empty] | PrProduce and Deliver Building Block Planning Meeting Minutes oduce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.08.02 |  | 10142 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.08.03 |  | 10143 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.08.04 |  | 10144 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.08.05 |  | 10145 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.08.06 |  | 10146 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.08.07 |  | 10147 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.08.08 |  | 10148 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.08.09 |  | 10149 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.08.10 |  | 10150 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.08.11 |  | 10151 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.08.12 |  | 10152 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.08.13 |  | 10153 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.08.14 |  | 10154 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.08.15 |  | 10155 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.08.16 |  | 10156 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.08.17 |  | 10157 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.08.18 |  | 10158 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.08.19 |  | 10159 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 08 | 20 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.08.20 |  | 10160 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) JUL 2015 ( 10 meetings) | 1.02.01.02.09 |  | 10161 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 09 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.09.01 |  | 10162 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.09.02 |  | 10163 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.09.03 |  | 10164 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 04 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.09.04 |  | 10165 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.09.05 |  | 10166 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.09.06 |  | 10167 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.09.07 |  | 10168 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.09.08 |  | 10169 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.09.09 |  | 10170 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.09.10 |  | 10171 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.09.11 |  | 10172 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.09.12 |  | 10173 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.09.13 |  | 10174 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.09.14 |  | 10175 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.09.15 |  | 10176 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.09.16 |  | 10177 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.09.17 |  | 10178 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.09.18 |  | 10179 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.09.19 |  | 10180 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 09 | 20 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.09.20 |  | 10181 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) AUG 2015 ( 10 meetings) | 1.02.01.02.10 |  | 10182 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 10 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.10.01 |  | 10183 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.10.02 |  | 10184 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.10.03 |  | 10185 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.10.04 |  | 10186 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.10.05 |  | 10187 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.10.06 |  | 10188 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.10.07 |  | 10189 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.10.08 |  | 10190 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.10.09 |  | 10191 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.10.10 |  | 10192 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.10.11 |  | 10193 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.10.12 |  | 10194 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.10.13 |  | 10195 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.10.14 |  | 10196 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.10.15 |  | 10197 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.10.16 |  | 10198 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.10.17 |  | 10199 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.10.18 |  | 10200 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.10.19 |  | 10201 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 10 | 20 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.10.20 |  | 10202 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) SEP 2015 ( 10 meetings) | 1.02.01.02.11 |  | 10203 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 11 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.11.01 |  | 10204 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.11.02 |  | 10205 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.11.03 |  | 10206 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.11.04 |  | 10207 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.11.05 |  | 10208 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.11.06 |  | 10209 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.11.07 |  | 10210 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.11.08 |  | 10211 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.11.09 |  | 10212 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.11.10 |  | 10213 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.11.11 |  | 10214 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.11.12 |  | 10215 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.11.13 |  | 10216 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.11.14 |  | 10217 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.11.15 |  | 10218 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.11.16 |  | 10219 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.11.17 |  | 10220 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.11.18 |  | 10221 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.11.19 |  | 10222 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 11 | 20 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.11.20 |  | 10223 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) OCT 2015 ( 10 meetings) | 1.02.01.02.12 |  | 10224 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 12 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.12.01 |  | 10225 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.12.02 |  | 10226 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.12.03 |  | 10227 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.12.04 |  | 10228 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.12.05 |  | 10229 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.12.06 |  | 10230 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.12.07 |  | 10231 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.12.08 |  | 10232 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.12.09 |  | 10233 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.12.10 |  | 10234 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.12.11 |  | 10235 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.12.12 |  | 10236 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.12.13 |  | 10237 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.12.14 |  | 10238 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.12.15 |  | 10239 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.12.16 |  | 10240 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.12.17 |  | 10241 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.12.18 |  | 10242 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.12.19 |  | 10243 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 12 | 20 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.12.20 |  | 10244 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) NOV 2015 ( 10 meetings) | 1.02.01.02.13 |  | 10245 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 13 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.13.01 |  | 10246 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.13.02 |  | 10247 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.13.03 |  | 10248 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.13.04 |  | 10249 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.13.05 |  | 10250 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.13.06 |  | 10251 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.13.07 |  | 10252 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.13.08 |  | 10253 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.13.09 |  | 10254 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.13.10 |  | 10255 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.13.11 |  | 10256 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.13.12 |  | 10257 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.13.13 |  | 10258 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.13.14 |  | 10259 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.13.15 |  | 10260 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.13.16 |  | 10261 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.13.17 |  | 10262 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.13.18 |  | 10263 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.13.19 |  | 10264 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 13 | 20 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.13.20 |  | 10265 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) DEC 2015 ( 10 meetings) | 1.02.01.02.14 |  | 10266 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 14 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.14.01 |  | 10267 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.14.02 |  | 10268 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.14.03 |  | 10269 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.14.04 |  | 10270 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.14.05 |  | 10271 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.14.06 |  | 10272 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.14.07 |  | 10273 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.14.08 |  | 10274 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.14.09 |  | 10275 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.14.10 |  | 10276 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.14.11 |  | 10277 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.14.12 |  | 10278 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.14.13 |  | 10279 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.14.14 |  | 10280 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.14.15 |  | 10281 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.14.16 |  | 10282 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.14.17 |  | 10283 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.14.18 |  | 10284 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.14.19 |  | 10285 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 14 | 20 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.14.20 |  | 10286 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) JAN 2016 ( 10 meetings) | 1.02.01.02.15 |  | 10287 | S | 20 days |  | 0
1 | 02 | 01 | 02 | 15 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.15.01 |  | 10288 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 02 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.15.02 |  | 10289 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 03 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.15.03 |  | 10290 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.15.04 |  | 10291 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.15.05 |  | 10292 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.15.06 |  | 10293 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.15.07 |  | 10294 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.15.08 |  | 10295 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.15.09 |  | 10296 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.15.10 |  | 10297 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.15.11 |  | 10298 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.15.12 |  | 10299 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.15.13 |  | 10300 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.15.14 |  | 10301 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.15.15 |  | 10302 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 16 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.15.16 |  | 10303 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.15.17 |  | 10304 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 18 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.15.18 |  | 10305 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.15.19 |  | 10306 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 15 | 20 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.15.20 |  | 10307 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) FEB 2016 ( 10 meetings) | 1.02.01.02.16 |  | 10308 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 16 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.16.01 |  | 10309 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 02 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.16.02 |  | 10310 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.16.03 |  | 10311 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 04 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.16.04 |  | 10312 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.16.05 |  | 10313 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 06 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.16.06 |  | 10314 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.16.07 |  | 10315 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 08 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.16.08 |  | 10316 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.16.09 |  | 10317 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 10 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.16.10 |  | 10318 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.16.11 |  | 10319 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 12 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.16.12 |  | 10320 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.16.13 |  | 10321 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 14 | [6 empty] | Produce and Deliver Building Block Planning Meeting Minutes | 1.02.01.02.16.14 |  | 10322 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.16.15 |  | 10323 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 16 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.16.16 |  | 10324 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.16.17 |  | 10325 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 18 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.16.18 |  | 10326 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.16.19 |  | 10327 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 16 | 20 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.16.20 |  | 10328 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) MAR 2016 ( 10 meetings) | 1.02.01.02.17 |  | 10329 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 17 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.17.01 |  | 10330 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 02 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.17.02 |  | 10331 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.17.03 |  | 10332 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 04 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.17.04 |  | 10333 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.17.05 |  | 10334 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 06 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.17.06 |  | 10335 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.17.07 |  | 10336 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 08 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.17.08 |  | 10337 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.17.09 |  | 10338 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 10 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.17.10 |  | 10339 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.17.11 |  | 10340 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 12 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.17.12 |  | 10341 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.17.13 |  | 10342 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 14 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.17.14 |  | 10343 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.17.15 |  | 10344 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 16 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.17.16 |  | 10345 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.17.17 |  | 10346 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 18 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.17.18 |  | 10347 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.17.19 |  | 10348 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 17 | 20 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.17.20 |  | 10349 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) APR 2016 ( 10 meetings) | 1.02.01.02.18 |  | 10350 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 18 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.18.01 |  | 10351 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 02 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.18.02 |  | 10352 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.18.03 |  | 10353 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 04 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.18.04 |  | 10354 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.18.05 |  | 10355 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 06 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.18.06 |  | 10356 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.18.07 |  | 10357 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 08 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.18.08 |  | 10358 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.18.09 |  | 10359 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 10 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.18.10 |  | 10360 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.18.11 |  | 10361 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 12 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.18.12 |  | 10362 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.18.13 |  | 10363 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 14 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.18.14 |  | 10364 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.18.15 |  | 10365 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 16 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.18.16 |  | 10366 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.18.17 |  | 10367 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 18 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.18.18 |  | 10368 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.18.19 |  | 10369 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 18 | 20 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.18.20 |  | 10370 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) MAY 2016 ( 10 meetings) | 1.02.01.02.19 |  | 10371 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 19 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.19.01 |  | 10372 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 02 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.19.02 |  | 10373 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.19.03 |  | 10374 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 04 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.19.04 |  | 10375 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.19.05 |  | 10376 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 06 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.19.06 |  | 10377 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.19.07 |  | 10378 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 08 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.19.08 |  | 10379 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.19.09 |  | 10380 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 10 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.19.10 |  | 10381 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.19.11 |  | 10382 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 12 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.19.12 |  | 10383 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.19.13 |  | 10384 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 14 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.19.14 |  | 10385 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.19.15 |  | 10386 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 16 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.19.16 |  | 10387 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.19.17 |  | 10388 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 18 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.19.18 |  | 10389 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.19.19 |  | 10390 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 19 | 20 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.19.20 |  | 10391 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) JUN 2016 ( 10 meetings) | 1.02.01.02.20 |  | 10392 | S | 21 days |  | 0
1 | 02 | 01 | 02 | 20 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.20.01 |  | 10393 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 02 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.20.02 |  | 10394 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.20.03 |  | 10395 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 04 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.20.04 |  | 10396 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.20.05 |  | 10397 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 06 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.20.06 |  | 10398 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.20.07 |  | 10399 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 08 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.20.08 |  | 10400 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.20.09 |  | 10401 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 10 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.20.10 |  | 10402 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.20.11 |  | 10403 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 12 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.20.12 |  | 10404 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.20.13 |  | 10405 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 14 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.20.14 |  | 10406 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.20.15 |  | 10407 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 16 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.20.16 |  | 10408 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.20.17 |  | 10409 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 18 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.20.18 |  | 10410 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.20.19 |  | 10411 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 20 | 20 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.20.20 |  | 10412 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) JUL 2016 ( 10 meetings) | 1.02.01.02.21 |  | 10413 | S | 21 days | 0 | 0
1 | 02 | 01 | 02 | 21 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.21.01 |  | 10414 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 02 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.21.02 |  | 10415 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.21.03 |  | 10416 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 04 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.21.04 |  | 10417 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.21.05 |  | 10418 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 06 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.21.06 |  | 10419 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.21.07 |  | 10420 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 08 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.21.08 |  | 10421 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.21.09 |  | 10422 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 10 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.21.10 |  | 10423 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.21.11 |  | 10424 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 12 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.21.12 |  | 10425 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.21.13 |  | 10426 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 14 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.21.14 |  | 10427 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.21.15 |  | 10428 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 16 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.21.16 |  | 10429 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.21.17 |  | 10430 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 18 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.21.18 |  | 10431 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.21.19 |  | 10432 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 21 | 20 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.21.20 |  | 10433 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) AUG 2016 ( 10 meetings) | 1.02.01.02.22 |  | 10434 | S | 23 days |  | 0
1 | 02 | 01 | 02 | 22 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.22.01 |  | 10435 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 02 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.22.02 |  | 10436 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.22.03 |  | 10437 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 04 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.22.04 |  | 10438 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.22.05 |  | 10439 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 06 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.22.06 |  | 10440 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.22.07 |  | 10441 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 08 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.22.08 |  | 10442 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.22.09 |  | 10443 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 10 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.22.10 |  | 10444 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.22.11 |  | 10445 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 12 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.22.12 |  | 10446 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.22.13 |  | 10447 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 14 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.22.14 |  | 10448 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.22.15 |  | 10449 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 16 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.22.16 |  | 10450 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 17 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.22.17 |  | 10451 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 18 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.22.18 |  | 10452 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 19 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.22.19 |  | 10453 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 22 | 20 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.22.20 |  | 10454 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | [7 empty] | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.2.2) SEP 2016 ( 10 meetings) | 1.02.01.02.23 |  | 10656 | S | 18 days |  | 0
1 | 02 | 01 | 02 | 23 | 01 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.23.01 |  | 10657 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 02 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.23.02 |  | 10658 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 03 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.23.03 |  | 10659 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 04 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.23.04 |  | 10660 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 05 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.23.05 |  | 10661 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 06 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.23.06 |  | 10662 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 07 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.23.07 |  | 10663 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 08 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.23.08 |  | 10664 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 09 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.23.09 |  | 10665 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 10 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.23.10 |  | 10666 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 11 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.23.11 |  | 10667 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 12 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.23.12 |  | 10668 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 13 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.23.13 |  | 10669 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 14 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.23.14 |  | 10670 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 15 | [6 empty] | Webcast on Cybersecurity Issues | 1.02.01.02.23.15 |  | 10671 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 23 | 16 | [6 empty] | Produce and Deliver Business Requirements Meeting Minutes | 1.02.01.02.23.16 |  | 10672 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | [7 empty] | Monthly Building Block Team Development Conference | 1.02.01.02.24 |  | 11271 | S | 416 days |  | 0
1 | 02 | 01 | 02 | 24 | 01 | [6 empty] | Beginning Feb 2015-Building Block Team Development Conference | 1.02.01.02.24.01 | 2.5.7 | 11267 | S | 44 days |  | 0
1 | 02 | 01 | 02 | 24 | 01 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.01.01 |  | 11268 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 01 | 02 | [5 empty] | Conviene the Initial Building Block Team Development Conference for Block 1 | 1.02.01.02.24.01.02 |  | 11269 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 01 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.01.03 |  | 11270 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 02 | [6 empty] | May 2015 - Building Block Team Development Conference | 1.02.01.02.24.02 | 2.5.7 | 11292 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 02 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.02.01 |  | 11293 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 02 | 02 | [5 empty] | Conviene the Initial Building Block Team Development Conference | 1.02.01.02.24.02.02 |  | 11294 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 02 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.02.03 |  | 11295 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 03 | [6 empty] | Jun 2015 - Building Block Team Development Conference | 1.02.01.02.24.03 | 2.5.7 | 11297 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 03 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.03.01 |  | 11298 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 03 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.03.02 |  | 11299 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 03 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.03.03 |  | 11300 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 04 | [6 empty] | Jul 2015 - Building Block Team Development Conference | 1.02.01.02.24.04 | 2.5.7 | 11303 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 04 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.04.01 |  | 11304 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 04 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.04.02 |  | 11305 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 04 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.04.03 |  | 11306 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 05 | [6 empty] | Aug 2015 - Building Block Team Development Conference | 1.02.01.02.24.05 | 2.5.7 | 11311 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 05 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.05.01 |  | 11312 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 05 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.05.02 |  | 11313 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 05 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.05.03 |  | 11314 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 06 | [6 empty] | Sep 2015 - Building Block Team Development Conference | 1.02.01.02.24.06 | 2.5.7 | 11319 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 06 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.06.01 |  | 11320 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 06 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.06.02 |  | 11321 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 06 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.06.03 |  | 11322 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 07 | [6 empty] | Oct 2015 - Building Block Team Development Conference | 1.02.01.02.24.07 | 2.5.7 | 11327 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 07 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.07.01 |  | 11328 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 07 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.07.02 |  | 11329 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 07 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.07.03 |  | 11330 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 08 | [6 empty] | Nov 2015 - Building Block Team Development Conference | 1.02.01.02.24.08 | 2.5.7 | 11367 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 08 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.08.01 |  | 11368 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 08 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.08.02 |  | 11369 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 08 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.08.03 |  | 11370 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 09 | [6 empty] | Dec 2015 - Building Block Team Development Conference | 1.02.01.02.24.09 | 2.5.7 | 11387 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 09 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.09.01 |  | 11388 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 09 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.09.02 |  | 11389 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 09 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.09.03 |  | 11390 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 10 | [6 empty] | Jan 2016 - Building Block Team Development Conference | 1.02.01.02.24.10 | 2.5.7 | 11439 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 10 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.10.01 |  | 11440 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 10 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.10.02 |  | 11441 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 10 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.10.03 |  | 11442 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 11 | [6 empty] | Feb 2016 - Building Block Team Development Conference | 1.02.01.02.24.11 | 2.5.7 | 11539 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 11 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.11.01 |  | 11540 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 11 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.11.02 |  | 11541 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 11 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.11.03 |  | 11542 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 12 | [6 empty] | Mar 2016 - Building Block Team Development Conference | 1.02.01.02.24.12 | 2.5.7 | 11639 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 12 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.12.01 |  | 11640 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 12 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.12.02 |  | 11641 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 12 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.12.03 |  | 11642 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 13 | [6 empty] | Apr 2016 - Building Block Team Development Conference | 1.02.01.02.24.13 | 2.5.7 | 11739 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 13 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.13.01 |  | 11740 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 13 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.13.02 |  | 11741 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 13 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.13.03 |  | 11742 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 14 | [6 empty] | May 2016 - Building Block Team Development Conference | 1.02.01.02.24.14 | 2.5.7 | 11839 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 14 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.14.01 |  | 11840 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 14 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.14.02 |  | 11841 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 14 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.14.03 |  | 11842 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 15 | [6 empty] | Jun 2016 - Building Block Team Development Conference | 1.02.01.02.24.15 | 2.5.7 | 11939 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 15 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.15.01 |  | 11940 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 15 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.15.02 |  | 11941 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 15 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.15.03 |  | 11942 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 16 | [6 empty] | Jul 2016 - Building Block Team Development Conference | 1.02.01.02.24.16 | 2.5.7 | 12039 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 16 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.16.01 |  | 12040 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 16 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.16.02 |  | 12041 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 16 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.16.03 |  | 12042 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 17 | [6 empty] | Aug 2016 - Building Block Team Development Conference | 1.02.01.02.24.17 | 2.5.7 | 12139 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 17 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.17.01 |  | 12140 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 17 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.17.02 |  | 12141 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 17 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.17.03 |  | 12142 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 18 | [6 empty] | Sep 2016 - Building Block Team Development Conference | 1.02.01.02.24.18 | 2.5.7 | 12239 | S | 8 days |  | 0
1 | 02 | 01 | 02 | 24 | 18 | 01 | [5 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR | 1.02.01.02.24.18.01 |  | 12240 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 18 | 02 | [5 empty] | Conviene the Building Block Team Development Conference | 1.02.01.02.24.18.02 |  | 12241 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
1 | 02 | 01 | 02 | 24 | 18 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes | 1.02.01.02.24.18.03 |  | 12242 | T | 1 day | 8 | 6.3388 | [14 empty] | 0 | 5.5408 | [30 empty] | 0.7449 | 0 | [29 empty] | 0.053061
| 02 | 01 | 02 | [8 empty] | Total Hours | 1.02.01.02 |  |  | A |  | 3920 | 3106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0
1 | 02 | 02 | [9 empty] | Phase 2 | 1.02.02 |  | 23377 | C | 478 days |  | 7242.0053
1 | 02 | 02 | 01 | [8 empty] | Draft Building Block Descriptions (5.3) | 1.02.02.01 |  | 10461 | W | 472 days |  | 4590.13 | [9 empty] | 673.68 | 867.29 |  |  | 1040.75 |  | 0 | [7 empty] | 981.05 | [9 empty] | 623.15 | [12 empty] | 67.37 | 0 | [19 empty] | 168.42 | 0 | [5 empty] | 168.42
1 | 02 | 02 | 01 | 01 | [7 empty] | Draft Building Block Description Block 1 (5.3) | 1.02.02.01.01 |  | 10456 | S | 73 days |  | 0 | [9 empty] | 0 |  |  |  | 0
1 | 02 | 02 | 01 | 01 | 01 | [6 empty] | Approval from COR on Block 1 Building Block Description (IMP) | 1.02.02.01.01.01 |  | 10654 | M | 0 days | 0 | 0 | [9 empty] | 0 |  |  |  | 0
1 | 02 | 02 | 01 | 01 | 02 | [6 empty] | Create Building Block Description | 1.02.02.01.01.02 |  | 10457 | T | 60 edays | 480 | 643.4762 | [9 empty] | 94.4411 | 121.5827 |  |  | 145.8995 |  | 0 | [7 empty] | 137.5304 | [9 empty] | 87.3575 | [12 empty] | 9.4444 | 0 | [19 empty] | 23.6103 | 0 | [5 empty] | 23.6103
1 | 02 | 02 | 01 | 01 | 03 | [6 empty] | Deliver Building Block Description to the COR | 1.02.02.01.01.03 |  | 10458 | T | 1 day | 8 | 10.7246 | [9 empty] | 1.574 | 2.0264 |  |  | 2.4317 |  | 0 | [7 empty] | 2.2922 | [9 empty] | 1.456 | [12 empty] | 0.15741 | 0 | [19 empty] | 0.3935 | 0 | [5 empty] | 0.3935
1 | 02 | 02 | 01 | 01 | 04 | [6 empty] | COR review of Block Description | 1.02.02.01.01.04 |  | 10459 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 01 | 05 | [6 empty] | Changes to the Block Description | 1.02.02.01.01.05 |  | 10460 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 01 | 06 | [6 empty] | Approval from COR on Block 1 | 1.02.02.01.01.06 |  | 10700 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 02 | [7 empty] | Draft Building Block Description Block 2 (5.3) | 1.02.02.01.02 |  | 10467 | S | 73 days |  | 0 | [9 empty] | 0 |  |  |  | 0
1 | 02 | 02 | 01 | 02 | 01 | [6 empty] | Approval from COR for Block 2 | 1.02.02.01.02.01 |  | 10678 | M | 0 days | 0 | 0 | [9 empty] | 0 |  |  |  | 0
1 | 02 | 02 | 01 | 02 | 02 | [6 empty] | Create Building Block 2 Description | 1.02.02.01.02.02 |  | 10687 | T | 60 edays | 480 | 643.4762 | [9 empty] | 94.4411 | 121.5827 |  |  | 145.8995 |  | 0 | [7 empty] | 137.5304 | [9 empty] | 87.3575 | [12 empty] | 9.4444 | 0 | [19 empty] | 23.6103 | 0 | [5 empty] | 23.6103
1 | 02 | 02 | 01 | 02 | 03 | [6 empty] | Deliver Building Block Description to the COR | 1.02.02.01.02.03 |  | 10688 | T | 1 day | 8 | 10.7246 | [9 empty] | 1.574 | 2.0264 |  |  | 2.4317 |  | 0 | [7 empty] | 2.2922 | [9 empty] | 1.456 | [12 empty] | 0.15741 | 0 | [19 empty] | 0.3935 | 0 | [5 empty] | 0.3935
1 | 02 | 02 | 01 | 02 | 04 | [6 empty] | COR review of Block Description | 1.02.02.01.02.04 |  | 10689 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 02 | 05 | [6 empty] | Changes to the Block Description | 1.02.02.01.02.05 |  | 10690 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 02 | 06 | [6 empty] | Approval from COR on Block 2 Block Description | 1.02.02.01.02.06 |  | 10703 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 03 | [7 empty] | Draft Building Block Description Block 3 (5.3) | 1.02.02.01.03 |  | 10493 | S | 73 days |  | 0 | [9 empty] | 0 |  |  |  | 0
1 | 02 | 02 | 01 | 03 | 01 | [6 empty] | Approval by COR Block 3 | 1.02.02.01.03.01 |  | 10691 | M | 0 days | 0 | 0 | [9 empty] | 0 |  |  |  | 0
1 | 02 | 02 | 01 | 03 | 02 | [6 empty] | Create Building Block 3 Description | 1.02.02.01.03.02 |  | 10494 | T | 60 edays | 480 | 643.4762 | [9 empty] | 94.4411 | 121.5827 |  |  | 145.8995 |  | 0 | [7 empty] | 137.5304 | [9 empty] | 87.3575 | [12 empty] | 9.4444 | 0 | [19 empty] | 23.6103 | 0 | [5 empty] | 23.6103
1 | 02 | 02 | 01 | 03 | 03 | [6 empty] | Deliver Building Block Description to the COR | 1.02.02.01.03.03 |  | 10495 | T | 1 day | 8 | 10.7246 | [9 empty] | 1.574 | 2.0264 |  |  | 2.4317 |  | 0 | [7 empty] | 2.2922 | [9 empty] | 1.456 | [12 empty] | 0.15741 | 0 | [19 empty] | 0.3935 | 0 | [5 empty] | 0.3935
1 | 02 | 02 | 01 | 03 | 04 | [6 empty] | COR review of Block Description | 1.02.02.01.03.04 |  | 10496 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 03 | 05 | [6 empty] | Changes to the Block Description | 1.02.02.01.03.05 |  | 10497 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 03 | 06 | [6 empty] | Denial from COR on Block 3 | 1.02.02.01.03.06 |  | 10705 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 04 | [7 empty] | Draft Building Block Description Block 4 (5.3) | 1.02.02.01.04 |  | 10518 | S | 74 days |  | 0 | [9 empty] | 0 |  |  |  | 0
1 | 02 | 02 | 01 | 04 | 01 | [6 empty] | Approval by COR | 1.02.02.01.04.01 |  | 10693 | M | 0 days | 0 | 0 | [9 empty] | 0 |  |  |  | 0
1 | 02 | 02 | 01 | 04 | 02 | [6 empty] | Create Building Block Description | 1.02.02.01.04.02 |  | 10519 | T | 60 edays | 480 | 643.4762 | [9 empty] | 94.4411 | 121.5827 |  |  | 145.8995 |  | 0 | [7 empty] | 137.5304 | [9 empty] | 87.3575 | [12 empty] | 9.4444 | 0 | [19 empty] | 23.6103 | 0 | [5 empty] | 23.6103
1 | 02 | 02 | 01 | 04 | 03 | [6 empty] | Deliver Building Block Description to the COR | 1.02.02.01.04.03 |  | 10520 | T | 1 day | 8 | 10.7246 | [9 empty] | 1.574 | 2.0264 |  |  | 2.4317 |  | 0 | [7 empty] | 2.2922 | [9 empty] | 1.456 | [12 empty] | 0.15741 | 0 | [19 empty] | 0.3935 | 0 | [5 empty] | 0.3935
1 | 02 | 02 | 01 | 04 | 04 | [6 empty] | COR review of Block Description | 1.02.02.01.04.04 |  | 10521 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 04 | 05 | [6 empty] | Changes to the Block Description | 1.02.02.01.04.05 |  | 10522 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 04 | 06 | [6 empty] | Denial from COR on Block 4 | 1.02.02.01.04.06 |  | 11113 | T | 10 days | 80 | 107.246 | [9 empty] | 15.7402 | 20.2638 |  |  | 24.3166 |  | 0 | [7 empty] | 22.9217 | [9 empty] | 14.5596 | [12 empty] | 1.5741 | 0 | [19 empty] | 3.935 | 0 | [5 empty] | 3.935
1 | 02 | 02 | 01 | 05 | [7 empty] | Draft Building Block Description Block 5 (5.3) | 1.02.02.01.05 |  | 10563 | T | 64 days | 512 | 686.3746 | [9 empty] | 100.7372 | 129.6882 |  |  | 155.6262 |  | 0 | [7 empty] | 146.6991 | [9 empty] | 93.1813 | [12 empty] | 10.074 | 0 | [19 empty] | 25.1843 | 0 | [5 empty] | 25.1843
1 | 02 | 02 | 01 | 06 | [7 empty] | Denial by COR | 1.02.02.01.06 |  | 10694 | M | 0 days |  | 0 | [9 empty] | 0 | 0 |  |  | 0
| 02 | 02 | 01 | [8 empty] | Total Hours | 1.02.02.01 |  |  | A |  | 3424 | 4590.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 673.68 | 867.29 | 0 | 0 | 1040.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 981.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168.42 | 0 | 0 | 0 | 0 | 0 | 0 | 168.42 | 0 | 0 | 0 | 0 | 0 | 0
1 | 02 | 02 | 02 | [8 empty] | Public and Technology Provider View (5.4) | 1.02.02.02 |  | 22041 | W | 356 days |  | 1113.2153 | [9 empty] | 160 | 0 |  |  | 346.91 | 197.47 | 366.73 | [51 empty] | 25.2632 | [6 empty] | 16.8421
1 | 02 | 02 | 02 | 01 | [7 empty] | Block 1 Publishing (5.4) | 1.02.02.02.01 | 2.5.4 | 11107 | S | 62 days |  | 0 | [9 empty] | 0 |  |  |  | 0 | 0 | 0 | [58 empty] | 0
1 | 02 | 02 | 02 | 01 | 01 | [6 empty] | Publish the Draft Building Block 1 Description for Public Comment (5.4) | 1.02.02.02.01.01 |  | 6819 | T | 30 edays | 240 | 128.4479 | [9 empty] | 18.4615 | 0 |  |  | 40.0281 | 22.785 | 42.315 | [51 empty] | 2.915 | [6 empty] | 1.9433
1 | 02 | 02 | 02 | 01 | 02 | [6 empty] | Execute a Comment Resolution Conference Agenda | 1.02.02.02.01.02 |  | 11108 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 01 | 03 | [6 empty] | Conduct a Comment resolution Conference | 1.02.02.02.01.03 |  | 11114 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 01 | 04 | [6 empty] | Comment Resolution Conference Minutes | 1.02.02.02.01.04 |  | 11109 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 01 | 05 | [6 empty] | Issuance of Requests to Interested Technology Providers (30) days to reply. | 1.02.02.02.01.05 |  | 11110 | T | 30 edays | 240 | 128.4479 | [9 empty] | 18.4615 | 0 |  |  | 40.0281 | 22.785 | 42.315 | [51 empty] | 2.915 | [6 empty] | 1.9433
1 | 02 | 02 | 02 | 01 | 06 | [6 empty] | Publish Final Building Block Description Block 1 (5.3) (IMP) | 1.02.02.02.01.06 |  | 11111 | T | 2 days | 16 | 8.5632 | [9 empty] | 1.2308 | 0 |  |  | 2.6685 | 1.519 | 2.821 | [51 empty] | 0.19433 | [6 empty] | 0.12955
1 | 02 | 02 | 02 | 02 | [7 empty] | Block 2 Publishing (5.4) | 1.02.02.02.02 | 2.5.4 | 11212 | S | 62 days |  | 0 | [9 empty] | 0 |  |  |  | 0 | 0 | 0 | [58 empty] | 0
1 | 02 | 02 | 02 | 02 | 01 | [6 empty] | Publish the Draft Building Block Description for Public Comment (5.4) | 1.02.02.02.02.01 |  | 11213 | T | 30 edays | 240 | 128.4479 | [9 empty] | 18.4615 | 0 |  |  | 40.0281 | 22.785 | 42.315 | [51 empty] | 2.915 | [6 empty] | 1.9433
1 | 02 | 02 | 02 | 02 | 02 | [6 empty] | Execute a Comment Resolution Conference Agenda | 1.02.02.02.02.02 |  | 11214 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 02 | 03 | [6 empty] | Conduct a Comment Resolution Conference | 1.02.02.02.02.03 |  | 11215 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 02 | 04 | [6 empty] | Comment Resolution Conference Minutes | 1.02.02.02.02.04 |  | 11216 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 02 | 05 | [6 empty] | Issuance of Requests to Interested Technology Providers (30) days to reply. | 1.02.02.02.02.05 |  | 11217 | T | 30 edays | 240 | 128.4479 | [9 empty] | 18.4615 | 0 |  |  | 40.0281 | 22.785 | 42.315 | [51 empty] | 2.915 | [6 empty] | 1.9433
1 | 02 | 02 | 02 | 02 | 06 | [6 empty] | Publish Final Building Block Description Block 2 (5.3) (IMP) | 1.02.02.02.02.06 |  | 11218 | T | 2 days | 16 | 8.5632 | [9 empty] | 1.2308 | 0 |  |  | 2.6685 | 1.519 | 2.821 | [51 empty] | 0.19433 | [6 empty] | 0.12955
1 | 02 | 02 | 02 | 03 | [7 empty] | Block 3 Publishing (5.4) | 1.02.02.02.03 | 2.5.4 | 11237 | S | 62 days |  | 0 | [9 empty] | 0 |  |  |  | 0 | 0 | 0 | [58 empty] | 0
1 | 02 | 02 | 02 | 03 | 01 | [6 empty] | Publish the Draft Building Block 3 Description for Public Comment (5.4) | 1.02.02.02.03.01 |  | 11238 | T | 30 edays | 240 | 128.4479 | [9 empty] | 18.4615 | 0 |  |  | 40.0281 | 22.785 | 42.315 | [51 empty] | 2.915 | [6 empty] | 1.9433
1 | 02 | 02 | 02 | 03 | 02 | [6 empty] | Execute a Comment Resolution Conference Agenda (5.4) Block 3 | 1.02.02.02.03.02 |  | 11239 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 03 | 03 | [6 empty] | Conduct a Comment Resolution Conference (5.4) | 1.02.02.02.03.03 |  | 11240 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 03 | 04 | [6 empty] | Comment Resolution Conference Minutes | 1.02.02.02.03.04 |  | 11241 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 03 | 05 | [6 empty] | Issuance of Requests to Interested Technology Providers (30) days to reply. | 1.02.02.02.03.05 |  | 11242 | T | 30 edays | 240 | 128.4479 | [9 empty] | 18.4615 | 0 |  |  | 40.0281 | 22.785 | 42.315 | [51 empty] | 2.915 | [6 empty] | 1.9433
1 | 02 | 02 | 02 | 03 | 06 | [6 empty] | Publish Final Building Block Description Block 3 (5.3) (IMP) | 1.02.02.02.03.06 |  | 11243 | T | 2 days | 16 | 8.5632 | [9 empty] | 1.2308 | 0 |  |  | 2.6685 | 1.519 | 2.821 | [51 empty] | 0.19433 | [6 empty] | 0.12955
1 | 02 | 02 | 02 | 04 | [7 empty] | Block 4 Publishing (5.4) | 1.02.02.02.04 | 2.5.4 | 11253 | S | 62 days |  | 0 | [9 empty] | 0 |  |  |  | 0 | 0 | 0 | [58 empty] | 0
1 | 02 | 02 | 02 | 04 | 01 | [6 empty] | Publish the Draft Building Block Description for Public Comment (5.4) | 1.02.02.02.04.01 |  | 11254 | T | 30 edays | 240 | 128.4479 | [9 empty] | 18.4615 | 0 |  |  | 40.0281 | 22.785 | 42.315 | [51 empty] | 2.915 | [6 empty] | 1.9433
1 | 02 | 02 | 02 | 04 | 02 | [6 empty] | Execute a Comment Resolution Conference Agenda | 1.02.02.02.04.02 |  | 11255 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 04 | 03 | [6 empty] | Conduct a Comment resolution Conference | 1.02.02.02.04.03 |  | 11256 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 04 | 04 | [6 empty] | Comment Resolution Conference Minutes | 1.02.02.02.04.04 |  | 11257 | T | 1 day | 8 | 4.2816 | [9 empty] | 0.61538 | 0 |  |  | 1.3343 | 0.7595 | 1.4105 | [51 empty] | 0.097166 | [6 empty] | 0.064777
1 | 02 | 02 | 02 | 04 | 05 | [6 empty] | Issuance of Requests to Interested Technology Providers (30) days to reply. | 1.02.02.02.04.05 |  | 11258 | T | 30 edays | 240 | 128.4479 | [9 empty] | 18.4615 | 0 |  |  | 40.0281 | 22.785 | 42.315 | [51 empty] | 2.915 | [6 empty] | 1.9433
1 | 02 | 02 | 02 | 04 | 06 | [6 empty] | Publish Final Building Block Description Block 4 (5.3) (IMP) | 1.02.02.02.04.06 |  | 11259 | T | 2 days | 16 | 8.5632 | [9 empty] | 1.2308 | 0 |  |  | 2.6685 | 1.519 | 2.821 | [51 empty] | 0.19433 | [6 empty] | 0.12955
| 02 | 02 | 02 | [8 empty] | Total Hours | 1.02.02.02 |  |  | A |  | 2080 | 1113.2153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 346.91 | 197.47 | 366.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 16.8421 | 0 | 0 | 0 | 0 | 0 | 0
1 | 02 | 02 | 03 | [8 empty] | Develop and Revise a Building Block Project Plan (5.5) | 1.02.02.03 |  | 22042 | W | 345 days |  | 1538.66 | [9 empty] | 555 | 0 |  |  | 663.66 |  | 320
1 | 02 | 02 | 03 | 01 | [7 empty] | Block 1 Project Plan (5.5) | 1.02.02.03.01 | 2.5.5 | 22043 | S | 51 days |  | 0
1 | 02 | 02 | 03 | 01 | 01 | [6 empty] | Develop Building Block Project Plan (5.5) Block 1 | 1.02.02.03.01.01 |  | 6862 | T | 30 days | 240 | 127.4272 | [9 empty] | 80.8252 | 0 |  |  |  |  | 46.6019
1 | 02 | 02 | 03 | 01 | 02 | [6 empty] | Deliver Building Block Project Plan to COR (5.5) Block 1 | 1.02.02.03.01.02 |  | 11115 | T | 1 day | 8 | 4.2476 | [9 empty] | 2.6942 | 0 |  |  |  |  | 1.5534
1 | 02 | 02 | 03 | 01 | 03 | [6 empty] | COR Reviews Block 1 Project Plan (5.5) | 1.02.02.03.01.03 |  | 11116 | T | 10 days | 80 | 42.4757 | [9 empty] | 26.9417 | 0 |  |  |  |  | 15.534
1 | 02 | 02 | 03 | 01 | 04 | [6 empty] | NCCoE revises Block 1 Project Plan based on review by COR (5.5) | 1.02.02.03.01.04 |  | 11117 | T | 10 days | 80 | 42.4757 | [9 empty] | 26.9417 | 0 |  |  |  |  | 15.534
1 | 02 | 02 | 03 | 01 | 05 | [6 empty] | COR Approves the Block 1 Building Block Project Plan (5.5) (IMP) | 1.02.02.03.01.05 |  | 11125 | M | 0 days | 0 | 0
1 | 02 | 02 | 03 | 02 | 06 | [6 empty] | Receive letters of Interest from Providers expressing interest in Participating for Block 1 | 1.02.02.03.01.06 |  | 11121 | T | 1 day | 8 | 4.2476 | [9 empty] | 2.6942 | 0 |  |  |  |  | 1.5534
1 | 02 | 02 | 03 | 02 | [7 empty] | Block 2 Project Plan (5.5) | 1.02.02.03.02 | 2.5.5 | 22044 | S | 51 days |  | 0
1 | 02 | 02 | 03 | 02 | 01 | [6 empty] | Develop Building Block Project Plan (5.5) Block 2 | 1.02.02.03.02.01 |  | 11219 | T | 30 days | 240 | 127.4272 | [9 empty] | 80.8252 | 0 |  |  |  |  | 46.6019
1 | 02 | 02 | 03 | 02 | 02 | [6 empty] | Deliver Building Block Project Plan to COR (5.5) Block 2 | 1.02.02.03.02.02 |  | 11220 | T | 1 day | 8 | 4.2476 | [9 empty] | 2.6942 | 0 |  |  |  |  | 1.5534
1 | 02 | 02 | 03 | 02 | 03 | [6 empty] | COR Reviews Block 2 Project Plan (5.5) Block 2 | 1.02.02.03.02.03 |  | 11221 | T | 10 days | 80 | 42.4757 | [9 empty] | 26.9417 | 0 |  |  |  |  | 15.534
1 | 02 | 02 | 03 | 02 | 04 | [6 empty] | NCCoE revises Block 2 Project Plan based on review by COR (5.5) Block 2 | 1.02.02.03.02.04 |  | 11222 | T | 10 days | 80 | 42.4757 | [9 empty] | 26.9417 | 0 |  |  |  |  | 15.534
1 | 02 | 02 | 03 | 02 | 05 | [6 empty] | COR Approves the Block 2 Building Block Project Plan (IMP) (5.5) Block 2 | 1.02.02.03.02.05 |  | 11223 | M | 0 days | 0 | 0
1 | 02 | 02 | 03 | 02 | 06 | [6 empty] | Receive letters of Interest from Providers expressing interest in Participating | 1.02.02.03.02.06 |  | 11224 | T | 1 day | 8 | 4.2476 | [9 empty] | 2.6942 | 0 |  |  |  |  | 1.5534
1 | 02 | 02 | 03 | 03 | [7 empty] | Block 3 Project Plan (5.5) | 1.02.02.03.03 | 2.5.5 | 22046 | S | 51 days |  | 0
1 | 02 | 02 | 03 | 03 | 01 | [6 empty] | Develop Building Block Project Plan (5.5) | 1.02.02.03.03.01 |  | 11244 | T | 30 days | 240 | 127.4272 | [9 empty] | 80.8252 | 0 |  |  |  |  | 46.6019
1 | 02 | 02 | 03 | 03 | 02 | [6 empty] | Deliver Building Block Project Plan to COR (5.5) | 1.02.02.03.03.02 |  | 11245 | T | 1 day | 8 | 4.2476 | [9 empty] | 2.6942 | 0 |  |  |  |  | 1.5534
1 | 02 | 02 | 03 | 03 | 03 | [6 empty] | COR Reviews Block 3 Project Plan (5.5) | 1.02.02.03.03.03 |  | 11246 | T | 10 days | 80 | 42.4757 | [9 empty] | 26.9417 | 0 |  |  |  |  | 15.534
1 | 02 | 02 | 03 | 03 | 04 | [6 empty] | NCCoE revises Block 3 Project Plan based on review by COR (5.5) | 1.02.02.03.03.04 |  | 11247 | T | 10 days | 80 | 42.4757 | [9 empty] | 26.9417 | 0 |  |  |  |  | 15.534
1 | 02 | 02 | 03 | 03 | 05 | [6 empty] | COR Declines the Block 3 Building Block Project Plan (IMP) | 1.02.02.03.03.05 |  | 11248 | M | 0 days | 0 | 0
1 | 02 | 02 | 03 | 04 | [7 empty] | Block-4 Project Plan (5.5) | 1.02.02.03.04 | 2.5.5 | 22047 | S | 51 days |  | 0
1 | 02 | 02 | 03 | 04 | 01 | [6 empty] | Develop Building Block Project Plan (5.5) | 1.02.02.03.04.01 |  | 11260 | T | 30 days | 240 | 127.4272 | [9 empty] | 80.8252 | 0 |  |  |  |  | 46.6019
1 | 02 | 02 | 03 | 04 | 02 | [6 empty] | Deliver Building Block Project Plan to COR (5.5) | 1.02.02.03.04.02 |  | 11261 | T | 1 day | 8 | 4.2476 | [9 empty] | 2.6942 | 0 |  |  |  |  | 1.5534
1 | 02 | 02 | 03 | 04 | 03 | [6 empty] | COR Reviews Block 4 Project Plan (5.5) | 1.02.02.03.04.03 |  | 11262 | T | 10 days | 80 | 42.4757 | [9 empty] | 26.9417 | 0 |  |  |  |  | 15.534
1 | 02 | 02 | 03 | 04 | 04 | [6 empty] | NCCoE revises Block 4 Project Plan based on review by COR (5.5) | 1.02.02.03.04.04 |  | 11263 | T | 10 days | 80 | 42.4757 | [9 empty] | 26.9417 | 0 |  |  |  |  | 15.534
1 | 02 | 02 | 03 | 04 | 05 | [6 empty] | COR Declines the Block 4 Building Block Project Plan (IMP) | 1.02.02.03.04.05 |  | 11264 | M | 0 days | 0 | 0
| 02 | 02 | 03 | [8 empty] | Total Hours | 1.02.02.03 |  |  | A |  | 1648 | 1538.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555 | 0 | 0 | 0 | 663.66 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 02 | 03 | [9 empty] | Phase 3 | 1.02.03 |  | 6943 | C | 292 days |  | 15241.9605
1 | 02 | 03 | 01 | [8 empty] | Develop Draft Building Block Team Development Work Plan (5.6) | 1.02.03.01 |  | 22048 | W | 144 days |  | 2902 |  |  | 347 | [7 empty] | 1388 |  |  |  |  | 540 | [30 empty] | 280 | 347
1 | 02 | 03 | 01 | 01 | [7 empty] | Building Block 1 Draft Team Development Work Plan | 1.02.03.01.01 |  | 22051 | T | 6 wks | 240 | 1451 |  |  | 173.5 | [7 empty] | 694 |  |  |  |  | 270 | [30 empty] | 140 | 173.5
1 | 02 | 03 | 01 | 02 | [7 empty] | Building Block 2 Draft Team Development Work Plan | 1.02.03.01.02 |  | 22052 | T | 6 wks | 240 | 1451 |  |  | 173.5 | [7 empty] | 694 |  |  |  |  | 270 | [30 empty] | 140 | 173.5
| 02 | 03 | 01 | [8 empty] | Total Hours | 1.02.03.01 |  |  | A |  | 480 | 2902 | 0 | 0 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1388 | 0 | 0 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 02 | 03 | 02 | [8 empty] | Conduct a Monthly Bilding Block Team Development Conference in conjunction with the Monthly Planning Conference (5.7) | 1.02.03.02 |  | 22054 | W | 165 days |  | 1013.91 |  |  | 347 | [12 empty] | 177 | [30 empty] | 143 | 346.91
1 | 02 | 03 | 02 | 01 | [7 empty] | Block-1 Execute a Monthly Building Block Team Development Conference Agenda (5.7) | 1.02.03.02.01 | 2.5.6 | 11119 | S | 81 days |  | 0 |  |  | 0 | [12 empty] | 0 | [31 empty] | 0
1 | 02 | 03 | 02 | 01 | 01 | [6 empty] | Develop Draft Building Block Team Development Work Plan (5.6) for Block 1 | 1.02.03.02.01.01 | 2.5.7 | 22056 | T | 6 wks | 240 | 460.8682 |  |  | 157.7273 | [12 empty] | 80.4545 | [30 empty] | 65 | 157.6864
1 | 02 | 03 | 02 | 01 | 02 | [6 empty] | Execute a Monthly Building Block 1 Team Development Conference Agenda (5.7) | 1.02.03.02.01.02 |  | 6866 | S | 8 days |  | 0 |  |  | 0 | [12 empty] | 0 | [31 empty] | 0
1 | 02 | 03 | 02 | 01 | 02 | 01 | [5 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR - Block-1 | 1.02.03.02.01.02.01 |  | 11123 | T | 1 day | 8 | 15.3623 |  |  | 5.2576 | [12 empty] | 2.6818 | [30 empty] | 2.1667 | 5.2562
1 | 02 | 03 | 02 | 01 | 02 | 02 | [5 empty] | Conviene the Initial Building Block Team Development Conference for Block 1 | 1.02.03.02.01.02.02 |  | 11122 | T | 1 day | 8 | 15.3623 |  |  | 5.2576 | [12 empty] | 2.6818 | [30 empty] | 2.1667 | 5.2562
1 | 02 | 03 | 02 | 01 | 02 | 03 | [5 empty] | Develop and Deliver the Buildng Block Team Development Conference Minutes Block-1 | 1.02.03.02.01.02.03 |  | 11124 | T | 1 day | 8 | 15.3623 |  |  | 5.2576 | [12 empty] | 2.6818 | [30 empty] | 2.1667 | 5.2562
1 | 02 | 03 | 02 | 02 | [7 empty] | Block -2 Execute a Monthly Building Block Team Development Conference Agenda (5.7) | 1.02.03.02.02 | 2.5.6 | 11200 | S | 51 days |  | 0 |  |  | 0 | [12 empty] | 0 | [31 empty] | 0
1 | 02 | 03 | 02 | 02 | 01 | [6 empty] | Develop Draft Building Block Team Development Work Plan (5.6) for Block 2 | 1.02.03.02.02.01 | 2.5.7 | 11225 | T | 6 wks | 240 | 460.8682 |  |  | 157.7273 | [12 empty] | 80.4545 | [30 empty] | 65 | 157.6864
1 | 02 | 03 | 02 | 02 | 02 | [6 empty] | Execute a Monthly Building Block 2 Team Development Conference Agenda (5.7) (Initial month) | 1.02.03.02.02.02 |  | 11201 | S | 8 days |  | 0 |  |  | 0 | [12 empty] | 0 | [31 empty] | 0
1 | 02 | 03 | 02 | 02 | 02 | 01 | [5 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Block-2 | 1.02.03.02.02.02.01 |  | 11202 | T | 1 day | 8 | 15.3623 |  |  | 5.2576 | [12 empty] | 2.6818 | [30 empty] | 2.1667 | 5.2562
1 | 02 | 03 | 02 | 02 | 02 | 02 | [5 empty] | Conviene the Initial Building Block Team Development Conference for Block 2 | 1.02.03.02.02.02.02 |  | 11203 | T | 1 day | 8 | 15.3623 |  |  | 5.2576 | [12 empty] | 2.6818 | [30 empty] | 2.1667 | 5.2562
1 | 02 | 03 | 02 | 02 | 02 | 03 | [5 empty] | Develop and Deliver the Building Block Team Development Conference Minutes Block-2 | 1.02.03.02.02.02.03 |  | 11204 | T | 1 day | 8 | 15.3623 |  |  | 5.2576 | [12 empty] | 2.6818 | [30 empty] | 2.1667 | 5.2562
| 02 | 03 | 02 | [8 empty] | Total Hours | 1.02.03.02 |  |  | A |  | 528 | 1013.91 | 0 | 0 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 346.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 02 | 03 | 03 | [8 empty] | Facilitate the development of Agreements between cybersecurity technology and the NCCoE (5.8) | 1.02.03.03 | 2.5.8 | 22049 | W | 90 days |  | 1855.9205 |  |  | 346.91 | [12 empty] | 404.2105 | [30 empty] | 757.89 | 346.91
1 | 02 | 03 | 03 | 01 | [7 empty] | Facilitate the development of Agreements between cybersecurity technology and the NCCoE (5.8) Block 1 | 1.02.03.03.01 |  | 6865 | T | 5 days | 40 | 441.8858 |  |  | 82.5976 | [12 empty] | 96.2406 | [30 empty] | 180.45 | 82.5976
1 | 02 | 03 | 03 | 02 | [7 empty] | Deliver Agreements to COR Block-1 | 1.02.03.03.02 | 2.5.8 | 22207 | T | 1 day | 8 | 88.3772 |  |  | 16.5195 | [12 empty] | 19.2481 | [30 empty] | 36.09 | 16.5195
1 | 02 | 03 | 03 | 03 | [7 empty] | Facilitate the development of Agreements between cybersecurity technology and the NCCoE (5.8) Block 2 | 1.02.03.03.03 |  | 11205 | T | 5 days | 40 | 441.8858 |  |  | 82.5976 | [12 empty] | 96.2406 | [30 empty] | 180.45 | 82.5976
1 | 02 | 03 | 03 | 04 | [7 empty] | Deliver Agreements to COR Block-2 | 1.02.03.03.04 |  | 22209 | T | 1 day | 80 | 883.7717 |  |  | 165.1952 | [12 empty] | 192.4812 | [30 empty] | 360.9 | 165.1952
| 02 | 03 | 03 | [8 empty] | Total Hours | 1.02.03.03 |  |  | A |  | 168 | 1855.9205 | 0 | 0 | 346.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404.2105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757.89 | 346.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 02 | 03 | 04 | [8 empty] | Develop and Deliver to the COR the Roster of Building Block Development and Demonstration Collaborators (5.9) | 1.02.03.04 | 2.5.9 | 22050 | W | 85 days |  | 785.63 |  |  | 346.91 | [12 empty] | 67.37 | [30 empty] | 16.84 | 346.91 | [19 empty] | 7.6
1 | 02 | 03 | 04 | 01 | [7 empty] | Develop and Deliver to the COR the Roster of Building Block Development and Demonstration Collaborators (5.9) Block 1 | 1.02.03.04.01 | 2.5.9 | 6863 | T | 1 day | 8 | 392.815 |  |  | 173.455 | [12 empty] | 33.685 | [30 empty] | 8.42 | 173.455 | [19 empty] | 3.8
1 | 02 | 03 | 04 | 02 | [7 empty] | Develop and Deliver to the COR the Roster of Building Block Development and Demonstration Collaborators (5.9) Block 2 | 1.02.03.04.02 | 2.5.10 | 11206 | T | 1 day | 8 | 392.815 |  |  | 173.455 | [12 empty] | 33.685 | [30 empty] | 8.42 | 173.455 | [19 empty] | 3.8
| 02 | 03 | 04 | [8 empty] | Total Hours | 1.02.03.04 |  |  | A |  | 16 | 785.63 | 0 | 0 | 346.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.84 | 346.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 02 | 03 | 05 | [8 empty] | Initiate Building Block Project Development (5.10) | 1.02.03.05 |  | 6869 | W | 144 days |  | 7575.5 | [9 empty] | 448 | 0 |  | 832 | 0 | [5 empty] | 480 | 3167.5 |  |  | 2192 | [43 empty] | 456
1 | 02 | 03 | 05 | 01 | [7 empty] | Initiate Building Block 1 Project (IMP) | 1.02.03.05.01 |  | 11127 | M | 0 days | 0 | 0
1 | 02 | 03 | 05 | 02 | [7 empty] | Complete the Building Block 1 Project Plan | 1.02.03.05.02 | 2.5.10.1 | 11128 | T | 3 wks | 120 | 946.9375 | [9 empty] | 56 | 0 |  | 104 | 0 | [5 empty] | 60 | 395.9375 |  |  | 274 | [43 empty] | 57
1 | 02 | 03 | 05 | 03 | [7 empty] | Develop and Deliver a Building Block 1 Development Report and Demonstration Script (5.10.1) | 1.02.03.05.03 |  | 6868 | T | 30 days | 240 | 1893.875 | [9 empty] | 112 | 0 |  | 208 | 0 | [5 empty] | 120 | 791.875 |  |  | 548 | [43 empty] | 114
1 | 02 | 03 | 05 | 04 | [7 empty] | COR review of Building Block 1 Development Report and Demonstration Script | 1.02.03.05.04 |  | 11129 | T | 5 days | 40 | 315.6458 | [9 empty] | 18.6667 | 0 |  | 34.6667 | 0 | [5 empty] | 20 | 131.9792 |  |  | 91.3333 | [43 empty] | 19
1 | 02 | 03 | 05 | 05 | [7 empty] | NCCoE review of changes from COR for Block 1 Final Acceptance | 1.02.03.05.05 |  | 11130 | T | 10 days | 80 | 631.2917 | [9 empty] | 37.3333 | 0 |  | 69.3333 | 0 | [5 empty] | 40 | 263.9583 |  |  | 182.6667 | [43 empty] | 38
1 | 02 | 03 | 05 | 06 | [7 empty] | COR Acceptance of Building Block 1 Development Report and Demonstration Script | 1.02.03.05.06 |  | 11131 | M | 0 days | 0 | 0
1 | 02 | 03 | 05 | 07 | [7 empty] | Initiate Building Block 2 Project (IMP) | 1.02.03.05.07 |  | 11197 | M | 0 days | 0 | 0
1 | 02 | 03 | 05 | 08 | [7 empty] | Complete the Building Block 2 Project Plan | 1.02.03.05.08 | 2.5.10.1 | 11141 | T | 3 wks | 120 | 946.9375 | [9 empty] | 56 | 0 |  | 104 | 0 | [5 empty] | 60 | 395.9375 |  |  | 274 | [43 empty] | 57
1 | 02 | 03 | 05 | 09 | [7 empty] | Develop and Deliver a Building Block 2 Development Report and Demonstration Script (5.10.1) | 1.02.03.05.09 |  | 11142 | T | 30 days | 240 | 1893.875 | [9 empty] | 112 | 0 |  | 208 | 0 | [5 empty] | 120 | 791.875 |  |  | 548 | [43 empty] | 114
1 | 02 | 03 | 05 | 10 | [7 empty] | COR review of Building Block 2 Development Report and Demonstration Script | 1.02.03.05.10 |  | 11143 | T | 5 days | 40 | 315.6458 | [9 empty] | 18.6667 | 0 |  | 34.6667 | 0 | [5 empty] | 20 | 131.9792 |  |  | 91.3333 | [43 empty] | 19
1 | 02 | 03 | 05 | 11 | [7 empty] | NCCoE review of changes from COR for Block 2 Final Acceptance | 1.02.03.05.11 |  | 11144 | T | 10 days | 80 | 631.2917 | [9 empty] | 37.3333 | 0 |  | 69.3333 | 0 | [5 empty] | 40 | 263.9583 |  |  | 182.6667 | [43 empty] | 38
1 | 02 | 03 | 05 | 12 | [7 empty] | COR Acceptance of Building Block 2 Development Report and Demonstration Script | 1.02.03.05.12 |  | 11145 | M | 0 days | 0 | 0
| 02 | 03 | 05 | [8 empty] | Total Hours | 1.02.03.05 |  |  | A |  | 960 | 7575.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 0 | 0 | 832 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 3167.5 | 0 | 0 | 2192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 02 | 03 | 06 | [8 empty] | Demonstration Schedule (5.11) | 1.02.03.06 | 2.5.11 | 11126 | W | 134 days |  | 688 | [8 empty] | 0 | 144 |  |  |  | 0 |  | 240 |  |  |  | 80 | 0 |  |  | 224
1 | 02 | 03 | 06 | 01 | [7 empty] | Develop and Deliver Building Block 1 Demonstration Schedule (in Conference Agenda Format) (5.11) | 1.02.03.06.01 |  | 6867 | T | 10 days | 80 | 215 | [8 empty] | 0 | 45 |  |  |  | 0 |  | 75 |  |  |  | 25 | 0 |  |  | 70
1 | 02 | 03 | 06 | 02 | [7 empty] | Conviene the Demonstrations for Block 1 | 1.02.03.06.02 |  | 11132 | T | 5 days | 40 | 107.5 | [8 empty] | 0 | 22.5 |  |  |  | 0 |  | 37.5 |  |  |  | 12.5 | 0 |  |  | 35
1 | 02 | 03 | 06 | 03 | [7 empty] | Develop and Deliver the Building Block 1 Demonstration Minutes (5.11) | 1.02.03.06.03 | 2.5.11 | 11133 | T | 1 day | 8 | 21.5 | [8 empty] | 0 | 4.5 |  |  |  | 0 |  | 7.5 |  |  |  | 2.5 | 0 |  |  | 7
1 | 02 | 03 | 06 | 04 | [7 empty] | Develop and Deliver Building Block 2 Demonstration Schedule (in Conference Agenda Format) (5.11) | 1.02.03.06.04 |  | 11146 | T | 10 days | 80 | 215 | [8 empty] | 0 | 45 |  |  |  | 0 |  | 75 |  |  |  | 25 | 0 |  |  | 70
1 | 02 | 03 | 06 | 05 | [7 empty] | Conviene the Demonstrations for Block 2 | 1.02.03.06.05 |  | 11147 | T | 5 days | 40 | 107.5 | [8 empty] | 0 | 22.5 |  |  |  | 0 |  | 37.5 |  |  |  | 12.5 | 0 |  |  | 35
1 | 02 | 03 | 06 | 06 | [7 empty] | Develop and Deliver the Building Block 2 Demonstration Minutes (5.11) | 1.02.03.06.06 |  | 11148 | T | 1 day | 8 | 21.5 | [8 empty] | 0 | 4.5 |  |  |  | 0 |  | 7.5 |  |  |  | 2.5 | 0 |  |  | 7
| 02 | 03 | 06 | [8 empty] | Total Hours | 1.02.03.06 |  |  | A |  | 256 | 688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 02 | 03 | 07 | [8 empty] | Documentation Report (5.12) | 1.02.03.07 | 2.5.12 | 22053 | W | 174 days |  | 379 | [9 empty] | 125 | 0 | [8 empty] | 124 | 0 | [46 empty] | 130
1 | 02 | 03 | 07 | 01 | [7 empty] | Deliver the Draft Building Block 1 Documentation Report (5.12) | 1.02.03.07.01 |  | 6870 | T | 40 days | 320 | 101.0667 | [9 empty] | 33.3333 | 0 | [8 empty] | 33.0667 | 0 | [46 empty] | 34.6667
1 | 02 | 03 | 07 | 02 | [7 empty] | COR Review of Draft Building Block 1 Documentation Report | 1.02.03.07.02 |  | 11136 | T | 15 days | 120 | 37.9 | [9 empty] | 12.5 | 0 | [8 empty] | 12.4 | 0 | [46 empty] | 13
1 | 02 | 03 | 07 | 03 | [7 empty] | NCCoE response to changes to the Building Block 1 Documentation Report by the COR | 1.02.03.07.03 |  | 11135 | T | 20 days | 160 | 50.5333 | [9 empty] | 16.6667 | 0 | [8 empty] | 16.5333 | 0 | [46 empty] | 17.3333
1 | 02 | 03 | 07 | 04 | [7 empty] | COR Acceptance of the Building Block 1 Documentation Report (IMP) | 1.02.03.07.04 | 2.5.12 | 11134 | M | 0 days | 0 | 0 | [10 empty] | 0 | [9 empty] | 0 | [46 empty] | 0
1 | 02 | 03 | 07 | 05 | [7 empty] | Deliver the Draft Building Block 2 Documentation Report (5.12) | 1.02.03.07.05 |  | 11149 | T | 40 days | 320 | 101.0667 | [9 empty] | 33.3333 | 0 | [8 empty] | 33.0667 | 0 | [46 empty] | 34.6667
1 | 02 | 03 | 07 | 06 | [7 empty] | COR Review of Draft Building Block 2 Documentation Report | 1.02.03.07.06 |  | 11150 | T | 15 days | 120 | 37.9 | [9 empty] | 12.5 | 0 | [8 empty] | 12.4 | 0 | [46 empty] | 13
1 | 02 | 03 | 07 | 07 | [7 empty] | NCCoE response to changes to the Building Block 2 Documentation Report by the COR | 1.02.03.07.07 |  | 11151 | T | 20 days | 160 | 50.5333 | [9 empty] | 16.6667 | 0 | [8 empty] | 16.5333 | 0 | [46 empty] | 17.3333
1 | 02 | 03 | 07 | 08 | [7 empty] | COR Acceptance of the Building Block 2 Documentation Report (IMP) | 1.02.03.07.08 | 2.5.12 | 11152 | M | 0 days | 0 | 0 | [10 empty] | 0 | [9 empty] | 0 | [46 empty] | 0
| 02 | 03 | 07 | [8 empty] | Total Hours | 1.02.03.07 |  |  | A |  | 1200 | 379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 02 | 04 | [9 empty] | Project Planning and Reporting (6.0) | 1.02.04 | 2.6 | 6812 | W | 15 days |  | 42 | [10 empty] | 14 |  |  | 8 | [6 empty] | 8 | [26 empty] | 8 | [19 empty] | 4.5
1 | 02 | 04 | 01 | [8 empty] | Attend Kickoff Meeting (6.1) | 1.02.04.01 | 2.6.1 | 6871 | T | 1 day | 8 | 32 | [10 empty] | 8 |  |  | 8 | [6 empty] | 8 | [26 empty] | 8
1 | 02 | 04 | 02 | [8 empty] | Develop and Maintain a Project Workplan (6.2) | 1.02.04.02 | 2.6.2 | 6872 | T | 15 days | 120 | 10.25 | 0.25 | [9 empty] | 5.5 | [56 empty] | 4.5
| 02 | 04 | 02 | [8 empty] | Total Hours | 1.02.04 |  |  | A |  |  | 42.25 | 0.25 | 0 | 0 | [5 empty] | 0 |  | 13.5 |  |  | 8 | 0 | 0 |  |  |  |  | 8 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 8 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 4.5 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 02 | 05 | [9 empty] | Deliverables (7.0) | 1.02.05 | 2.7.1 | 6877 | W | 514 days |  | 0
1 | 02 | 05 | 01 | [8 empty] | Attend Kickoff Meeting at NIST (7.1) | 1.02.05.01 | 2.7.2 | 6878 | M | 0 days |  | 0
1 | 02 | 05 | 02 | [8 empty] | Project Work Plan (7.2) | 1.02.05.02 | 2.7.3 | 6879 | M | 0 days |  | 0
1 | 02 | 05 | 03 | [8 empty] | Monthly Planning Conference Agenda (7.3) | 1.02.05.03 |  | 6880 | S | 501 days |  | 0
1 | 02 | 05 | 03 | 01 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Oct 2014 | 1.02.05.03.01 |  | 22060 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 02 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Nov 2014 | 1.02.05.03.02 |  | 22061 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 03 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Dec 2014 | 1.02.05.03.03 |  | 22062 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 04 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jan 2015 | 1.02.05.03.04 |  | 22063 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 05 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Feb 2015 | 1.02.05.03.05 |  | 22064 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 06 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Mar 2015 | 1.02.05.03.06 |  | 22065 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 07 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Apr 2015 | 1.02.05.03.07 |  | 22066 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 08 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for May 2015 | 1.02.05.03.08 |  | 22067 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 09 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jun 2015 | 1.02.05.03.09 |  | 22068 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 10 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jul 2015 | 1.02.05.03.10 |  | 22069 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 11 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Aug 2015 | 1.02.05.03.11 |  | 22070 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 12 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Sep 2015 | 1.02.05.03.12 |  | 22071 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 13 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Oct 2015 | 1.02.05.03.13 |  | 22072 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 14 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Nov 2015 | 1.02.05.03.14 |  | 22085 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 15 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Dec 2015 | 1.02.05.03.15 |  | 22086 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 16 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jan 2016 | 1.02.05.03.16 |  | 22087 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 17 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Feb 2016 | 1.02.05.03.17 |  | 22088 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 18 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Mar 2016 | 1.02.05.03.18 |  | 22089 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 19 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Apr 2016 | 1.02.05.03.19 |  | 22090 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 20 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for May 2016 | 1.02.05.03.20 |  | 22091 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 21 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jun 2016 | 1.02.05.03.21 |  | 22092 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 22 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Jul 2016 | 1.02.05.03.22 |  | 22093 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 23 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Aug 2016 | 1.02.05.03.23 |  | 22094 | M | 0 days |  | 0
1 | 02 | 05 | 03 | 24 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Agenda for Sep 2016 | 1.02.05.03.24 | 2.7.4 | 22095 | M | 0 days |  | 0
1 | 02 | 05 | 04 | [8 empty] | Monthly Planning Conference Minutes (7.4) | 1.02.05.04 |  | 6881 | S | 503 days |  | 0
1 | 02 | 05 | 04 | 01 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Oct 2014 | 1.02.05.04.01 |  | 22108 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 02 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Nov 2014 | 1.02.05.04.02 |  | 22109 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 03 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Dec 2014 | 1.02.05.04.03 |  | 22110 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 04 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jan 2015 | 1.02.05.04.04 |  | 22111 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 05 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Feb 2015 | 1.02.05.04.05 |  | 22112 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 06 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Mar 2015 | 1.02.05.04.06 |  | 22113 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 07 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Apr 2015 | 1.02.05.04.07 |  | 22114 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 08 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes May 2015 | 1.02.05.04.08 |  | 22115 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 09 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jun 2015 | 1.02.05.04.09 |  | 22116 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 10 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jul 2015 | 1.02.05.04.10 |  | 22118 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 11 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Aug 2015 | 1.02.05.04.11 |  | 22119 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 12 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Sep 2015 | 1.02.05.04.12 |  | 22120 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 13 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Oct 2015 | 1.02.05.04.13 |  | 22121 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 14 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Nov 2015 | 1.02.05.04.14 |  | 22134 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 15 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Dec 2015 | 1.02.05.04.15 |  | 22135 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 16 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jan 2016 | 1.02.05.04.16 |  | 22136 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 17 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Feb 2016 | 1.02.05.04.17 |  | 22137 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 18 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Mar 2016 | 1.02.05.04.18 |  | 22138 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 19 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Apr 2016 | 1.02.05.04.19 |  | 22139 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 20 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes May 2016 | 1.02.05.04.20 |  | 22140 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 21 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jun 2016 | 1.02.05.04.21 |  | 22141 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 22 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jul 2016 | 1.02.05.04.22 |  | 22142 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 23 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Aug 2016 | 1.02.05.04.23 |  | 22144 | M | 0 days |  | 0
1 | 02 | 05 | 04 | 24 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Sep 2016 | 1.02.05.04.24 | 2.7.5 | 22145 | M | 0 days |  | 0
1 | 02 | 05 | 05 | [8 empty] | Building Block Planning Meeting Minutes (7.5) | 1.02.05.05 |  | 6882 | S | 503 days |  | 0
1 | 02 | 05 | 05 | 01 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Oct 2014 | 1.02.05.05.01 |  | 23276 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 02 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Nov 2014 | 1.02.05.05.02 |  | 23275 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 03 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Dec 2014 | 1.02.05.05.03 |  | 23277 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 04 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jan 2015 | 1.02.05.05.04 |  | 23274 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 05 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Feb 2015 | 1.02.05.05.05 |  | 23273 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 06 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Mar 2015 | 1.02.05.05.06 |  | 23278 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 07 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Apr 2015 | 1.02.05.05.07 |  | 23279 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 08 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes May 2015 | 1.02.05.05.08 |  | 23280 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 09 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jun 2015 | 1.02.05.05.09 |  | 23281 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 10 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jul 2015 | 1.02.05.05.10 |  | 23282 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 11 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Aug 2015 | 1.02.05.05.11 |  | 23283 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 12 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Sep 2015 | 1.02.05.05.12 |  | 23284 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 13 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Oct 2015 | 1.02.05.05.13 |  | 23285 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 14 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Nov 2015 | 1.02.05.05.14 |  | 23286 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 15 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Dec 2015 | 1.02.05.05.15 |  | 23287 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 16 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jan 2016 | 1.02.05.05.16 |  | 23288 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 17 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Feb 2016 | 1.02.05.05.17 |  | 23289 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 18 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Mar 2016 | 1.02.05.05.18 |  | 23290 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 19 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Apr 2016 | 1.02.05.05.19 |  | 23291 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 20 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes May 2016 | 1.02.05.05.20 |  | 23292 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 21 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jun 2016 | 1.02.05.05.21 |  | 23293 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 22 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Jul 2016 | 1.02.05.05.22 |  | 23294 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 23 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Aug 2016 | 1.02.05.05.23 |  | 23295 | M | 0 days |  | 0
1 | 02 | 05 | 05 | 24 | [7 empty] | Produce and Deliver Monthly Building Block Planning and Management Conference Minutes Sep 2016 | 1.02.05.05.24 | 2.7.6 | 23296 | M | 0 days |  | 0
1 | 02 | 05 | 06 | [8 empty] | Draft Building Block Description (7.6) | 1.02.05.06 |  | 6883 | S | 317 days |  | 0
1 | 02 | 05 | 06 | 01 | [7 empty] | Draft Building Block Description Block 1 (5.3) | 1.02.05.06.01 |  | 22150 | M | 0 days |  | 0
1 | 02 | 05 | 06 | 02 | [7 empty] | Draft Building Block Description Block 2 (5.3) | 1.02.05.06.02 |  | 22149 | M | 0 days |  | 0
1 | 02 | 05 | 06 | 03 | [7 empty] | Draft Building Block Description Block 3 (5.3) | 1.02.05.06.03 |  | 22148 | M | 0 days |  | 0
1 | 02 | 05 | 06 | 04 | [7 empty] | Draft Building Block Description Block 4 (5.3) | 1.02.05.06.04 |  | 22147 | M | 0 days |  | 0
1 | 02 | 05 | 06 | 05 | [7 empty] | Draft Building Block Description Block 5 (5.3) | 1.02.05.06.05 | 2.7.7 | 22146 | M | 0 days |  | 0
1 | 02 | 05 | 07 | [8 empty] | Draft Building Block Description Publication for Public Comment (7.7) | 1.02.05.07 |  | 6884 | S | 294 days |  | 0
1 | 02 | 05 | 07 | 01 | [7 empty] | Draft Building Block Description Publication for Public Comment (7.7) Block-1 | 1.02.05.07.01 |  | 22152 | M | 0 days |  | 0
1 | 02 | 05 | 07 | 02 | [7 empty] | Draft Building Block Description Publication for Public Comment (7.7) Block-2 | 1.02.05.07.02 |  | 22153 | M | 0 days |  | 0
1 | 02 | 05 | 07 | 03 | [7 empty] | Draft Building Block Description Publication for Public Comment (7.7) Block-3 | 1.02.05.07.03 |  | 22176 | M | 0 days |  | 0
1 | 02 | 05 | 07 | 04 | [7 empty] | Draft Building Block Description Publication for Public Comment (7.7) Block-4 | 1.02.05.07.04 | 2.7.8 | 22177 | M | 0 days |  | 0
1 | 02 | 05 | 08 | [8 empty] | Comment resolution Conference Agenda (7.8) | 1.02.05.08 |  | 6885 | S | 221 days |  | 0
1 | 02 | 05 | 08 | 01 | [7 empty] | Comment resolution Conference Agenda (7.8) Block-1 | 1.02.05.08.01 |  | 22157 | M | 0 days |  | 0
1 | 02 | 05 | 08 | 02 | [7 empty] | Comment resolution Conference Agenda (7.8) Block-2 | 1.02.05.08.02 |  | 22156 | M | 0 days |  | 0
1 | 02 | 05 | 08 | 03 | [7 empty] | Comment resolution Conference Agenda (7.8) Block-3 | 1.02.05.08.03 |  | 22179 | M | 0 days |  | 0
1 | 02 | 05 | 08 | 04 | [7 empty] | Comment resolution Conference Agenda (7.8) Block-4 | 1.02.05.08.04 | 2.7.9 | 22178 | M | 0 days |  | 0
1 | 02 | 05 | 09 | [8 empty] | Comment resolution Conference Minutes (7.9) | 1.02.05.09 |  | 6886 | S | 294 days |  | 0
1 | 02 | 05 | 09 | 01 | [7 empty] | Comment resolution Conference Minutes (7.9) Block-1 | 1.02.05.09.01 |  | 22159 | M | 0 days |  | 0
1 | 02 | 05 | 09 | 02 | [7 empty] | Comment resolution Conference Minutes (7.9) Block-2 | 1.02.05.09.02 |  | 22158 | M | 0 days |  | 0
1 | 02 | 05 | 09 | 03 | [7 empty] | Comment resolution Conference Minutes (7.9) Block-3 | 1.02.05.09.03 |  | 22182 | M | 0 days |  | 0
1 | 02 | 05 | 09 | 04 | [7 empty] | Comment resolution Conference Minutes (7.9) Block-4 | 1.02.05.09.04 | 2.7.10 | 22183 | M | 0 days |  | 0
1 | 02 | 05 | 10 | [8 empty] | Final Building Block Description (7.10) | 1.02.05.10 |  | 6887 | S | 294 days |  | 0
1 | 02 | 05 | 10 | 01 | [7 empty] | Final Building Block Description (7.10) Block-1 | 1.02.05.10.01 |  | 22161 | M | 0 days |  | 0
1 | 02 | 05 | 10 | 02 | [7 empty] | Final Building Block Description (7.10) Block-2 | 1.02.05.10.02 |  | 22186 | M | 0 days |  | 0
1 | 02 | 05 | 10 | 03 | [7 empty] | Final Building Block Description (7.10) Block-3 | 1.02.05.10.03 |  | 22187 | M | 0 days |  | 0
1 | 02 | 05 | 10 | 04 | [7 empty] | Final Building Block Description (7.10) Block-4 | 1.02.05.10.04 | 2.7.11 | 22188 | M | 0 days |  | 0
1 | 02 | 05 | 11 | [8 empty] | Building Block Project Plan (7.11) | 1.02.05.11 |  | 6888 | S | 294 days |  | 0
1 | 02 | 05 | 11 | 01 | [7 empty] | Building Block Project Plan (7.11) Block-1 | 1.02.05.11.01 |  | 22163 | M | 0 days |  | 0
1 | 02 | 05 | 11 | 02 | [7 empty] | Building Block Project Plan (7.11) Block-2 | 1.02.05.11.02 |  | 22191 | M | 0 days |  | 0
1 | 02 | 05 | 11 | 03 | [7 empty] | Building Block Project Plan (7.11) Block-3 | 1.02.05.11.03 |  | 22192 | M | 0 days |  | 0
1 | 02 | 05 | 11 | 04 | [7 empty] | Building Block Project Plan (7.11) Block-4 | 1.02.05.11.04 | 2.7.12 | 22193 | M | 0 days |  | 0
1 | 02 | 05 | 12 | [8 empty] | Building Block Team Development Work Plan (7.12) | 1.02.05.12 |  | 6889 | S | 114 days |  | 0
1 | 02 | 05 | 12 | 01 | [7 empty] | Building Block Team Development Work Plan (7.12) Block-1 | 1.02.05.12.01 |  | 22165 | M | 0 days |  | 0
1 | 02 | 05 | 12 | 02 | [7 empty] | Building Block Team Development Work Plan (7.12) Block-2 | 1.02.05.12.02 | 2.7.13 | 22194 | M | 0 days |  | 0
1 | 02 | 05 | 13 | [8 empty] | Monthly Building Block Team Development Conference Agenda (7.13) | 1.02.05.13 |  | 6890 | S | 372 days |  | 0
1 | 02 | 05 | 13 | 01 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR - Apr-2015 | 1.02.05.13.01 |  | 23306 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 02 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR May-2015 | 1.02.05.13.02 |  | 23307 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 03 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Jun-2015 | 1.02.05.13.03 |  | 23305 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 04 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Jul-2015 | 1.02.05.13.04 |  | 23308 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 05 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Aug-2015 | 1.02.05.13.05 |  | 23309 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 06 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Sep-2015 | 1.02.05.13.06 |  | 23311 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 07 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Oct-2015 | 1.02.05.13.07 |  | 23310 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 08 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Nov-2015 | 1.02.05.13.08 |  | 23312 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 09 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Dec-2015 | 1.02.05.13.09 |  | 23313 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 10 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Jan-2016 | 1.02.05.13.10 |  | 23314 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 11 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Feb-2016 | 1.02.05.13.11 |  | 23315 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 12 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Mar-2016 | 1.02.05.13.12 |  | 23316 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 13 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Apr-2016 | 1.02.05.13.13 |  | 23317 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 14 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR May-2016 | 1.02.05.13.14 |  | 23318 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 15 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Jun-2016 | 1.02.05.13.15 |  | 23319 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 16 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Jul-2016 | 1.02.05.13.16 |  | 23320 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 17 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Aug-2016 | 1.02.05.13.17 |  | 23321 | M | 0 days |  | 0
1 | 02 | 05 | 13 | 18 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Agenda to COR Sep-2016 | 1.02.05.13.18 | 2.7.13 | 23322 | M | 0 days |  | 0
1 | 02 | 05 | 14 | [8 empty] | Monthly Building Block Team Development Conference Minutes (7.14) | 1.02.05.14 |  | 23325 | S | 372 days |  | 0
1 | 02 | 05 | 14 | 01 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR - Apr-2015 | 1.02.05.14.01 |  | 23326 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 02 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR May-2015 | 1.02.05.14.02 |  | 23327 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 03 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Jun-2015 | 1.02.05.14.03 |  | 23328 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 04 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Jul-2015 | 1.02.05.14.04 |  | 23329 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 05 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Aug-2015 | 1.02.05.14.05 |  | 23330 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 06 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Sep-2015 | 1.02.05.14.06 |  | 23331 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 07 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Oct-2015 | 1.02.05.14.07 |  | 23332 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 08 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Nov-2015 | 1.02.05.14.08 |  | 23333 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 09 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Dec-2015 | 1.02.05.14.09 |  | 23334 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 10 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Jan-2016 | 1.02.05.14.10 |  | 23335 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 11 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Feb-2016 | 1.02.05.14.11 |  | 23336 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 12 | [7 empty] | Develope and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Mar-2016 | 1.02.05.14.12 |  | 23337 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 13 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Apr-2016 | 1.02.05.14.13 |  | 23338 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 14 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR May-2016 | 1.02.05.14.14 |  | 23339 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 15 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Jun-2016 | 1.02.05.14.15 |  | 23340 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 16 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Jul-2016 | 1.02.05.14.16 |  | 23341 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 17 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Aug-2016 | 1.02.05.14.17 |  | 23342 | M | 0 days |  | 0
1 | 02 | 05 | 14 | 18 | [7 empty] | Develop and Deliver the Initial Monthly Building Block Team Development Conference Minutes to COR Sep-2016 | 1.02.05.14.18 | 2.7.15 | 23343 | M | 0 days |  | 0
1 | 02 | 05 | 15 | [8 empty] | Agreements facilitated with NCCoE collaborators (7.15) | 1.02.05.15 |  | 6892 | S | 84 days |  | 0
1 | 02 | 05 | 15 | 01 | [7 empty] | Agreements facilitated with NCCoE collaborators (7.15) Block-1 | 1.02.05.15.01 |  | 22206 | M | 0 days |  | 0
1 | 02 | 05 | 15 | 02 | [7 empty] | Agreements facilitated with NCCoE collaborators (7.15) Block-2 | 1.02.05.15.02 | 2.7.16 | 22210 | M | 0 days |  | 0
1 | 02 | 05 | 16 | [8 empty] | Roster of Use Case Development and Demostration Collaborators (7.16) | 1.02.05.16 |  | 6893 | S | 84 days |  | 0
1 | 02 | 05 | 16 | 01 | [7 empty] | Roster of Use Case Development and Demostration Collaborators (7.16) Block-1 | 1.02.05.16.01 |  | 22203 | M | 0 days |  | 0
1 | 02 | 05 | 16 | 02 | [7 empty] | Roster of Use Case Development and Demostration Collaborators (7.16) Block-2 | 1.02.05.16.02 | 2.7.17 | 22204 | M | 0 days |  | 0
1 | 02 | 05 | 17 | [8 empty] | Building Block Development Report and Demonstration Script (7.17) | 1.02.05.17 |  | 6894 | S | 99 days |  | 0
1 | 02 | 05 | 17 | 01 | [7 empty] | Building Block Development Report and Demonstration Script (7.17) Block-1 | 1.02.05.17.01 |  | 22169 | M | 0 days |  | 0
1 | 02 | 05 | 17 | 02 | [7 empty] | Building Block Development Report and Demonstration Script (7.17) Block-2 | 1.02.05.17.02 | 2.7.18 | 22201 | M | 0 days |  | 0
1 | 02 | 05 | 18 | [8 empty] | Building Block Demonstration Schedule (7.18) | 1.02.05.18 |  | 6895 | S | 114 days |  | 0
1 | 02 | 05 | 18 | 01 | [7 empty] | Building Block Demonstration Schedule (7.18) Block-1 | 1.02.05.18.01 |  | 22171 | M | 0 days |  | 0
1 | 02 | 05 | 18 | 02 | [7 empty] | Building Block Demonstration Schedule (7.18) Block-2 | 1.02.05.18.02 | 2.7.19 | 22200 | M | 0 days |  | 0
1 | 02 | 05 | 19 | [8 empty] | Building Block Demonstration Minutes (7.19) | 1.02.05.19 |  | 6896 | S | 114 days |  | 0
1 | 02 | 05 | 19 | 01 | [7 empty] | Building Block Demonstration Minutes (7.19) Block-1 | 1.02.05.19.01 |  | 22173 | M | 0 days |  | 0
1 | 02 | 05 | 19 | 02 | [7 empty] | Building Block Demonstration Minutes (7.19) Block-2 | 1.02.05.19.02 | 2.7.20 | 22172 | M | 0 days |  | 0
1 | 02 | 05 | 20 | [8 empty] | Building Block Documentation Report (7.20) | 1.02.05.20 |  | 6897 | S | 99 days |  | 0
1 | 02 | 05 | 20 | 01 | [7 empty] | Building Block Documentation Report (7.20) Block-1 | 1.02.05.20.01 |  | 22198 | M | 0 days |  | 0
1 | 02 | 05 | 20 | 02 | [7 empty] | Building Block Documentation Report (7.20) Block-2 | 1.02.05.20.02 | 2.8 | 22199 | M | 0 days |  | 0
1 | 02 | 06 | [9 empty] | Government Furnished Property,Material,Equipment or Information (GFP,GFM,GFE,GFF) (8.0) | 1.02.06 | 2.9 | 6913 | W | 525 days |  | 0
1 | 02 | 07 | [9 empty] | Security (9.0) | 1.02.07 | 2.1 | 6914 | W | 525 days |  | 0
1 | 02 | 08 | [9 empty] | Key Personnel (10.0) | 1.02.08 | 2.10.1 | 6915 | W | 525 days |  | 0
1 | 02 | 08 | 01 | [8 empty] | Cybersecurity Subject Matter Expert Designated | 1.02.08.01 | 2.10.2 | 6916 | T | 525 days |  | 0
1 | 02 | 08 | 02 | [8 empty] | Cybersecurity Development Subject Matter Expert Designated | 1.02.08.02 | 2.10.3 | 6917 | T | 525 days |  | 0
1 | 02 | 08 | 03 | [8 empty] | Cybersecurity Security Engineer Designated | 1.02.08.03 | 2.11 | 6919 | T | 525 days |  | 0
1 | 02 | 09 | [9 empty] | Travel (11.0) | 1.02.09 | 2.12 | 6920 | W | 525 days |  | 0
1 | 02 | 10 | [9 empty] | Place of performance (12.0) | 1.02.10 | 2.13 | 6921 | W | 525 days |  | 0
1 | 02 | 11 | [9 empty] | Perior of Performance (13.0) | 1.02.11 | 2.14 | 6922 | W | 0 days |  | 0
1 | 02 | 12 | [9 empty] | Risk Levels (14.0) | 1.02.12 | 3 | 6923 | W | 0 days |  | 0
| 02 | [10 empty] | Total Taskorder 2 | 1.02 |  |  | A2 |  |  | 29096.9158 | 0.25 | 0 | 1447.82 | [5 empty] | 0 |  | 3261.79 |  |  | 3620.32 | 197.47 | 4830.3105 |  |  |  |  | 3620.5 | 0 |  | 3397.05 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 623.15 | [5 empty] | 0 | [6 empty] | 1630.1 | 1809.73 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 791.7832 | 0 | 0 |  |  |  | 0 | 185.2621 |  | 0 | 59.7 |  | 0 | 0
1 | 03 | [10 empty] | Task Order 3 - NCCoE FFRDC Operations Management and Facilities Planning | 1.03 | 3.15 | 6798 | C | 1307 days |  | 169993.25
1 | 03 | 15 | [9 empty] | Task Order #3 Major Milestones | 1.03.15 | 3.15.1 | 7005 | S | 1305 days |  | 0
1 | 03 | 15 | 01 | [8 empty] | Task Order 3 Award | 1.03.15.01 | 3.15.2 | 7006 | M | 0 days |  | 0
1 | 03 | 15 | 02 | [8 empty] | Task Order 3 Closure- Operations Mgmt | 1.03.15.02 | 3.15.3 | 7007 | M | 0 days |  | 0
| 03 | 15 | 03 | [8 empty] | Task Order 3 Closure- Facilities Planning Suport | 1.03.15.03 | 3.5.a | 7008 | M | 0 days |  | 0
1 | 03 | 01 | [9 empty] | Operations Management and technical Support Tasks (5.2) | 1.03.01 | 3.5.1 | 6928 | C | 1306 days |  | 168439
1 | 03 | 01 | 01 | [8 empty] | Provide Program Management Support by Assigning a Program Manager and appropriate senior administrative (5.1) | 1.03.01.01 | 3.5.1.1 | 6929 | W | 1306 days |  | 158673 | 8995 | 0 | 716 | [18 empty] | 9042 |  | 13575 | 9050 | 9050 | [7 empty] | 0 | [5 empty] | 9042 | [8 empty] | 2375 |  |  |  |  | 8343 | [7 empty] | 9050 |  | 9050 |  | 4750 | 9020 |  |  | 9050 |  |  |  | 9050 |  |  |  | 20475 | 8990 | 9050
1 | 03 | 01 | 01 | 01 | [7 empty] | Provide all clerical, administrative, technical and scientific writing services necessary | 1.03.01.01.01 | 3.5.1.2 | 6931 | T | 1306 days | 10448 | 14424.8182 | 817.7273 | 0 | 65.0909 | [18 empty] | 822 |  | 1234.0909 | 822.7273 | 822.7273 | [7 empty] | 0 | [5 empty] | 822 | [8 empty] | 215.9091 |  |  |  |  | 758.4545 | [7 empty] | 822.7273 |  | 822.7273 |  | 431.8182 | 820 |  |  | 822.7273 |  |  |  | 822.7273 |  |  |  | 1861.3636 | 817.2727 | 822.7273
1 | 03 | 01 | 01 | 02 | [7 empty] | Manage FFRDC contractor employees, subcontractors and consultants working under all task orders issued under the IDIQ contract | 1.03.01.01.02 | 3.5.1.3 | 6932 | T | 1306 days | 10448 | 14424.8182 | 817.7273 | 0 | 65.0909 | [18 empty] | 822 |  | 1234.0909 | 822.7273 | 822.7273 | [7 empty] | 0 | [5 empty] | 822 | [8 empty] | 215.9091 |  |  |  |  | 758.4545 | [7 empty] | 822.7273 |  | 822.7273 |  | 431.8182 | 820 |  |  | 822.7273 |  |  |  | 822.7273 |  |  |  | 1861.3636 | 817.2727 | 822.7273
1 | 03 | 01 | 01 | 03 | [7 empty] | Manage task order activities as necessary to ensure timely deliveries that meet the requirements of all contract task order Statement of Work | 1.03.01.01.03 | 3.5.1.4 | 6934 | T | 1306 days | 10448 | 14424.8182 | 817.7273 | 0 | 65.0909 | [18 empty] | 822 |  | 1234.0909 | 822.7273 | 822.7273 | [7 empty] | 0 | [5 empty] | 822 | [8 empty] | 215.9091 |  |  |  |  | 758.4545 | [7 empty] | 822.7273 |  | 822.7273 |  | 431.8182 | 820 |  |  | 822.7273 |  |  |  | 822.7273 |  |  |  | 1861.3636 | 817.2727 | 822.7273
1 | 03 | 01 | 01 | 04 | [7 empty] | Manage the implementation of the contractor Organizational Conflict of Interest Compliance Program for all FFRDC tasks | 1.03.01.01.04 | 3.5.1.5 | 6935 | T | 1306 days | 10448 | 14424.8182 | 817.7273 | 0 | 65.0909 | [18 empty] | 822 |  | 1234.0909 | 822.7273 | 822.7273 | [7 empty] | 0 | [5 empty] | 822 | [8 empty] | 215.9091 |  |  |  |  | 758.4545 | [7 empty] | 822.7273 |  | 822.7273 |  | 431.8182 | 820 |  |  | 822.7273 |  |  |  | 822.7273 |  |  |  | 1861.3636 | 817.2727 | 822.7273
1 | 03 | 01 | 01 | 05 | [7 empty] | Provide technical support for the full range of IT and support systems required for FFRDC operations | 1.03.01.01.05 | 3.5.1.6 | 6936 | T | 1306 days | 10448 | 14424.8182 | 817.7273 | 0 | 65.0909 | [18 empty] | 822 |  | 1234.0909 | 822.7273 | 822.7273 | [7 empty] | 0 | [5 empty] | 822 | [8 empty] | 215.9091 |  |  |  |  | 758.4545 | [7 empty] | 822.7273 |  | 822.7273 |  | 431.8182 | 820 |  |  | 822.7273 |  |  |  | 822.7273 |  |  |  | 1861.3636 | 817.2727 | 822.7273
1 | 03 | 01 | 01 | 06 | [7 empty] | Facilitate government NCCoE program partnerships, communications, and outreach operations: | 1.03.01.01.06 | 3.5.1.6.1 | 6937 | S | 1306 days | 0 | 0 | 0 | 0 | 0 | [18 empty] | 0 |  | 0 | 0 | 0 | [13 empty] | 0 | [8 empty] | 0 |  |  |  |  | 0 | [7 empty] | 0 |  | 0 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0
1 | 03 | 01 | 01 | 06 | 01 | [6 empty] | Participation in all NCCoE Planning Activities | 1.03.01.01.06.01 | 3.5.1.6.2 | 6938 | T | 1306 days | 10448 | 14424.8182 | 817.7273 | 0 | 65.0909 | [18 empty] | 822 |  | 1234.0909 | 822.7273 | 822.7273 | [7 empty] | 0 | [5 empty] | 822 | [8 empty] | 215.9091 |  |  |  |  | 758.4545 | [7 empty] | 822.7273 |  | 822.7273 |  | 431.8182 | 820 |  |  | 822.7273 |  |  |  | 822.7273 |  |  |  | 1861.3636 | 817.2727 | 822.7273
1 | 03 | 01 | 01 | 06 | 02 | [6 empty] | Facilitation of various formal and informal agreements | 1.03.01.01.06.02 | 3.5.1.6.3 | 6944 | T | 1306 days | 10448 | 14424.8182 | 817.7273 | 0 | 65.0909 | [18 empty] | 822 |  | 1234.0909 | 822.7273 | 822.7273 | [7 empty] | 0 | [5 empty] | 822 | [8 empty] | 215.9091 |  |  |  |  | 758.4545 | [7 empty] | 822.7273 |  | 822.7273 |  | 431.8182 | 820 |  |  | 822.7273 |  |  |  | 822.7273 |  |  |  | 1861.3636 | 817.2727 | 822.7273
1 | 03 | 01 | 01 | 06 | 03 | [6 empty] | Support to NCCoE conference operations | 1.03.01.01.06.03 | 3.5.1.6.4 | 6945 | T | 1306 days | 10448 | 14424.8182 | 817.7273 | 0 | 65.0909 | [18 empty] | 822 |  | 1234.0909 | 822.7273 | 822.7273 | [7 empty] | 0 | [5 empty] | 822 | [8 empty] | 215.9091 |  |  |  |  | 758.4545 | [7 empty] | 822.7273 |  | 822.7273 |  | 431.8182 | 820 |  |  | 822.7273 |  |  |  | 822.7273 |  |  |  | 1861.3636 | 817.2727 | 822.7273
1 | 03 | 01 | 01 | 06 | 04 | [6 empty] | NCCoE outreach activities | 1.03.01.01.06.04 | 3.5.1.7 | 6946 | T | 1306 days | 10448 | 14424.8182 | 817.7273 | 0 | 65.0909 | [18 empty] | 822 |  | 1234.0909 | 822.7273 | 822.7273 | [7 empty] | 0 | [5 empty] | 822 | [8 empty] | 215.9091 |  |  |  |  | 758.4545 | [7 empty] | 822.7273 |  | 822.7273 |  | 431.8182 | 820 |  |  | 822.7273 |  |  |  | 822.7273 |  |  |  | 1861.3636 | 817.2727 | 822.7273
1 | 03 | 01 | 01 | 07 | [7 empty] | Safely and efficiently conduct FFRDC mail and parcel receipt and delivery operations | 1.03.01.01.07 | 3.5.1.8 | 6948 | T | 1306 days | 10448 | 14424.8182 | 817.7273 | 0 | 65.0909 | [18 empty] | 822 |  | 1234.0909 | 822.7273 | 822.7273 | [7 empty] | 0 | [5 empty] | 822 | [8 empty] | 215.9091 |  |  |  |  | 758.4545 | [7 empty] | 822.7273 |  | 822.7273 |  | 431.8182 | 820 |  |  | 822.7273 |  |  |  | 822.7273 |  |  |  | 1861.3636 | 817.2727 | 822.7273
1 | 03 | 01 | 01 | 08 | [7 empty] | Conduct clerical and reception support required for NCCoE FFRDC operations. | 1.03.01.01.08 |  | 6949 | T | 1306 days | 10448 | 14424.8182 | 817.7273 | 0 | 65.0909 | [18 empty] | 822 |  | 1234.0909 | 822.7273 | 822.7273 | [7 empty] | 0 | [5 empty] | 822 | [8 empty] | 215.9091 |  |  |  |  | 758.4545 | [7 empty] | 822.7273 |  | 822.7273 |  | 431.8182 | 820 |  |  | 822.7273 |  |  |  | 822.7273 |  |  |  | 1861.3636 | 817.2727 | 822.7273
| 03 | 01 | 01 | [8 empty] | Total Hours | 1.03.01.01 |  |  | A |  | 114928 | 158673 | 8995 | 0 | 716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9042 | 0 | 13575 | 9050 | 9050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375 | 0 | 0 | 0 | 0 | 8343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050 | 0 | 9050 | 0 | 4750 | 9020 | 0 | 0 | 9050 | 0 | 0 | 0 | 9050 | 0 | 0 | 0 | 20475 | 8990 | 9050 | 0
1 | 03 | 01 | 02 | [8 empty] | Operations Management Work Plan (5.2) | 1.03.01.02 | 3.5.2 | 22213 | W | 1306 days |  | 0
1 | 03 | 01 | 02 | 01 | [7 empty] | Develop and Deliver the Operations Management Project Work Plan to the COR (5.2) | 1.03.01.02.01 |  | 6950 | T | 15 edays | 720 | 0
1 | 03 | 01 | 02 | 02 | [7 empty] | COR approves the Operations Management Project Work Plan (IMP) | 1.03.01.02.02 |  | 21877 | T | 5 days | 40 | 0
1 | 03 | 01 | 02 | 03 | [7 empty] | Status and Maintain the Operations Management Project Work Plan to the COR | 1.03.01.02.03 |  | 21878 | T | 1237 days | 9896 | 0
| 03 | 01 | 02 | [8 empty] | Total Hours | 1.03.01.02 |  |  | A |  | 10656 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 03 | 01 | 03 | [8 empty] | Task Order 1 Task Management | 1.03.01.03 |  | 22742 | W | 525 days |  | 362 | [10 empty] | 362
| 03 | 01 | 03 | [8 empty] | Total Hours | 1.03.01.03 |  |  | A |  |  | 362 | 0 | 0 | 0 | [5 empty] | 0 |  | 362 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 03 | 01 | 04 | [8 empty] | Task Order 2 Task Management | 1.03.01.04 | 3.5.b | 22741 | W | 525 days |  | 362 | [10 empty] | 362
| 03 | 01 | 04 | [8 empty] | Total Hours | 1.03.01.04 |  |  | A |  |  | 362 | 0 | 0 | 0 | [5 empty] | 0 |  | 362 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 03 | 01 | 05 | [8 empty] | Task Order 3 Task Management | 1.03.01.05 | 3.5.b | 22741 | W | 525 days |  | 9042 |  | 9042 | [8 empty] | 0
| 03 | 01 | 05 | [8 empty] | Total Hours | 1.03.01.05 |  |  | A |  |  | 9042 | 0 | 9042 | 0 | [5 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
1 | 03 | 02 | [9 empty] | Facilities Planning Support Tasks (5.3 through 5.6): | 1.03.02 |  | 6958 | C | 1300 days |  | 755.25
1 | 03 | 02 | 01 | [8 empty] | Facility Design Work Plan | 1.03.02.01 | 3.5.3 | 22214 | W | 64 days |  | 246 | [58 empty] | 8 | [7 empty] | 30 | [9 empty] | 208
1 | 03 | 02 | 01 | 01 | [7 empty] | Develop and Deliver a Phase II Facility Design and Design Implementation Work Plan (5.3) | 1.03.02.01.01 |  | 6959 | T | 90 edays | 720 | 246 | [58 empty] | 8 | [7 empty] | 30 | [9 empty] | 208
| 03 | 02 | 01 | [8 empty] | Total Hours | 1.03.02.01 |  |  | A |  | 720 | 246 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 8 |  | 0 | 0 |  | 0 |  | 0 | 30 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 208 | 0 |  | 0 | 0
1 | 03 | 02 | 02 | [8 empty] | Prepare and Execute a Monthly Facility Infrastructure Design Conference Agenda (5.4) | 1.03.02.02 |  | 21876 | W | 1291 days |  | 156 | [60 empty] | 24 | [15 empty] | 66 | 66
1 | 03 | 02 | 02 | 01 | [7 empty] | Monthly Facility Planning Meeting Submittal (60 months) | 1.03.02.02.01 |  | 12297 | S | 1291 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 01 | [6 empty] | 2014 | 1.03.02.02.01.01 |  | 12298 | S | 50 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 01 | 01 | [5 empty] | Oct 2014 | 1.03.02.02.01.01.01 | 3.5.4 | 12299 | S | 8 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 01 | 01 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.01.01.01 | 3.5.5 | 6973 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 01 | 01 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.01.01.02 | 3.5.6 | 6974 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 01 | 01 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.01.01.03 |  | 6975 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 01 | 02 | [5 empty] | Nov 2014 | 1.03.02.02.01.01.02 | 3.5.4 | 12303 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 01 | 02 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.01.02.01 | 3.5.5 | 12304 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 01 | 02 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.01.02.02 | 3.5.6 | 12305 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 01 | 02 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.01.02.03 |  | 12306 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 01 | 03 | [5 empty] | Dec 2014 | 1.03.02.02.01.01.03 | 3.5.4 | 12310 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 01 | 03 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.01.03.01 | 3.5.5 | 12311 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 01 | 03 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.01.03.02 | 3.5.6 | 12312 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 01 | 03 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.01.03.03 |  | 12313 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | [6 empty] | 2015 | 1.03.02.02.01.02 |  | 12320 | S | 251 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 01 | [5 empty] | Jan 2015 | 1.03.02.02.01.02.01 | 3.5.4 | 12354 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 01 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.01.01 | 3.5.5 | 12355 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 01 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.01.02 | 3.5.6 | 12356 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 01 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.01.03 |  | 12357 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 02 | [5 empty] | Feb 2015 | 1.03.02.02.01.02.02 | 3.5.4 | 12358 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 02 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.02.01 | 3.5.5 | 12359 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 02 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.02.02 | 3.5.6 | 12360 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 02 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.02.03 |  | 12361 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 03 | [5 empty] | Mar 2015 | 1.03.02.02.01.02.03 | 3.5.4 | 12371 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 03 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.03.01 | 3.5.5 | 12372 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 03 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.03.02 | 3.5.6 | 12373 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 03 | 03 |  |  |  |  | Phase 2 - Facility DesiFacility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.03.03 |  | 12374 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 04 | [5 empty] | Apr 2015 | 1.03.02.02.01.02.04 | 3.5.4 | 12393 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 04 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.04.01 | 3.5.5 | 12394 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 04 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.04.02 | 3.5.6 | 12395 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 04 | 03 |  |  |  |  | Phase 2Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.04.03 |  | 12396 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 05 | [5 empty] | May 2015 | 1.03.02.02.01.02.05 | 3.5.4 | 12433 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 05 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.05.01 | 3.5.5 | 12434 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 05 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.05.02 | 3.5.6 | 12435 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 05 | 03 |  |  |  |  | Phase 2 - FaciliFacility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.05.03 |  | 12436 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 06 | [5 empty] | Jun 2015 | 1.03.02.02.01.02.06 | 3.5.4 | 12509 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 06 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.06.01 | 3.5.5 | 12510 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 06 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.06.02 | 3.5.6 | 12511 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 06 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.06.03 |  | 12512 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 07 | [5 empty] | Jul 2015 | 1.03.02.02.01.02.07 | 3.5.4 | 12657 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 07 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.07.01 | 3.5.5 | 12658 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 07 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.07.02 | 3.5.6 | 12659 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 07 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.07.03 |  | 12660 | T | 1 day |  | 0 | [60 empty] | 0 | [15 empty] | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 08 | [5 empty] | Aug 2015 | 1.03.02.02.01.02.08 | 3.5.4 | 12949 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 08 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.08.01 | 3.5.5 | 12950 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 08 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.08.02 | 3.5.6 | 12951 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 08 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.08.03 |  | 12952 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 09 | [5 empty] | Sep 2015 | 1.03.02.02.01.02.09 | 3.5.4 | 13529 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 09 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.09.01 | 3.5.5 | 13530 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 09 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.09.02 | 3.5.6 | 13531 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 09 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.09.03 |  | 13532 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 10 | [5 empty] | Oct 2015 | 1.03.02.02.01.02.10 | 3.5.4 | 14685 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 10 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.10.01 | 3.5.5 | 14686 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 10 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.10.02 | 3.5.6 | 14687 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 10 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.10.03 |  | 14688 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 11 | [5 empty] | Nov 2015 | 1.03.02.02.01.02.11 | 3.5.4 | 14689 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 11 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.11.01 | 3.5.5 | 14690 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 11 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.11.02 | 3.5.6 | 14691 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 11 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.11.03 |  | 14692 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 12 | [5 empty] | Dec 2015 | 1.03.02.02.01.02.12 | 3.5.4 | 14693 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 02 | 12 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.02.12.01 | 3.5.5 | 14694 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 12 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.02.12.02 | 3.5.6 | 14695 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 02 | 12 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.02.12.03 |  | 14696 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | [6 empty] | 2016 | 1.03.02.02.01.03 |  | 14698 | S | 252 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 01 | [5 empty] | Jan 2016 | 1.03.02.02.01.03.01 | 3.5.4 | 14699 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 01 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.01.01 | 3.5.5 | 14700 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 01 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.01.02 | 3.5.6 | 14701 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 01 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.01.03 |  | 14702 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 02 | [5 empty] | Feb 2016 | 1.03.02.02.01.03.02 | 3.5.4 | 14703 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 02 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.02.01 | 3.5.5 | 14704 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 02 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.02.02 | 3.5.6 | 14705 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 02 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.02.03 |  | 14706 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 03 | [5 empty] | Mar 2016 | 1.03.02.02.01.03.03 | 3.5.4 | 14707 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 03 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.03.01 | 3.5.5 | 14708 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 03 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.03.02 | 3.5.6 | 14709 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 03 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.03.03 |  | 14710 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 04 | [5 empty] | Apr 2016 | 1.03.02.02.01.03.04 | 3.5.4 | 14711 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 04 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.04.01 | 3.5.5 | 14712 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 04 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.04.02 | 3.5.6 | 14713 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 04 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.04.03 |  | 14714 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 05 | [5 empty] | May 2016 | 1.03.02.02.01.03.05 | 3.5.4 | 14715 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 05 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.05.01 | 3.5.5 | 14716 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 05 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.05.02 | 3.5.6 | 14717 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 05 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.05.03 |  | 14718 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 06 | [5 empty] | Jun 2016 | 1.03.02.02.01.03.06 | 3.5.4 | 14719 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 06 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.06.01 | 3.5.5 | 14720 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 06 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.06.02 | 3.5.6 | 14721 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 06 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.06.03 |  | 14722 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 07 | [5 empty] | Jul 2016 | 1.03.02.02.01.03.07 | 3.5.4 | 14723 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 07 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.07.01 | 3.5.5 | 14724 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 07 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.07.02 | 3.5.6 | 14725 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 07 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.07.03 |  | 14726 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 08 | [5 empty] | Aug 2016 | 1.03.02.02.01.03.08 | 3.5.4 | 14727 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 08 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.08.01 | 3.5.5 | 14728 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 08 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.08.02 | 3.5.6 | 14729 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 08 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.08.03 |  | 14730 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 09 | [5 empty] | Sep 2016 | 1.03.02.02.01.03.09 | 3.5.4 | 14731 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 09 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.09.01 | 3.5.5 | 14732 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 09 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.09.02 | 3.5.6 | 14733 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 09 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.09.03 |  | 14734 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 10 | [5 empty] | Oct 2016 | 1.03.02.02.01.03.10 | 3.5.4 | 14735 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 10 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.10.01 | 3.5.5 | 14736 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 10 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.10.02 | 3.5.6 | 14737 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 10 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.10.03 |  | 14738 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 11 | [5 empty] | Nov 2016 | 1.03.02.02.01.03.11 | 3.5.4 | 14739 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 11 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.11.01 | 3.5.5 | 14740 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 11 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.11.02 | 3.5.6 | 14741 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 11 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.11.03 |  | 14742 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 12 | [5 empty] | Dec 2016 | 1.03.02.02.01.03.12 | 3.5.4 | 14743 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 03 | 12 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.03.12.01 | 3.5.5 | 14744 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 12 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.03.12.02 | 3.5.6 | 14745 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 03 | 12 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.03.12.03 |  | 14746 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | [6 empty] | 2017 | 1.03.02.02.01.04 |  | 17057 | S | 251 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 01 | [5 empty] | Jan 2017 | 1.03.02.02.01.04.01 | 3.5.4 | 17058 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 01 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.04.01.01 | 3.5.5 | 17059 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 01 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.01.02 | 3.5.6 | 17060 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 01 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.01.03 |  | 17061 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 02 | [5 empty] | Feb 2017 | 1.03.02.02.01.04.02 | 3.5.4 | 17062 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 02 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.04.02.01 | 3.5.5 | 17063 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 02 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.02.02 | 3.5.6 | 17064 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 02 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.02.03 |  | 17065 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 03 | [5 empty] | Mar 2017 | 1.03.02.02.01.04.03 | 3.5.4 | 17066 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 03 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.04.03.01 | 3.5.5 | 17067 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 03 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.03.02 | 3.5.6 | 17068 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 03 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.03.03 |  | 17069 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 04 | [5 empty] | Apr 2017 | 1.03.02.02.01.04.04 | 3.5.4 | 17070 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 04 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agendas | 1.03.02.02.01.04.04.01 | 3.5.5 | 17071 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 04 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.04.02 | 3.5.6 | 17072 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 04 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.04.03 |  | 17073 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 05 | [5 empty] | May 2017 | 1.03.02.02.01.04.05 | 3.5.4 | 17074 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 05 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.04.05.01 | 3.5.5 | 17075 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 05 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.05.02 | 3.5.6 | 17076 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 05 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.05.03 |  | 17077 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 06 | [5 empty] | Jun 2017 | 1.03.02.02.01.04.06 | 3.5.4 | 17078 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 06 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.04.06.01 | 3.5.5 | 17079 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 06 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.06.02 | 3.5.6 | 17080 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 06 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.06.03 |  | 17081 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 07 | [5 empty] | Jul 2017 | 1.03.02.02.01.04.07 | 3.5.4 | 17082 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 07 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.04.07.01 | 3.5.5 | 17083 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 07 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.07.02 | 3.5.6 | 17084 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 07 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.07.03 |  | 17085 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 08 | [5 empty] | Aug 2017 | 1.03.02.02.01.04.08 | 3.5.4 | 17086 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 08 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.04.08.01 | 3.5.5 | 17087 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 08 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.08.02 | 3.5.6 | 17088 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 08 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.08.03 |  | 17089 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 09 | [5 empty] | Sep 2017 | 1.03.02.02.01.04.09 | 3.5.4 | 17090 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 09 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.04.09.01 | 3.5.5 | 17091 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 09 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.09.02 | 3.5.6 | 17092 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 09 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.09.03 |  | 17093 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 10 | [5 empty] | Oct 2017 | 1.03.02.02.01.04.10 | 3.5.4 | 17094 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 10 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.04.10.01 | 3.5.5 | 17095 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 10 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.10.02 | 3.5.6 | 17096 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 10 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.10.03 |  | 17097 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 11 | [5 empty] | Nov 2017 | 1.03.02.02.01.04.11 | 3.5.4 | 17098 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 11 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.04.11.01 | 3.5.5 | 17099 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 11 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.11.02 | 3.5.6 | 17100 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 11 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.11.03 |  | 17101 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 12 | [5 empty] | Dec 2017 | 1.03.02.02.01.04.12 | 3.5.4 | 17102 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 04 | 12 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.04.12.01 | 3.5.5 | 17103 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 12 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.04.12.02 | 3.5.6 | 17104 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 04 | 12 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.04.12.03 |  | 17105 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | [6 empty] | 2018 | 1.03.02.02.01.05 |  | 17106 | S | 251 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 01 | [5 empty] | Jan 2018 | 1.03.02.02.01.05.01 | 3.5.4 | 17107 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 01 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.01.01 | 3.5.5 | 17108 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 01 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.01.02 | 3.5.6 | 17109 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 01 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.01.03 |  | 17110 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 02 | [5 empty] | Feb 2018 | 1.03.02.02.01.05.02 | 3.5.4 | 17111 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 02 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.02.01 | 3.5.5 | 17112 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 02 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.02.02 | 3.5.6 | 17113 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 02 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.02.03 |  | 17114 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 03 | [5 empty] | Mar 2018 | 1.03.02.02.01.05.03 | 3.5.4 | 17115 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 03 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.03.01 | 3.5.5 | 17116 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 03 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.03.02 | 3.5.6 | 17117 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 03 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.03.03 |  | 17118 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 04 | [5 empty] | Apr 2018 | 1.03.02.02.01.05.04 | 3.5.4 | 17119 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 04 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.04.01 | 3.5.5 | 17120 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 04 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.04.02 | 3.5.6 | 17121 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 04 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.04.03 |  | 17122 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 05 | [5 empty] | May 2018 | 1.03.02.02.01.05.05 | 3.5.4 | 17123 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 05 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.05.01 | 3.5.5 | 17124 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 05 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.05.02 | 3.5.6 | 17125 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 05 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.05.03 |  | 17126 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 06 | [5 empty] | Jun 2018 | 1.03.02.02.01.05.06 | 3.5.4 | 17127 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 06 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.06.01 | 3.5.5 | 17128 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 06 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.06.02 | 3.5.6 | 17129 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 06 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.06.03 |  | 17130 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 07 | [5 empty] | Jul 2018 | 1.03.02.02.01.05.07 | 3.5.4 | 17131 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 07 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.07.01 | 3.5.5 | 17132 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 07 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.07.02 | 3.5.6 | 17133 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 07 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.07.03 |  | 17134 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 08 | [5 empty] | Aug 2018 | 1.03.02.02.01.05.08 | 3.5.4 | 17135 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 08 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.08.01 | 3.5.5 | 17136 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 08 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.08.02 | 3.5.6 | 17137 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 08 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.08.03 |  | 17138 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 09 | [5 empty] | Sep 2018 | 1.03.02.02.01.05.09 | 3.5.4 | 17139 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 09 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.09.01 | 3.5.5 | 17140 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 09 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.09.02 | 3.5.6 | 17141 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 09 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.09.03 |  | 17142 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 10 | [5 empty] | Oct 2018 | 1.03.02.02.01.05.10 | 3.5.4 | 17143 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 10 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.10.01 | 3.5.5 | 17144 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 10 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.10.02 | 3.5.6 | 17145 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 10 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.10.03 |  | 17146 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 11 | [5 empty] | Nov 2018 | 1.03.02.02.01.05.11 | 3.5.4 | 17147 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 11 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.11.01 | 3.5.5 | 17148 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 11 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.11.02 | 3.5.6 | 17149 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 11 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.11.03 |  | 17150 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 12 | [5 empty] | Dec 2018 | 1.03.02.02.01.05.12 | 3.5.4 | 17151 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 05 | 12 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.05.12.01 | 3.5.5 | 17152 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 12 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.05.12.02 | 3.5.6 | 17153 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 05 | 12 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.05.12.03 |  | 17154 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | [6 empty] | 2019 | 1.03.02.02.01.06 |  | 21775 | S | 188 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 06 | 01 | [5 empty] | Jan 2019 | 1.03.02.02.01.06.01 | 3.5.4 | 21776 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 06 | 01 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.06.01.01 | 3.5.5 | 21777 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 01 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.06.01.02 | 3.5.6 | 21778 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 01 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.06.01.03 |  | 21779 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 02 | [5 empty] | Feb 2019 | 1.03.02.02.01.06.02 | 3.5.4 | 21780 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 06 | 02 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.06.02.01 | 3.5.5 | 21781 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 02 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.06.02.02 | 3.5.6 | 21782 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 02 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.06.02.03 |  | 21783 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 03 | [5 empty] | Mar 2019 | 1.03.02.02.01.06.03 | 3.5.4 | 21784 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 06 | 03 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.06.03.01 | 3.5.5 | 21785 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 03 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.06.03.02 | 3.5.6 | 21786 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 03 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.06.03.03 |  | 21787 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 04 | [5 empty] | Apr 2019 | 1.03.02.02.01.06.04 | 3.5.4 | 21788 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 06 | 04 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.06.04.01 | 3.5.5 | 21789 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 04 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.06.04.02 | 3.5.6 | 21790 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 04 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.06.04.03 |  | 21791 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 05 | [5 empty] | May 2019 | 1.03.02.02.01.06.05 | 3.5.4 | 21792 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 06 | 05 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.06.05.01 | 3.5.5 | 21793 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 05 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.06.05.02 | 3.5.6 | 21794 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 05 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.06.05.03 |  | 21795 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 06 | [5 empty] | Jun 2019 | 1.03.02.02.01.06.06 | 3.5.4 | 21796 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 06 | 06 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.06.06.01 | 3.5.5 | 21797 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 06 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.06.06.02 | 3.5.6 | 21798 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 06 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.06.06.03 |  | 21799 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 07 | [5 empty] | Jul 2019 | 1.03.02.02.01.06.07 | 3.5.4 | 21800 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 06 | 07 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.06.07.01 | 3.5.5 | 21801 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 07 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.06.07.02 | 3.5.6 | 21802 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 07 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.06.07.03 |  | 21803 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 08 | [5 empty] | Aug 2019 | 1.03.02.02.01.06.08 | 3.5.4 | 21804 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 06 | 08 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.06.08.01 | 3.5.5 | 21805 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 08 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.06.08.02 | 3.5.6 | 21806 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 08 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.06.08.03 |  | 21807 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 09 | [5 empty] | Sep 2019 | 1.03.02.02.01.06.09 | 3.5.4 | 21808 | S | 13 days | 0 | 0
1 | 03 | 02 | 02 | 01 | 06 | 09 | 01 |  |  |  |  | Prepare and execute a Monthly Facility Infrastructure Design Conference Agenda | 1.03.02.02.01.06.09.01 | 3.5.5 | 21809 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 09 | 02 |  |  |  |  | Facility Development and Acquisition Meetings | 1.03.02.02.01.06.09.02 | 3.5.6 | 21810 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
1 | 03 | 02 | 02 | 01 | 06 | 09 | 03 |  |  |  |  | Facility Infrastructure Design Conference Minutes | 1.03.02.02.01.06.09.03 |  | 21811 | T | 1 day | 8 | 0.87151 | [60 empty] | 0.13408 | [15 empty] | 0.36872 | 0.36872
| 03 | 02 | 02 | [8 empty] | Total Hours | 1.03.02.02 |  |  | A |  | 1432 | 156 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 24 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 66 | 66 |  | 0 | 0
1 | 03 | 02 | 03 | [8 empty] | Conduct in-person or teleconference meetings | 1.03.02.03 |  | 22226 | W | 44.5 days |  | 240 | [53 empty] | 150 | [23 empty] | 90
1 | 03 | 02 | 03 | 01 | [7 empty] | Jan 2015 | 1.03.02.03.01 | 3.5.4 | 22229 | S | 25 days | 0 | 0
1 | 03 | 02 | 03 | 01 | 01 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.01 | 3.5.4 | 22301 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 02 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.02 | 3.5.4 | 22230 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 03 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.03 | 3.5.5 | 22300 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 04 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.04 | 3.5.5 | 22231 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 05 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.05 | 3.5.5 | 22321 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 06 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.06 | 3.5.5 | 22320 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 07 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.07 | 3.5.5 | 22319 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 08 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.08 | 3.5.5 | 22318 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 09 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.09 | 3.5.5 | 22317 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 10 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.10 | 3.5.5 | 22316 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 11 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.11 | 3.5.5 | 22315 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 12 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.12 | 3.5.5 | 22314 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 13 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.13 | 3.5.5 | 22313 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 14 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.14 | 3.5.5 | 22323 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 15 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.15 | 3.5.5 | 22324 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 16 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.16 | 3.5.5 | 22326 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 17 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.17 | 3.5.5 | 22327 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 18 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.18 | 3.5.5 | 22328 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 19 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.19 | 3.5.5 | 22329 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 20 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.20 | 3.5.5 | 22330 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 21 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.21 | 3.5.5 | 22331 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 22 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.22 | 3.5.5 | 22332 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 23 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.23 | 3.5.5 | 22333 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 24 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.24 | 3.5.5 | 22325 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 25 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.25 | 3.5.5 | 22334 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 26 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.26 | 3.5.5 | 22335 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 27 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.27 | 3.5.5 | 22336 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 28 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.28 | 3.5.5 | 22337 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 29 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.29 | 3.5.5 | 22339 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 30 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.30 | 3.5.5 | 22340 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 31 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.31 | 3.5.5 | 22341 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 32 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.32 | 3.5.5 | 22338 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 33 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.33 | 3.5.5 | 22342 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 34 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.34 | 3.5.5 | 22343 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 35 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.35 | 3.5.5 | 22344 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 36 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.36 | 3.5.5 | 22345 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 37 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.37 | 3.5.5 | 22346 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 38 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.38 | 3.5.5 | 22347 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 39 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.39 | 3.5.5 | 22348 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 40 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.40 | 3.5.5 | 22349 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 41 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.41 | 3.5.5 | 22350 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 42 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.42 | 3.5.5 | 22351 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 43 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.43 | 3.5.5 | 22352 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 44 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.44 | 3.5.5 | 22375 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 45 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.45 | 3.5.5 | 22353 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 46 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.46 | 3.5.5 | 22374 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 47 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.47 | 3.5.5 | 22354 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 48 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.48 | 3.5.5 | 22373 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 49 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.49 | 3.5.5 | 22355 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 01 | 50 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.01.50 |  | 22372 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | [7 empty] | Feb 2015 | 1.03.02.03.02 | 3.5.5 | 22383 | S | 19.5 days | 0 | 0
1 | 03 | 02 | 03 | 02 | 01 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.01 | 3.5.5 | 22357 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 02 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.02 | 3.5.5 | 22371 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 03 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.03 | 3.5.5 | 22356 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 04 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.04 | 3.5.5 | 22370 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 05 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.05 | 3.5.5 | 22358 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 06 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.06 |  | 22369 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 07 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.07 | 3.5.5 | 22312 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 08 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.08 |  | 22368 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 09 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.09 | 3.5.5 | 22311 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 10 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.10 | 3.5.5 | 22367 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 11 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.11 |  | 22376 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 12 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.12 | 3.5.5 | 22310 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 13 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.13 |  | 22366 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 14 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.14 | 3.5.5 | 22309 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 15 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.15 |  | 22365 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 16 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.16 | 3.5.5 | 22308 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 17 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.17 | 3.5.5 | 22364 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 18 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.18 | 3.5.5 | 22377 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 19 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.19 |  | 22363 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 20 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.20 | 3.5.5 | 22306 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 21 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.21 |  | 22362 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 22 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.22 | 3.5.5 | 22305 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 23 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.23 |  | 22361 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 24 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.24 | 3.5.5 | 22304 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 25 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.25 |  | 22360 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 26 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.26 | 3.5.5 | 22303 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 27 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.27 |  | 22359 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 28 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.28 | 3.5.4 | 22264 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 29 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.29 |  | 22302 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 30 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.30 |  | 22263 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 31 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.31 |  | 22262 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 32 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.32 |  | 22261 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 33 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.33 | 3.5.5 | 22260 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 34 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.34 | 3.5.5 | 22322 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 35 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.35 | 3.5.5 | 22378 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 36 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.36 | 3.5.5 | 22379 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 37 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.37 | 3.5.5 | 22380 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 38 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.38 | 3.5.5 | 22381 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
1 | 03 | 02 | 03 | 02 | 39 | [6 empty] | Teleconference meeting 5.5 | 1.03.02.03.02.39 |  | 22382 | T | 0.5 days | 4 | 2.6966 | [53 empty] | 1.6854 | [23 empty] | 1.0112
| 03 | 02 | 03 | [8 empty] | Total Hours | 1.03.02.03 |  |  | A |  | 356 | 240 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 150 |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 90 |  | 0 | 0
1 | 03 | 02 | 04 | [8 empty] | Prepare and deliver a draft Phase II Facility Design Report | 1.03.02.04 |  | 22227 | W | 80 days |  | 113.25 | [76 empty] | 113.25
1 | 03 | 02 | 04 | 01 | [7 empty] | Develop and Deliver a Draft Phase II Facility Design Report | 1.03.02.04.01 |  | 21956 | T | 60 days | 480 | 84.9375 | [76 empty] | 84.9375
1 | 03 | 02 | 04 | 02 | [7 empty] | COR Approves Phase II Facility Design Report (IMP) | 1.03.02.04.02 |  | 21955 | T | 5 days | 40 | 7.0781 | [76 empty] | 7.0781
1 | 03 | 02 | 04 | 03 | [7 empty] | Deliver Final Phase II Facility Design Report | 1.03.02.04.03 | 3.6 | 21954 | T | 3 wks | 120 | 21.2344 | [76 empty] | 21.2344
| 03 | 02 | 04 | [8 empty] | Total Hours | 1.03.02.04 |  |  | A |  | 640 | 113.25 | 0 | 0 | 0 | [5 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 113.25 | 0 |  | 0 | 0
1 | 03 | 03 | [9 empty] | Project Planning and Reporting (6.0) | 1.03.03 | 3.6.1 | 6976 | C | 1303 days |  | 799
1 | 03 | 03 | 01 | [8 empty] | Attend Kick Off Meeting. | 1.03.03.01 | 3.6.2 | 6978 | W | 1 day | 8 | 56 | 8 | 8 | 8 | [18 empty] | 8 | [17 empty] | 8 | [13 empty] | 8 | [22 empty] | 8
1 | 03 | 03 | 02 | [8 empty] | Devlop and Maintain an Operations Management Project Work Plan | 1.03.03.02 | 3.6.3 | 6979 | W | 15ed | 120 | 113 | 16.75 | [52 empty] | 68.75 | [13 empty] | 27.5
| 03 | 03 | 02 | [8 empty] | Total Hours | 1.03.03.02 |  |  | A |  |  | 169 | 24.75 | 8 | 8 | [5 empty] | 0 |  | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 8 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | [5 empty] | 8 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 76.75 |  |  |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 27.5 | 0 | 0 |  |  |  | 0 | 0 |  | 8 | 0 |  | 0 | 0
1 | 03 | 03 | 03 | [8 empty] | Status Reporting (6.3) | 1.03.03.03 |  | 6980 | W | 11 days |  | 630 | 30 | [31 empty] | 0 | [20 empty] | 480 | [13 empty] | 60 | [10 empty] | 60
1 | 03 | 03 | 03 | 01 | [7 empty] | Integrated Master Schedule (IMS) Status Collection Use Case | 1.03.03.03.01 |  | 22216 | T | 5 days | 40 | 262.5 | 12.5 | [52 empty] | 200 | [13 empty] | 25 | [10 empty] | 25
1 | 03 | 03 | 03 | 02 | [7 empty] | Monthly Program Management Review Meeting | 1.03.03.03.02 |  | 22215 | S | 2 days | 0 | 0 | 0 | [52 empty] | 0 | [13 empty] | 0 | [10 empty] | 0
1 | 03 | 03 | 03 | 02 | 01 | [6 empty] | Monthly Task Order Status Agenda | 1.03.03.03.02.01 |  | 22221 | T | 1 day | 8 | 52.5 | 2.5 | [52 empty] | 40 | [13 empty] | 5 | [10 empty] | 5
1 | 03 | 03 | 03 | 02 | 02 | [6 empty] | Monthly Facilities Agenda | 1.03.03.03.02.02 |  | 22223 | T | 1 day | 8 | 52.5 | 2.5 | [52 empty] | 40 | [13 empty] | 5 | [10 empty] | 5
1 | 03 | 03 | 03 | 02 | 03 | [6 empty] | Monthly Change Board Agenda | 1.03.03.03.02.03 |  | 22219 | T | 1 day | 8 | 52.5 | 2.5 | [52 empty] | 40 | [13 empty] | 5 | [10 empty] | 5
1 | 03 | 03 | 03 | 02 | 04 | [6 empty] | Monthly Risk Board Agenda | 1.03.03.03.02.04 |  | 22220 | T | 1 day | 8 | 52.5 | 2.5 | [52 empty] | 40 | [13 empty] | 5 | [10 empty] | 5
1 | 03 | 03 | 03 | 02 | 05 | [6 empty] | PMR | 1.03.03.03.02.05 |  | 22224 | T | 1 day | 8 | 52.5 | 2.5 | [52 empty] | 40 | [13 empty] | 5 | [10 empty] | 5
1 | 03 | 03 | 03 | 03 | [7 empty] | Monthly Program Management Review (PMR) Minutes | 1.03.03.03.03 |  | 22218 | T | 1 day | 8 | 52.5 | 2.5 | [52 empty] | 40 | [13 empty] | 5 | [10 empty] | 5
1 | 03 | 03 | 03 | 04 | [7 empty] | Produce and Deliver Status Report to the COR by the 10th of each month | 1.03.03.03.04 |  | 22217 | M | 0 days | 0 | 0 | 0 | [52 empty] | 0 | [13 empty] | 0 | [10 empty] | 0
1 | 03 | 03 | 03 | 05 | [7 empty] | PMR Minutes submitted to COR | 1.03.03.03.05 | 3.7 | 22222 | T | 1 day | 8 | 52.5 | 2.5 | [52 empty] | 40 | [13 empty] | 5 | [10 empty] | 5
| 03 | 03 | 03 | [8 empty] | Total Hours | 1.03.03.03 |  |  | A |  | 96 | 630 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0
1 | 03 | 04 | [9 empty] | Deliverables (7.0) | 1.03.04 | 3.7.1 | 6981 | W | 1296 days |  | 0
1 | 03 | 04 | 01 | [8 empty] | Attend kick-off meeting at NIST | 1.03.04.01 | 3.7.2 | 6982 | M | 0 days |  | 0
1 | 03 | 04 | 02 | [8 empty] | Operations Management Project Work Plan | 1.03.04.02 | 3.7.3 | 6983 | M | 0 days |  | 0
1 | 03 | 04 | 03 | [8 empty] | Monthly Status Reports | 1.03.04.03 |  | 6984 | S | 1283 days |  | 0
1 | 03 | 04 | 03 | 01 | [7 empty] | 2014 | 1.03.04.03.01 |  | 22739 | S | 43 days |  | 0
1 | 03 | 04 | 03 | 01 | 01 | [6 empty] | Oct 2014 | 1.03.04.03.01.01 |  | 22489 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 01 | 02 | [6 empty] | Nov 2014 | 1.03.04.03.01.02 |  | 22490 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 01 | 03 | [6 empty] | Dec 2014 | 1.03.04.03.01.03 |  | 22491 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | [7 empty] | 2015 | 1.03.04.03.02 |  | 22506 | S | 240 days |  | 0
1 | 03 | 04 | 03 | 02 | 01 | [6 empty] | Jan 2015 | 1.03.04.03.02.01 |  | 22507 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | 02 | [6 empty] | Feb 2015 | 1.03.04.03.02.02 |  | 22511 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | 03 | [6 empty] | Mar 2015 | 1.03.04.03.02.03 |  | 22515 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | 04 | [6 empty] | Apr 2015 | 1.03.04.03.02.04 |  | 22519 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | 05 | [6 empty] | May 2015 | 1.03.04.03.02.05 |  | 22523 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | 06 | [6 empty] | Jun 2015 | 1.03.04.03.02.06 |  | 22527 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | 07 | [6 empty] | Jul 2015 | 1.03.04.03.02.07 |  | 22531 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | 08 | [6 empty] | Aug 2015 | 1.03.04.03.02.08 |  | 22535 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | 09 | [6 empty] | Sep 2015 | 1.03.04.03.02.09 |  | 22539 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | 10 | [6 empty] | Oct 2015 | 1.03.04.03.02.10 |  | 22543 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | 11 | [6 empty] | Nov 2015 | 1.03.04.03.02.11 |  | 22547 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 02 | 12 | [6 empty] | Dec 2015 | 1.03.04.03.02.12 |  | 22551 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | [7 empty] | 2016 | 1.03.04.03.03 |  | 22555 | S | 240 days | 0 | 0
1 | 03 | 04 | 03 | 03 | 01 | [6 empty] | Jan 2016 | 1.03.04.03.03.01 |  | 22556 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | 02 | [6 empty] | Feb 2016 | 1.03.04.03.03.02 |  | 22560 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | 03 | [6 empty] | Mar 2016 | 1.03.04.03.03.03 |  | 22564 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | 04 | [6 empty] | Apr 2016 | 1.03.04.03.03.04 |  | 22568 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | 05 | [6 empty] | May 2016 | 1.03.04.03.03.05 |  | 22572 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | 06 | [6 empty] | Jun 2016 | 1.03.04.03.03.06 |  | 22576 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | 07 | [6 empty] | Jul 2016 | 1.03.04.03.03.07 |  | 22580 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | 08 | [6 empty] | Aug 2016 | 1.03.04.03.03.08 |  | 22584 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | 09 | [6 empty] | Sep 2016 | 1.03.04.03.03.09 |  | 22588 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | 10 | [6 empty] | Oct 2016 | 1.03.04.03.03.10 |  | 22592 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | 11 | [6 empty] | Nov 2016 | 1.03.04.03.03.11 |  | 22596 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 03 | 12 | [6 empty] | Dec 2016 | 1.03.04.03.03.12 |  | 22600 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | [7 empty] | 2017 | 1.03.04.03.04 |  | 22604 | S | 238 days |  | 0
1 | 03 | 04 | 03 | 04 | 01 | [6 empty] | Jan 2017 | 1.03.04.03.04.01 |  | 22605 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | 02 | [6 empty] | Feb 2017 | 1.03.04.03.04.02 |  | 22609 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | 03 | [6 empty] | Mar 2017 | 1.03.04.03.04.03 |  | 22613 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | 04 | [6 empty] | Apr 2017 | 1.03.04.03.04.04 |  | 22617 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | 05 | [6 empty] | May 2017 | 1.03.04.03.04.05 |  | 22621 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | 06 | [6 empty] | Jun 2017 | 1.03.04.03.04.06 |  | 22625 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | 07 | [6 empty] | Jul 2017 | 1.03.04.03.04.07 |  | 22629 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | 08 | [6 empty] | Aug 2017 | 1.03.04.03.04.08 |  | 22633 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | 09 | [6 empty] | Sep 2017 | 1.03.04.03.04.09 |  | 22637 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | 10 | [6 empty] | Oct 2017 | 1.03.04.03.04.10 |  | 22641 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | 11 | [6 empty] | Nov 2017 | 1.03.04.03.04.11 |  | 22645 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 04 | 12 | [6 empty] | Dec 2017 | 1.03.04.03.04.12 |  | 22649 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | [7 empty] | 2018 | 1.03.04.03.05 |  | 22653 | S | 238 days |  | 0
1 | 03 | 04 | 03 | 05 | 01 | [6 empty] | Jan 2018 | 1.03.04.03.05.01 |  | 22654 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | 02 | [6 empty] | Feb 2018 | 1.03.04.03.05.02 |  | 22658 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | 03 | [6 empty] | Mar 2018 | 1.03.04.03.05.03 |  | 22662 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | 04 | [6 empty] | Apr 2018 | 1.03.04.03.05.04 |  | 22666 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | 05 | [6 empty] | May 2018 | 1.03.04.03.05.05 |  | 22670 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | 06 | [6 empty] | Jun 2018 | 1.03.04.03.05.06 |  | 22674 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | 07 | [6 empty] | Jul 2018 | 1.03.04.03.05.07 |  | 22678 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | 08 | [6 empty] | Aug 2018 | 1.03.04.03.05.08 |  | 22682 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | 09 | [6 empty] | Sep 2018 | 1.03.04.03.05.09 |  | 22686 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | 10 | [6 empty] | Oct 2018 | 1.03.04.03.05.10 |  | 22690 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | 11 | [6 empty] | Nov 2018 | 1.03.04.03.05.11 |  | 22694 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 05 | 12 | [6 empty] | Dec 2018 | 1.03.04.03.05.12 |  | 22698 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 06 | [7 empty] | 2019 | 1.03.04.03.06 |  | 22702 | S | 173 days |  | 0
1 | 03 | 04 | 03 | 06 | 01 | [6 empty] | Jan 2019 | 1.03.04.03.06.01 |  | 22703 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 06 | 02 | [6 empty] | Feb 2019 | 1.03.04.03.06.02 |  | 22707 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 06 | 03 | [6 empty] | Mar 2019 | 1.03.04.03.06.03 |  | 22711 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 06 | 04 | [6 empty] | Apr 2019 | 1.03.04.03.06.04 |  | 22715 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 06 | 05 | [6 empty] | May 2019 | 1.03.04.03.06.05 |  | 22719 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 06 | 06 | [6 empty] | Jun 2019 | 1.03.04.03.06.06 |  | 22723 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 06 | 07 | [6 empty] | Jul 2019 | 1.03.04.03.06.07 |  | 22727 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 06 | 08 | [6 empty] | Aug 2019 | 1.03.04.03.06.08 |  | 22731 | M | 0 days |  | 0
1 | 03 | 04 | 03 | 06 | 09 | [6 empty] | Sep 2019 | 1.03.04.03.06.09 | 3.7.4 | 22735 | M | 0 days |  | 0
1 | 03 | 04 | 04 | [8 empty] | Phase II Facility Design Work Plan | 1.03.04.04 | 3.7.5 | 6985 | M | 0 days |  | 0
1 | 03 | 04 | 05 | [8 empty] | Monthly Facility Infrastructure Design Conference Agenda | 1.03.04.05 |  | 6986 | S | 1281 days |  | 0
1 | 03 | 04 | 05 | 01 | [7 empty] | 2014 | 1.03.04.05.01 |  | 23200 | S | 37 days |  | 0
1 | 03 | 04 | 05 | 01 | 01 | [6 empty] | Oct 2014 | 1.03.04.05.01.01 |  | 23201 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 01 | 02 | [6 empty] | Nov 2014 | 1.03.04.05.01.02 |  | 23202 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 01 | 03 | [6 empty] | Dec 2014 | 1.03.04.05.01.03 |  | 23203 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | [7 empty] | 2015 | 1.03.04.05.02 |  | 23204 | S | 238 days | 0 | 0
1 | 03 | 04 | 05 | 02 | 01 | [6 empty] | Jan 2015 | 1.03.04.05.02.01 |  | 23205 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | 02 | [6 empty] | Feb 2015 | 1.03.04.05.02.02 |  | 23206 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | 03 | [6 empty] | Mar 2015 | 1.03.04.05.02.03 |  | 23207 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | 04 | [6 empty] | Apr 2015 | 1.03.04.05.02.04 |  | 23208 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | 05 | [6 empty] | May 2015 | 1.03.04.05.02.05 |  | 23209 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | 06 | [6 empty] | Jun 2015 | 1.03.04.05.02.06 |  | 23210 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | 07 | [6 empty] | Jul 2015 | 1.03.04.05.02.07 |  | 23211 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | 08 | [6 empty] | Aug 2015 | 1.03.04.05.02.08 |  | 23212 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | 09 | [6 empty] | Sep 2015 | 1.03.04.05.02.09 |  | 23213 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | 10 | [6 empty] | Oct 2015 | 1.03.04.05.02.10 |  | 23214 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | 11 | [6 empty] | Nov 2015 | 1.03.04.05.02.11 |  | 23215 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 02 | 12 | [6 empty] | Dec 2015 | 1.03.04.05.02.12 |  | 23216 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | [7 empty] | 2016 | 1.03.04.05.03 |  | 23217 | S | 239 days | 0 | 0
1 | 03 | 04 | 05 | 03 | 01 | [6 empty] | Jan 2016 | 1.03.04.05.03.01 |  | 23218 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | 02 | [6 empty] | Feb 2016 | 1.03.04.05.03.02 |  | 23219 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | 03 | [6 empty] | Mar 2016 | 1.03.04.05.03.03 |  | 23220 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | 04 | [6 empty] | Apr 2016 | 1.03.04.05.03.04 |  | 23221 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | 05 | [6 empty] | May 2016 | 1.03.04.05.03.05 |  | 23222 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | 06 | [6 empty] | Jun 2016 | 1.03.04.05.03.06 |  | 23223 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | 07 | [6 empty] | Jul 2016 | 1.03.04.05.03.07 |  | 23224 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | 08 | [6 empty] | Aug 2016 | 1.03.04.05.03.08 |  | 23225 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | 09 | [6 empty] | Sep 2016 | 1.03.04.05.03.09 |  | 23226 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | 10 | [6 empty] | Oct 2016 | 1.03.04.05.03.10 |  | 23227 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | 11 | [6 empty] | Nov 2016 | 1.03.04.05.03.11 |  | 23228 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 03 | 12 | [6 empty] | Dec 2016 | 1.03.04.05.03.12 |  | 23229 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | [7 empty] | 2017 | 1.03.04.05.04 |  | 23230 | S | 238 days | 0 | 0
1 | 03 | 04 | 05 | 04 | 01 | [6 empty] | Jan 2017 | 1.03.04.05.04.01 |  | 23231 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | 02 | [6 empty] | Feb 2017 | 1.03.04.05.04.02 |  | 23232 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | 03 | [6 empty] | Mar 2017 | 1.03.04.05.04.03 |  | 23233 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | 04 | [6 empty] | Apr 2017 | 1.03.04.05.04.04 |  | 23234 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | 05 | [6 empty] | May 2017 | 1.03.04.05.04.05 |  | 23235 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | 06 | [6 empty] | Jun 2017 | 1.03.04.05.04.06 |  | 23236 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | 07 | [6 empty] | Jul 2017 | 1.03.04.05.04.07 |  | 23237 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | 08 | [6 empty] | Aug 2017 | 1.03.04.05.04.08 |  | 23238 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | 09 | [6 empty] | Sep 2017 | 1.03.04.05.04.09 |  | 23239 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | 10 | [6 empty] | Oct 2017 | 1.03.04.05.04.10 |  | 23240 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | 11 | [6 empty] | Nov 2017 | 1.03.04.05.04.11 |  | 23241 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 04 | 12 | [6 empty] | Dec 2017 | 1.03.04.05.04.12 |  | 23242 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | [7 empty] | 2018 | 1.03.04.05.05 |  | 23243 | S | 250 days | 0 | 0
1 | 03 | 04 | 05 | 05 | 01 | [6 empty] | Jan 2018 | 1.03.04.05.05.01 |  | 23244 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | 02 | [6 empty] | Feb 2018 | 1.03.04.05.05.02 |  | 23245 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | 03 | [6 empty] | Mar 2018 | 1.03.04.05.05.03 |  | 23246 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | 04 | [6 empty] | Apr 2018 | 1.03.04.05.05.04 |  | 23247 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | 05 | [6 empty] | May 2018 | 1.03.04.05.05.05 |  | 23248 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | 06 | [6 empty] | Jun 2018 | 1.03.04.05.05.06 |  | 23249 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | 07 | [6 empty] | Jul 2018 | 1.03.04.05.05.07 |  | 23250 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | 08 | [6 empty] | Aug 2018 | 1.03.04.05.05.08 |  | 23251 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | 09 | [6 empty] | Sep 2018 | 1.03.04.05.05.09 |  | 23252 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | 10 | [6 empty] | Oct 2018 | 1.03.04.05.05.10 |  | 23253 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | 11 | [6 empty] | Nov 2018 | 1.03.04.05.05.11 |  | 23254 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 05 | 12 | [6 empty] | Dec 2018 | 1.03.04.05.05.12 |  | 23255 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 06 | [7 empty] | 2019 | 1.03.04.05.06 |  | 23256 | S | 178 days | 0 | 0
1 | 03 | 04 | 05 | 06 | 01 | [6 empty] | Jan 2019 | 1.03.04.05.06.01 |  | 23257 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 06 | 02 | [6 empty] | Feb 2019 | 1.03.04.05.06.02 |  | 23258 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 06 | 03 | [6 empty] | Mar 2019 | 1.03.04.05.06.03 |  | 23259 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 06 | 04 | [6 empty] | Apr 2019 | 1.03.04.05.06.04 |  | 23260 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 06 | 05 | [6 empty] | May 2019 | 1.03.04.05.06.05 |  | 23261 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 06 | 06 | [6 empty] | Jun 2019 | 1.03.04.05.06.06 |  | 23262 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 06 | 07 | [6 empty] | Jul 2019 | 1.03.04.05.06.07 |  | 23263 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 06 | 08 | [6 empty] | Aug 2019 | 1.03.04.05.06.08 |  | 23264 | M | 0 days |  | 0
1 | 03 | 04 | 05 | 06 | 09 | [6 empty] | Sep 2019 | 1.03.04.05.06.09 |  | 23265 | M | 0 days |  | 0
1 | 03 | 04 | 06 | [8 empty] | Monthly Facility Infrastructure Design Conference Minutes | 1.03.04.06 |  | 22761 | S | 1283 days | 0 | 0
1 | 03 | 04 | 06 | 01 | [7 empty] | 2014 | 1.03.04.06.01 |  | 22764 | S | 42 days | 0 | 0
1 | 03 | 04 | 06 | 01 | 01 | [6 empty] | Oct 2014 | 1.03.04.06.01.01 |  | 22765 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 01 | 02 | [6 empty] | Nov 2014 | 1.03.04.06.01.02 |  | 22766 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 01 | 03 | [6 empty] | Dec 2014 | 1.03.04.06.01.03 |  | 22767 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | [7 empty] | 2015 | 1.03.04.06.02 |  | 22768 | S | 238 days | 0 | 0
1 | 03 | 04 | 06 | 02 | 01 | [6 empty] | Jan 2015 | 1.03.04.06.02.01 |  | 22769 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | 02 | [6 empty] | Feb 2015 | 1.03.04.06.02.02 |  | 22770 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | 03 | [6 empty] | Mar 2015 | 1.03.04.06.02.03 |  | 22771 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | 04 | [6 empty] | Apr 2015 | 1.03.04.06.02.04 |  | 22772 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | 05 | [6 empty] | May 2015 | 1.03.04.06.02.05 |  | 22773 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | 06 | [6 empty] | Jun 2015 | 1.03.04.06.02.06 |  | 22774 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | 07 | [6 empty] | Jul 2015 | 1.03.04.06.02.07 |  | 22775 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | 08 | [6 empty] | Aug 2015 | 1.03.04.06.02.08 |  | 22776 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | 09 | [6 empty] | Sep 2015 | 1.03.04.06.02.09 |  | 22777 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | 10 | [6 empty] | Oct 2015 | 1.03.04.06.02.10 |  | 22778 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | 11 | [6 empty] | Nov 2015 | 1.03.04.06.02.11 |  | 22779 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 02 | 12 | [6 empty] | Dec 2015 | 1.03.04.06.02.12 |  | 22780 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | [7 empty] | 2016 | 1.03.04.06.03 |  | 22781 | S | 239 days | 0 | 0
1 | 03 | 04 | 06 | 03 | 01 | [6 empty] | Jan 2016 | 1.03.04.06.03.01 |  | 22782 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | 02 | [6 empty] | Feb 2016 | 1.03.04.06.03.02 |  | 22783 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | 03 | [6 empty] | Mar 2016 | 1.03.04.06.03.03 |  | 22784 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | 04 | [6 empty] | Apr 2016 | 1.03.04.06.03.04 |  | 22785 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | 05 | [6 empty] | May 2016 | 1.03.04.06.03.05 |  | 22786 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | 06 | [6 empty] | Jun 2016 | 1.03.04.06.03.06 |  | 22787 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | 07 | [6 empty] | Jul 2016 | 1.03.04.06.03.07 |  | 22788 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | 08 | [6 empty] | Aug 2016 | 1.03.04.06.03.08 |  | 22789 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | 09 | [6 empty] | Sep 2016 | 1.03.04.06.03.09 |  | 22790 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | 10 | [6 empty] | Oct 2016 | 1.03.04.06.03.10 |  | 22791 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | 11 | [6 empty] | Nov 2016 | 1.03.04.06.03.11 |  | 22792 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 03 | 12 | [6 empty] | Dec 2016 | 1.03.04.06.03.12 |  | 22793 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | [7 empty] | 2017 | 1.03.04.06.04 |  | 22794 | S | 238 days | 0 | 0
1 | 03 | 04 | 06 | 04 | 01 | [6 empty] | Jan 2017 | 1.03.04.06.04.01 |  | 22795 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | 02 | [6 empty] | Feb 2017 | 1.03.04.06.04.02 |  | 22796 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | 03 | [6 empty] | Mar 2017 | 1.03.04.06.04.03 |  | 22797 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | 04 | [6 empty] | Apr 2017 | 1.03.04.06.04.04 |  | 22798 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | 05 | [6 empty] | May 2017 | 1.03.04.06.04.05 |  | 22799 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | 06 | [6 empty] | Jun 2017 | 1.03.04.06.04.06 |  | 22800 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | 07 | [6 empty] | Jul 2017 | 1.03.04.06.04.07 |  | 22801 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | 08 | [6 empty] | Aug 2017 | 1.03.04.06.04.08 |  | 22802 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | 09 | [6 empty] | Sep 2017 | 1.03.04.06.04.09 |  | 22803 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | 10 | [6 empty] | Oct 2017 | 1.03.04.06.04.10 |  | 22804 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | 11 | [6 empty] | Nov 2017 | 1.03.04.06.04.11 |  | 22805 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 04 | 12 | [6 empty] | Dec 2017 | 1.03.04.06.04.12 |  | 22806 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | [7 empty] | 2018 | 1.03.04.06.05 |  | 22807 | S | 238 days | 0 | 0
1 | 03 | 04 | 06 | 05 | 01 | [6 empty] | Jan 2018 | 1.03.04.06.05.01 |  | 22808 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | 02 | [6 empty] | Feb 2018 | 1.03.04.06.05.02 |  | 22809 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | 03 | [6 empty] | Mar 2018 | 1.03.04.06.05.03 |  | 22810 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | 04 | [6 empty] | Apr 2018 | 1.03.04.06.05.04 |  | 22811 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | 05 | [6 empty] | May 2018 | 1.03.04.06.05.05 |  | 22812 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | 06 | [6 empty] | Jun 2018 | 1.03.04.06.05.06 |  | 22813 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | 07 | [6 empty] | Jul 2018 | 1.03.04.06.05.07 |  | 22814 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | 08 | [6 empty] | Aug 2018 | 1.03.04.06.05.08 |  | 22815 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | 09 | [6 empty] | Sep 2018 | 1.03.04.06.05.09 |  | 22816 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | 10 | [6 empty] | Oct 2018 | 1.03.04.06.05.10 |  | 22817 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | 11 | [6 empty] | Nov 2018 | 1.03.04.06.05.11 |  | 22818 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 05 | 12 | [6 empty] | Dec 2018 | 1.03.04.06.05.12 |  | 22819 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 06 | [7 empty] | 2019 | 1.03.04.06.06 |  | 22820 | S | 175 days | 0 | 0
1 | 03 | 04 | 06 | 06 | 01 | [6 empty] | Jan 2019 | 1.03.04.06.06.01 |  | 22821 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 06 | 02 | [6 empty] | Feb 2019 | 1.03.04.06.06.02 |  | 22822 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 06 | 03 | [6 empty] | Mar 2019 | 1.03.04.06.06.03 |  | 22823 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 06 | 04 | [6 empty] | Apr 2019 | 1.03.04.06.06.04 |  | 22824 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 06 | 05 | [6 empty] | May 2019 | 1.03.04.06.06.05 |  | 22825 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 06 | 06 | [6 empty] | Jun 2019 | 1.03.04.06.06.06 |  | 22826 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 06 | 07 | [6 empty] | Jul 2019 | 1.03.04.06.06.07 |  | 22827 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 06 | 08 | [6 empty] | Aug 2019 | 1.03.04.06.06.08 |  | 22828 | M | 0 days |  | 0
1 | 03 | 04 | 06 | 06 | 09 | [6 empty] | Sep 2019 | 1.03.04.06.06.09 | 3.7.6 | 22829 | M | 0 days |  | 0
1 | 03 | 04 | 07 | [8 empty] | In-person and Teleconference Meeting Minutes | 1.03.04.07 |  | 6987 | S | 44 days | 0 | 0
1 | 03 | 04 | 07 | 01 | [7 empty] | In-person and Teleconference Meeting Minutes-01 | 1.03.04.07.01 |  | 22392 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 02 | [7 empty] | In-person and Teleconference Meeting Minutes-02 | 1.03.04.07.02 |  | 22393 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 03 | [7 empty] | In-person and Teleconference Meeting Minutes-03 | 1.03.04.07.03 |  | 22394 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 04 | [7 empty] | In-person and Teleconference Meeting Minutes-04 | 1.03.04.07.04 |  | 22395 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 05 | [7 empty] | In-person and Teleconference Meeting Minutes-05 | 1.03.04.07.05 |  | 22396 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 06 | [7 empty] | In-person and Teleconference Meeting Minutes-06 | 1.03.04.07.06 |  | 22397 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 07 | [7 empty] | In-person and Teleconference Meeting Minutes-07 | 1.03.04.07.07 |  | 22398 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 08 | [7 empty] | In-person and Teleconference Meeting Minutes-08 | 1.03.04.07.08 |  | 22399 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 09 | [7 empty] | In-person and Teleconference Meeting Minutes-09 | 1.03.04.07.09 |  | 22400 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 10 | [7 empty] | In-person and Teleconference Meeting Minutes-10 | 1.03.04.07.10 |  | 22401 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 11 | [7 empty] | In-person and Teleconference Meeting Minutes-11 | 1.03.04.07.11 |  | 22402 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 12 | [7 empty] | In-person and Teleconference Meeting Minutes-12 | 1.03.04.07.12 |  | 22403 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 13 | [7 empty] | In-person and Teleconference Meeting Minutes-13 | 1.03.04.07.13 |  | 22404 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 14 | [7 empty] | In-person and Teleconference Meeting Minutes-14 | 1.03.04.07.14 |  | 22405 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 15 | [7 empty] | In-person and Teleconference Meeting Minutes-15 | 1.03.04.07.15 |  | 22406 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 16 | [7 empty] | In-person and Teleconference Meeting Minutes-16 | 1.03.04.07.16 |  | 22407 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 17 | [7 empty] | In-person and Teleconference Meeting Minutes-17 | 1.03.04.07.17 |  | 22408 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 18 | [7 empty] | In-person and Teleconference Meeting Minutes-18 | 1.03.04.07.18 |  | 22409 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 19 | [7 empty] | In-person and Teleconference Meeting Minutes-19 | 1.03.04.07.19 |  | 22410 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 20 | [7 empty] | In-person and Teleconference Meeting Minutes-20 | 1.03.04.07.20 |  | 22411 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 21 | [7 empty] | In-person and Teleconference Meeting Minutes-21 | 1.03.04.07.21 |  | 22412 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 22 | [7 empty] | In-person and Teleconference Meeting Minutes-22 | 1.03.04.07.22 |  | 22413 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 23 | [7 empty] | In-person and Teleconference Meeting Minutes-23 | 1.03.04.07.23 |  | 22414 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 24 | [7 empty] | In-person and Teleconference Meeting Minutes-24 | 1.03.04.07.24 |  | 22415 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 25 | [7 empty] | In-person and Teleconference Meeting Minutes-25 | 1.03.04.07.25 |  | 22416 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 26 | [7 empty] | In-person and Teleconference Meeting Minutes-26 | 1.03.04.07.26 |  | 22417 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 27 | [7 empty] | In-person and Teleconference Meeting Minutes-27 | 1.03.04.07.27 |  | 22418 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 28 | [7 empty] | In-person and Teleconference Meeting Minutes-28 | 1.03.04.07.28 |  | 22419 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 29 | [7 empty] | In-person and Teleconference Meeting Minutes-29 | 1.03.04.07.29 |  | 22420 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 30 | [7 empty] | In-person and Teleconference Meeting Minutes-30 | 1.03.04.07.30 |  | 22421 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 31 | [7 empty] | In-person and Teleconference Meeting Minutes-31 | 1.03.04.07.31 |  | 22422 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 32 | [7 empty] | In-person and Teleconference Meeting Minutes-32 | 1.03.04.07.32 |  | 22423 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 33 | [7 empty] | In-person and Teleconference Meeting Minutes-33 | 1.03.04.07.33 |  | 22424 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 34 | [7 empty] | In-person and Teleconference Meeting Minutes-34 | 1.03.04.07.34 |  | 22425 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 35 | [7 empty] | In-person and Teleconference Meeting Minutes-35 | 1.03.04.07.35 |  | 22426 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 36 | [7 empty] | In-person and Teleconference Meeting Minutes-36 | 1.03.04.07.36 |  | 22427 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 37 | [7 empty] | In-person and Teleconference Meeting Minutes-37 | 1.03.04.07.37 |  | 22428 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 38 | [7 empty] | In-person and Teleconference Meeting Minutes-38 | 1.03.04.07.38 |  | 22429 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 39 | [7 empty] | In-person and Teleconference Meeting Minutes-39 | 1.03.04.07.39 |  | 22430 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 40 | [7 empty] | In-person and Teleconference Meeting Minutes-40 | 1.03.04.07.40 |  | 22431 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 41 | [7 empty] | In-person and Teleconference Meeting Minutes-41 | 1.03.04.07.41 |  | 22432 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 42 | [7 empty] | In-person and Teleconference Meeting Minutes-42 | 1.03.04.07.42 |  | 22433 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 43 | [7 empty] | In-person and Teleconference Meeting Minutes-43 | 1.03.04.07.43 |  | 22434 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 44 | [7 empty] | In-person and Teleconference Meeting Minutes-44 | 1.03.04.07.44 |  | 22435 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 45 | [7 empty] | In-person and Teleconference Meeting Minutes-45 | 1.03.04.07.45 |  | 22436 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 46 | [7 empty] | In-person and Teleconference Meeting Minutes-46 | 1.03.04.07.46 |  | 22437 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 47 | [7 empty] | In-person and Teleconference Meeting Minutes-47 | 1.03.04.07.47 |  | 22438 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 48 | [7 empty] | In-person and Teleconference Meeting Minutes-48 | 1.03.04.07.48 |  | 22439 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 49 | [7 empty] | In-person and Teleconference Meeting Minutes-49 | 1.03.04.07.49 |  | 22440 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 50 | [7 empty] | In-person and Teleconference Meeting Minutes-50 | 1.03.04.07.50 |  | 22441 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 51 | [7 empty] | In-person and Teleconference Meeting Minutes-51 | 1.03.04.07.51 |  | 22442 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 52 | [7 empty] | In-person and Teleconference Meeting Minutes-52 | 1.03.04.07.52 |  | 22443 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 53 | [7 empty] | In-person and Teleconference Meeting Minutes-53 | 1.03.04.07.53 |  | 22444 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 54 | [7 empty] | In-person and Teleconference Meeting Minutes-54 | 1.03.04.07.54 |  | 22445 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 55 | [7 empty] | In-person and Teleconference Meeting Minutes-55 | 1.03.04.07.55 |  | 22447 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 56 | [7 empty] | In-person and Teleconference Meeting Minutes-56 | 1.03.04.07.56 |  | 22448 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 57 | [7 empty] | In-person and Teleconference Meeting Minutes-57 | 1.03.04.07.57 |  | 22449 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 58 | [7 empty] | In-person and Teleconference Meeting Minutes-58 | 1.03.04.07.58 |  | 22450 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 59 | [7 empty] | In-person and Teleconference Meeting Minutes-59 | 1.03.04.07.59 |  | 22451 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 60 | [7 empty] | In-person and Teleconference Meeting Minutes-60 | 1.03.04.07.60 |  | 22452 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 61 | [7 empty] | In-person and Teleconference Meeting Minutes-61 | 1.03.04.07.61 |  | 22453 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 62 | [7 empty] | In-person and Teleconference Meeting Minutes-62 | 1.03.04.07.62 |  | 22454 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 63 | [7 empty] | In-person and Teleconference Meeting Minutes-63 | 1.03.04.07.63 |  | 22446 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 64 | [7 empty] | In-person and Teleconference Meeting Minutes-64 | 1.03.04.07.64 |  | 22455 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 65 | [7 empty] | In-person and Teleconference Meeting Minutes-65 | 1.03.04.07.65 |  | 22456 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 66 | [7 empty] | In-person and Teleconference Meeting Minutes-66 | 1.03.04.07.66 |  | 22457 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 67 | [7 empty] | In-person and Teleconference Meeting Minutes-67 | 1.03.04.07.67 |  | 22458 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 68 | [7 empty] | In-person and Teleconference Meeting Minutes-68 | 1.03.04.07.68 |  | 22459 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 69 | [7 empty] | In-person and Teleconference Meeting Minutes-69 | 1.03.04.07.69 |  | 22460 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 70 | [7 empty] | In-person and Teleconference Meeting Minutes-70 | 1.03.04.07.70 |  | 22461 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 71 | [7 empty] | In-person and Teleconference Meeting Minutes-71 | 1.03.04.07.71 |  | 22462 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 72 | [7 empty] | In-person and Teleconference Meeting Minutes-72 | 1.03.04.07.72 |  | 22463 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 73 | [7 empty] | In-person and Teleconference Meeting Minutes-73 | 1.03.04.07.73 |  | 22464 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 74 | [7 empty] | In-person and Teleconference Meeting Minutes-74 | 1.03.04.07.74 |  | 22465 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 75 | [7 empty] | In-person and Teleconference Meeting Minutes-75 | 1.03.04.07.75 |  | 22466 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 76 | [7 empty] | In-person and Teleconference Meeting Minutes-76 | 1.03.04.07.76 |  | 22467 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 77 | [7 empty] | In-person and Teleconference Meeting Minutes-77 | 1.03.04.07.77 |  | 22468 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 78 | [7 empty] | In-person and Teleconference Meeting Minutes-78 | 1.03.04.07.78 |  | 22469 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 79 | [7 empty] | In-person and Teleconference Meeting Minutes-79 | 1.03.04.07.79 |  | 22470 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 80 | [7 empty] | In-person and Teleconference Meeting Minutes-80 | 1.03.04.07.80 |  | 22471 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 81 | [7 empty] | In-person and Teleconference Meeting Minutes-81 | 1.03.04.07.81 |  | 22472 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 82 | [7 empty] | In-person and Teleconference Meeting Minutes-82 | 1.03.04.07.82 |  | 22473 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 83 | [7 empty] | In-person and Teleconference Meeting Minutes-83 | 1.03.04.07.83 |  | 22474 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 84 | [7 empty] | In-person and Teleconference Meeting Minutes-84 | 1.03.04.07.84 |  | 22475 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 85 | [7 empty] | In-person and Teleconference Meeting Minutes-85 | 1.03.04.07.85 |  | 22476 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 86 | [7 empty] | In-person and Teleconference Meeting Minutes-86 | 1.03.04.07.86 |  | 22477 | M | 0 days |  | 0
1 | 03 | 04 | 07 | 87 | [7 empty] | In-person and Teleconference Meeting Minutes-87 | 1.03.04.07.87 | 3.7.7 | 22478 | M | 0 days |  | 0
1 | 03 | 04 | 08 | [8 empty] | Phase II Facility Design Report | 1.03.04.08 | 3.8 | 6988 | M | 0 days |  | 0
1 | 03 | 05 | [9 empty] | GOVERNMENT-FURNISHED PROPERTY, MATERIAL, EQUIPMENT, OR Information (GFP,GFM) (8.0) | 1.03.05 | 3.9 | 6990 | W | 1306 days |  | 0
1 | 03 | 06 | [9 empty] | Security (9.0) | 1.03.06 | 3.1 | 6991 | W | 1306 days |  | 0
1 | 03 | 07 | [9 empty] | Key Personnel (10.0) | 1.03.07 | 3.10.1 | 6992 | W | 1306 days |  | 0
1 | 03 | 07 | 01 | [8 empty] | Program Manager (to be filled | 1.03.07.01 | 3.10.2 | 6993 | T | 1306 days | 0 | 0
1 | 03 | 07 | 02 | [8 empty] | Senior Cybersecurity Engineer | 1.03.07.02 | 3.10.3 | 6994 | T | 1306 days | 0 | 0
1 | 03 | 07 | 03 | [8 empty] | Facilities Subject Matter Expert | 1.03.07.03 | 3.10.4 | 6995 | T | 1306 days | 0 | 0
1 | 03 | 07 | 04 | [8 empty] | Organizational Conflict of Interest Compliance Officer | 1.03.07.04 | 3.11 | 6996 | T | 1306 days | 0 | 0
1 | 03 | 08 | [9 empty] | Travel | 1.03.08 | 3.12 | 6997 | W | 1306 days |  | 0
1 | 03 | 09 | [9 empty] | Place of Performance | 1.03.09 | 3.13 | 6998 | W | 1306 days |  | 0
1 | 03 | 10 | [9 empty] | Period of Performance | 1.03.10 | 3.14 | 6999 | W | 1306 days |  | 0
1 | 03 | 11 | [9 empty] | Risk Levels | 1.03.11 |  | 7000 | W | 1306 days |  | 0
| 03 | [10 empty] | Total Task Order 3 |  |  |  | A3 |  |  | 169993.25 | 9049.75 | 8 | 724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050 | 0 | 13575 | 9050 | 9050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2375 | 0 | 0 | 0 | 0 | 9049.75 | 0 | 0 | 0 | 0 | 8 | 0 | 24 | 9050 | 0 | 9050 | 0 | 4750 | 9050 | 87.5 | 0 | 9050 | 0 | 0 | 0 | 9050 | 0 | 0 | 395.25 | 20631 | 9050 | 9050 | 0
1 | 04 | [10 empty] | IMP | 1.04 |  | 23372 | C | 484 days | 0 | 0
1 | 04 | 01 | [9 empty] | Task Order -1 | 1.04.01 |  | 23366 | W | 484 days |  | 0
1 | 04 | 01 | 01 | [8 empty] | Task Order 1,2,3 Award | 1.04.01.01 |  | 23351 | M | 0 days |  | 0
1 | 04 | 01 | 02 | [8 empty] | Use Case 1 Government Acceptance of Use Case Build Plan (IMP) | 1.04.01.02 |  | 23352 | M | 0 days |  | 0
1 | 04 | 01 | 03 | [8 empty] | Use Case 1 Develop and Deliver Final Use Case Documentation Report (IMP) | 1.04.01.03 |  | 23353 | M | 0 days |  | 0
1 | 04 | 01 | 04 | [8 empty] | Use Case 4 Develop and Deliver Final Use Case Documentation Report (IMP) | 1.04.01.04 |  | 23367 | M | 0 days |  | 0
1 | 04 | 01 | 05 | [8 empty] | Use Case 2 Develop and Deliver Final Use Case Documentation Report (IMP) | 1.04.01.05 |  | 23354 | M | 0 days |  | 0
1 | 04 | 01 | 06 | [8 empty] | Use Case 6 Develop and Deliver Final Use Case Documentation Report (IMP) | 1.04.01.06 |  | 23374 | M | 0 days |  | 0
1 | 04 | 02 | [9 empty] | Task Order -2 | 1.04.02 |  | 23355 | W | 464 days |  | 0
1 | 04 | 02 | 01 | [8 empty] | Approval from COR on Block 1 Building Block Description (IMP) | 1.04.02.01 |  | 23368 | M | 0 days |  | 0
1 | 04 | 02 | 02 | [8 empty] | Publish Final Building Block Description Block 1 (5.3) (IMP) | 1.04.02.02 |  | 23359 | M | 0 days |  | 0
1 | 04 | 02 | 03 | [8 empty] | COR Approves the Block 1 Building Block Project Plan (5.5) (IMP) | 1.04.02.03 |  | 23362 | M | 0 days |  | 0
1 | 04 | 02 | 04 | [8 empty] | Initiate Building Block 1 Project (IMP) | 1.04.02.04 |  | 23356 | M | 0 days |  | 0
1 | 04 | 02 | 05 | [8 empty] | Publish Final Building Block Description Block 2 (5.3) (IMP) | 1.04.02.05 |  | 23360 | M | 0 days |  | 0
1 | 04 | 02 | 06 | [8 empty] | COR Approves the Block 2 Building Block Project Plan (IMP) (5.5) Block 2 | 1.04.02.06 |  | 23363 | M | 0 days |  | 0
1 | 04 | 02 | 07 | [8 empty] | Initiate Building Block 2 Project (IMP) | 1.04.02.07 |  | 23364 | M | 0 days |  | 0
1 | 04 | 02 | 08 | [8 empty] | COR Acceptance of the Building Block 1 Documentation Report (IMP) | 1.04.02.08 |  | 23357 | M | 0 days |  | 0
1 | 04 | 02 | 09 | [8 empty] | Publish Final Building Block Description Block 3 (5.3) (IMP) | 1.04.02.09 |  | 23369 | M | 0 days |  | 0
1 | 04 | 02 | 10 | [8 empty] | COR Declines the Block 3 Building Block Project Plan (IMP) | 1.04.02.10 |  | 23365 | M | 0 days |  | 0
1 | 04 | 02 | 11 | [8 empty] | COR Acceptance of the Building Block 2 Documentation Report (IMP) | 1.04.02.11 |  | 23358 | M | 0 days |  | 0
1 | 04 | 02 | 12 | [8 empty] | Publish Final Building Block Description Block 4 (5.3) (IMP) | 1.04.02.12 |  | 23361 | M | 0 days |  | 0
1 | 04 | 02 | 13 | [8 empty] | COR Declines the Block 4 Building Block Project Plan (IMP) | 1.04.02.13 |  | 23376 | M | 0 days |  | 0
1 | 04 | 03 | [9 empty] | Task Order -3 | 1.04.03 |  | 23370 | W | 104.5 days |  | 0
1 | 04 | 03 | 01 | [8 empty] | COR approves the Operations Management Project Work Plan (IMP) | 1.04.03.01 |  | 23371 | M | 0 days |  | 0
1 | 04 | 03 | 02 | [8 empty] | COR Approves Phase II Facility Design Report (IMP) | 1.04.03.02 |  | 23372 | M | 0 days |  | 0
1 | [11 empty] | Total Proposal Hours |  |  |  | AA | 0 days |  | 242375.1558 | 9050.25 | 8 | 3619.15 | [5 empty] | 0 |  | 7257.29 |  |  | 7240.32 | 3589.47 | 10438.3105 |  |  |  |  | 7244.5 | 9050 |  | 21484.37 | 9050 | 9050 |  |  | 3552 | 0 |  |  | 0 | 623.15 | [5 empty] | 9050 | [6 empty] | 3540.43 | 3626.89 | 2375 |  |  |  |  | 9049.75 |  |  |  |  | 8 |  | 24 | 9050 |  | 9050 |  | 4750 | 9050 | 3430.7832 | 0 | 9050 |  |  |  | 9050 | 354.4621 |  | 395.25 | 21702.7 |  | 9050 | 0
| 01 | 01 | 01 | [8 empty] | Formula | [9 empty] | 0.014634 | [7 empty] | 0.076098 |  |  | 0.21415 | 0.19512 |  |  |  |  | 0.19122 | 0.091707 | [7 empty] | 0.22049 | 0 | [17 empty] | 0.017561 | [19 empty] | 0.044878 | [6 empty] | 0.012439 |  |  | 0.088293
| 01 | 02 | 01 | [8 empty] | Formula |  |  |  | F |  |  | Phase 2 to-1 | [9 empty] | 0.034884 | 0.071366 |  |  | 0.26977 | 0.26047 | 0.30698 |  |  |  | 0.20698 |  |  |  | 0.029349 |  |  |  |  | 0.25349 |  |  |  |  | 0 | [13 empty] | 0 |  |  | 0.019535 | [16 empty] | 0.048837 | [6 empty] | 0.0097674 |  |  | 0.04186
[12 empty] | Formula |  |  |  | F | [18 empty] | 0 | [30 empty] | 0.16525 | 0
| 01 | 03 | 01 | [8 empty] | Formula |  |  |  | F | [5 empty] | 1.22 | [7 empty] | 0.38879 |  |  |  |  | 3.2132 | [30 empty] | 1.22 | 1.5305
| 01 | 03 | 02 | [8 empty] | Formula |  |  |  | F | [12 empty] | 0.32483 | 0.48753 |  | 0.64768 | 0 | [6 empty] | 0.81179 | 0 |  | 1.2218 | [22 empty] | 0.16525 | 0 | [19 empty] | 0.52239
| 02 | 01 | 01 | [8 empty] | Formula | 1.02.01.01 |  |  | F | [5 empty] | 0.078125 | [7 empty] | 1.293 |  |  | 2.0326 | [6 empty] | 0.57943 | [26 empty] | 0.53906 | [29 empty] | 0.04388
| 02 | 01 | 02 | [8 empty] | Formula | 1.02.01.02 |  |  | F | [17 empty] | 0 | 0.6926 | [30 empty] | 0.093112 | 0 | [29 empty] | 0.0066327
| 02 | 02 | 02 | [8 empty] | Formula | 1.02.02.02 |  |  | F | [12 empty] | 0.076923 | 0 |  |  | 0.16678 | 0.094937 | 0.17631 | [51 empty] | 0.012146 | [6 empty] | 0.0080972
| 02 | 02 | 01 | [8 empty] | Formula | 1.02.02.01 |  |  | F | [12 empty] | 0.19675 | 0.2533 |  |  | 0.30396 |  | 0 | [7 empty] | 0.28652 | [9 empty] | 0.18199 | [12 empty] | 0.019676 | 0 | [19 empty] | 0.049188 | 0 | [5 empty] | 0.049188
| 02 | 02 | 03 | [8 empty] | Formula | 1.02.02.03 |  |  | F | [12 empty] | 0.33677 | 0 |  |  |  |  | 0.19417
| 02 | 03 | 01 | [8 empty] | Formula | 1.02.03.01 |  |  | F | [5 empty] | 0.72292 | [7 empty] | 2.8917 |  |  |  |  | 1.125 | [30 empty] | 0.58333 | 0.72292
| 02 | 03 | 02 | [8 empty] | Formula | 1.02.03.02 |  |  | F | [5 empty] | 0.6572 | [12 empty] | 0.33523 | [30 empty] | 0.27083 | 0.65703
| 02 | 03 | 04 | [8 empty] | Formula | 1.02.03.04 |  |  | F | [5 empty] | 21.6819 | [12 empty] | 4.2106 | [30 empty] | 1.0525 | 21.6819 | [19 empty] | 0.475
| 02 | 03 | 05 | [8 empty] | Formula | 1.02.03.05 |  |  | F | [12 empty] | 0.46667 | 0 |  | 0.86667 | 0 | [5 empty] | 0.5 | 3.2995 |  |  | 2.2833 | [43 empty] | 0.475
| 02 | 03 | 03 | [8 empty] | Formula | 1.02.03.03 |  |  | F | [5 empty] | 2.0649 | [12 empty] | 2.406 | [30 empty] | 4.5112 | 2.0649
| 02 | 03 | 06 | [8 empty] | Formula | 1.02.03.06 |  |  | F | [11 empty] | 0 | 0.5625 |  |  |  | 0 |  | 0.9375 |  |  |  | 0.3125 | 0 |  |  | 0.875
| 02 | 03 | 07 | [8 empty] | Formula | 1.02.03.07 |  |  | F | [12 empty] | 0.10417 | 0 | [8 empty] | 0.10333 | 0 | [46 empty] | 0.10833
| 02 | 04 | 02 | [8 empty] | Formula | 1.02.04 |  |  | F
| 03 | 01 | 01 | [8 empty] | Formula | 1.03.01.01 |  |  | F |  |  |  | 0.078266 | 0 | 0.00623 | [18 empty] | 0.078675 |  | 0.11812 | 0.078745 | 0.078745 | [7 empty] | 0 | [5 empty] | 0.078675 | [8 empty] | 0.020665 |  |  |  |  | 0.072593 | [7 empty] | 0.078745 |  | 0.078745 |  | 0.04133 | 0.078484 |  |  | 0.078745 |  |  |  | 0.078745 |  |  |  | 0.17816 | 0.078223 | 0.078745
| 03 | 02 | 01 | [8 empty] | Formula | 1.03.02.01 |  |  | F | [61 empty] | 0.011111 | [7 empty] | 0.041667 | [9 empty] | 0.28889
| 03 | 02 | 02 | [8 empty] | Formula | 1.03.02.02 |  |  | F | [63 empty] | 0.01676 | [15 empty] | 0.046089 | 0.046089
| 03 | 02 | 03 | [8 empty] | Formula | 1.03.02.03 |  |  | F | [56 empty] | 0.42135 | [23 empty] | 0.25281
| 03 | 02 | 04 | [8 empty] | Formula | 1.03.02.04 |  |  | F | [79 empty] | 0.17695
| 03 | 03 | 03 | [8 empty] | Formula | 1.03.03.03 |  |  | F |  |  |  | 0.3125 | [31 empty] | 0 | [20 empty] | 5 | [13 empty] | 0.625 | [10 empty] | 0.625
| 01 | 04 | [9 empty] | Formula | 1.01.04 |  |  | F
| 03 | 03 | 02 | [8 empty] | Formula | 1.03.03.02 |  |  | F
Note on O2: LEGEND Hours marked in RED are taken Final Matrix

## Sheet2
National Cybersecurity Center of Excellence
WBS
1.01.01.01.01.01.01
1.01.01.01.01.01.02
1.01.01.01.01.01.03
1.01.01.01.01.01.04
1.01.01.01.01.01.05
1.01.01.01.01.01.06
|  |  | Produce and Deliver Agenda DEC 2014 | 1.01.01.01.01.01.07
1.01.01.01.01.01.08
1.01.01.01.01.01.09
|  |  | Produce and Deliver Agenda JAN 2015 | 1.01.01.01.01.01.10
1.01.01.01.01.01.11
1.01.01.01.01.01.12
|  |  | Produce and Deliver Agenda FEB 2015 | 1.01.01.01.01.01.13
1.01.01.01.01.01.14
1.01.01.01.01.01.15
|  |  | Produce and Deliver Agenda MAR 2015 | 1.01.01.01.01.01.16
1.01.01.01.01.01.17
1.01.01.01.01.01.18
|  |  | Produce and Deliver Agenda APR 2015 | 1.01.01.01.01.01.19
1.01.01.01.01.01.20
1.01.01.01.01.01.21
|  |  | Produce and Deliver Agenda MAY 2015 | 1.01.01.01.01.01.22
1.01.01.01.01.01.23
1.01.01.01.01.01.24
|  |  | Produce and Deliver Agenda JUN 2015 | 1.01.01.01.01.01.25
1.01.01.01.01.01.26
1.01.01.01.01.01.27
|  |  | Produce and Deliver Agenda JUL 2015 | 1.01.01.01.01.01.28
1.01.01.01.01.01.29
1.01.01.01.01.01.30
|  |  | Produce and Deliver Agenda AUG 2015 | 1.01.01.01.01.01.31
1.01.01.01.01.01.32
1.01.01.01.01.01.33
|  |  | Produce and Deliver Agenda SEP 2015 | 1.01.01.01.01.01.34
1.01.01.01.01.01.35
1.01.01.01.01.01.36
|  |  | Produce and Deliver Agenda OCT 2015 | 1.01.01.01.01.01.37
1.01.01.01.01.01.38
1.01.01.01.01.01.39
|  |  | Produce and Deliver Agenda NOV 2015 | 1.01.01.01.01.01.40
1.01.01.01.01.01.41
1.01.01.01.01.01.42
|  |  | Produce and Deliver Agenda DEC 2015 | 1.01.01.01.01.01.43
1.01.01.01.01.01.44
1.01.01.01.01.01.45
|  |  | Produce and Deliver Agenda JAN 2016 | 1.01.01.01.01.01.46
1.01.01.01.01.01.47
1.01.01.01.01.01.48
|  |  | Produce and Deliver Agenda FEB 2016 | 1.01.01.01.01.01.49
1.01.01.01.01.01.50
1.01.01.01.01.01.51
|  |  | Produce and Deliver Agenda MAR 2016 | 1.01.01.01.01.01.52
1.01.01.01.01.01.53
1.01.01.01.01.01.54
|  |  | Produce and Deliver Agenda APR 2016 | 1.01.01.01.01.01.55
1.01.01.01.01.01.56
1.01.01.01.01.01.57
|  |  | Produce and Deliver Agenda MAY 2016 | 1.01.01.01.01.01.58
1.01.01.01.01.01.59
1.01.01.01.01.01.60
|  |  | Produce and Deliver Agenda JUN 2016 | 1.01.01.01.01.01.61
1.01.01.01.01.01.62
1.01.01.01.01.01.63
|  |  | Produce and Deliver Agenda JUL 2016 | 1.01.01.01.01.01.64
1.01.01.01.01.01.65
1.01.01.01.01.01.66
|  |  | Produce and Deliver Agenda AUG 2016 | 1.01.01.01.01.01.67
1.01.01.01.01.01.68
1.01.01.01.01.01.69
Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2)
| 1 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) NOV 2014 ( 6 meetings) | 1.01.01.01.01.02.01
| 2 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.01.01
| 3 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.01.02
| 4 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.01.03
| 5 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.01.04
| 6 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.01.05
| 7 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.01.06
| 8 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.01.07
| 9 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.01.08
| 10 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.01.09
| 11 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.01.10
| 12 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.01.11
| 13 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.01.12
| 13 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) DEC 2014 ( 7 meetings) | 1.01.01.01.01.02.02
| 14 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.02.01
| 15 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.02.02
| 16 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.02.03
| 17 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.02.04
| 18 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.02.05
| 19 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.02.06
| 20 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.02.07
| 21 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.02.08
| 22 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.02.09
| 23 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.02.10
| 24 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.02.11
| 25 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.02.12
| 26 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.02.13
| 27 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.02.14
| 27 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) JAN 2015 ( 8 meetings) | 1.01.01.01.01.02.03
| 28 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.03.01
| 29 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.03.02
| 30 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.03.03
| 31 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.03.04
| 32 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.03.05
| 33 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.03.06
| 34 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.03.07
| 35 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.03.08
| 36 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.03.09
| 37 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.03.10
| 38 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.03.11
| 39 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.03.12
| 40 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.03.13
| 41 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.03.14
| 42 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.03.15
| 43 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.03.16
| 43 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) FEB 2015 ( 9 meetings) | 1.01.01.01.01.02.04
| 44 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.04.01
| 45 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.04.02
| 46 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.04.03
| 47 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.04.04
| 48 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.04.05
| 49 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.04.06
| 50 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.04.07
| 51 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.04.08
| 52 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.04.09
| 53 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.04.10
| 54 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.04.11
| 55 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.04.12
| 56 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.04.13
| 57 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.04.14
| 58 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.04.15
| 59 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.04.16
| 60 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.04.17
| 61 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.04.18
| 61 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) MAR 2015 ( 10 meetings) | 1.01.01.01.01.02.05
| 62 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.05.01
| 63 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.05.02
| 64 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.05.03
| 65 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.05.04
| 66 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.05.05
| 67 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.05.06
| 68 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.05.07
| 69 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.05.08
| 70 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.05.09
| 71 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.05.10
| 72 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.05.11
| 73 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.05.12
| 74 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.05.13
| 75 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.05.14
| 76 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.05.15
| 77 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.05.16
| 78 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.05.17
| 79 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.05.18
| 80 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.05.19
| 81 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.05.20
| 81 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) APR 2015 (10 meetings) | 1.01.01.01.01.02.06
| 82 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.06.01
| 83 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.06.02
| 84 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.06.03
| 85 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.06.04
| 86 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.06.05
| 87 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.06.06
| 88 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.06.07
| 89 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.06.08
| 90 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.06.09
| 91 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.06.10
| 92 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.06.11
| 93 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.06.12
| 94 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.06.13
| 95 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.06.14
| 96 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.06.15
| 97 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.06.16
| 98 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.06.17
| 99 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.06.18
| 98 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.06.19
| 99 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.06.20
| 99 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) MAY 2015 ( 10 meetings) | 1.01.01.01.01.02.07
| 100 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.07.01
| 101 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.07.02
| 102 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.07.03
| 103 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.07.04
| 104 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.07.05
| 105 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.07.06
| 106 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.07.07
| 107 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.07.08
| 108 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.07.09
| 109 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.07.10
| 110 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.07.11
| 111 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.07.12
| 112 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.07.13
| 113 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.07.14
| 114 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.07.15
| 115 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.07.16
| 116 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.07.17
| 117 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.07.18
| 116 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.07.19
| 117 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.07.20
| 08 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) JUN 2015 ( 10 meetings) | 1.01.01.01.01.02.08
| 09 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.08.01
| 10 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.08.02
| 11 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.08.03
| 12 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.08.04
| 13 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.08.05
| 14 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.08.06
| 15 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.08.07
| 16 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.08.08
| 17 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.08.09
| 18 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.08.10
| 19 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.08.11
| 20 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.08.12
| 21 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.08.13
| 22 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.08.14
| 23 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.08.15
| 24 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.08.16
| 25 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.08.17
| 26 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.08.18
| 27 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.08.19
| 28 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.08.20
| 09 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) JUL 2015 ( 10 meetings) | 1.01.01.01.01.02.09
| 10 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.09.01
| 11 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.09.02
| 12 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.09.03
| 13 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.09.04
| 14 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.09.05
| 15 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.09.06
| 16 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.09.07
| 17 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.09.08
| 18 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.09.09
| 19 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.09.10
| 20 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.09.11
| 21 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.09.12
| 22 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.09.13
| 23 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.09.14
| 24 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.09.15
| 25 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.09.16
| 26 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.09.17
| 27 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.09.18
| 28 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.09.19
| 29 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.09.20
| 10 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) AUG 2015 ( 10 meetings) | 1.01.01.01.01.02.10
| 11 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.10.01
| 12 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.10.02
| 13 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.10.03
| 14 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.10.04
| 15 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.10.05
| 16 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.10.06
| 17 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.10.07
| 18 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.10.08
| 19 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.10.09
| 20 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.10.10
| 21 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.10.11
| 22 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.10.12
| 23 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.10.13
| 24 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.10.14
| 25 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.10.15
| 26 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.10.16
| 27 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.10.17
| 28 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.10.18
| 29 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.10.19
| 30 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.10.20
| 11 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) SEP 2015 ( 10 meetings) | 1.01.01.01.01.02.11
| 12 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.11.01
| 13 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.11.02
| 14 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.11.03
| 15 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.11.04
| 16 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.11.05
| 17 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.11.06
| 18 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.11.07
| 19 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.11.08
| 20 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.11.09
| 21 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.11.10
| 22 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.11.11
| 23 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.11.12
| 24 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.11.13
| 25 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.11.14
| 26 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.11.15
| 27 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.11.16
| 28 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.11.17
| 29 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.11.18
| 30 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.11.19
| 31 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.11.20
| 12 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) OCT 2015 ( 10 meetings) | 1.01.01.01.01.02.12
| 13 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.12.01
| 14 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.12.02
| 15 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.12.03
| 16 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.12.04
| 17 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.12.05
| 18 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.12.06
| 19 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.12.07
| 20 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.12.08
| 21 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.12.09
| 22 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.12.10
| 23 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.12.11
| 24 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.12.12
| 25 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.12.13
| 26 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.12.14
| 27 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.12.15
| 28 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.12.16
| 29 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.12.17
| 30 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.12.18
| 31 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.12.19
| 32 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.12.20
| 13 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) NOV 2015 ( 10 meetings) | 1.01.01.01.01.02.13
| 14 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.13.01
| 15 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.13.02
| 16 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.13.03
| 17 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.13.04
| 18 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.13.05
| 19 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.13.06
| 20 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.13.07
| 21 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.13.08
| 22 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.13.09
| 23 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.13.10
| 24 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.13.11
| 25 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.13.12
| 26 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.13.13
| 27 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.13.14
| 28 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.13.15
| 29 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.13.16
| 30 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.13.17
| 31 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.13.18
| 32 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.13.19
| 33 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.13.20
| 14 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) DEC 2015 ( 10 meetings) | 1.01.01.01.01.02.14
| 15 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.14.01
| 16 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.14.02
| 17 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.14.03
| 18 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.14.04
| 19 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.14.05
| 20 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.14.06
| 21 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.14.07
| 22 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.14.08
| 23 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.14.09
| 24 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.14.10
| 25 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.14.11
| 26 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.14.12
| 27 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.14.13
| 28 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.14.14
| 29 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.14.15
| 30 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.14.16
| 31 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.14.17
| 32 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.14.18
| 33 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.14.19
| 34 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.14.20
| 15 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) JAN 2016 ( 10 meetings) | 1.01.01.01.01.02.15
| 16 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.15.01
| 17 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.15.02
| 18 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.15.03
| 19 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.15.04
| 20 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.15.05
| 21 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.15.06
| 22 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.15.07
| 23 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.15.08
| 24 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.15.09
| 25 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.15.10
| 26 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.15.11
| 27 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.15.12
| 28 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.15.13
| 29 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.15.14
| 30 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.15.15
| 31 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.15.16
| 32 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.15.17
| 33 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.15.18
| 34 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.15.19
| 35 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.15.20
| 16 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) FEB 2016 ( 10 meetings) | 1.01.01.01.01.02.16
| 17 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.16.01
| 18 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.16.02
| 19 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.16.03
| 20 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.16.04
| 21 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.16.05
| 22 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.16.06
| 23 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.16.07
| 24 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.16.08
| 25 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.16.09
| 26 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.16.10
| 27 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.16.11
| 28 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.16.12
| 29 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.16.13
| 30 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.16.14
| 31 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.16.15
| 32 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.16.16
| 33 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.16.17
| 34 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.16.18
| 35 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.16.19
| 36 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.16.20
| 17 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) MAR 2016 ( 10 meetings) | 1.01.01.01.01.02.17
| 18 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.17.01
| 19 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.17.02
| 20 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.17.03
| 21 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.17.04
| 22 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.17.05
| 23 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.17.06
| 24 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.17.07
| 25 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.17.08
| 26 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.17.09
| 27 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.17.10
| 28 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.17.11
| 29 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.17.12
| 30 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.17.13
| 31 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.17.14
| 32 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.17.15
| 33 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.17.16
| 34 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.17.17
| 35 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.17.18
| 36 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.17.19
| 37 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.17.20
| 18 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) APR 2016 ( 10 meetings) | 1.01.01.01.01.02.18
| 19 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.18.01
| 20 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.18.02
| 21 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.18.03
| 22 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.18.04
| 23 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.18.05
| 24 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.18.06
| 25 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.18.07
| 26 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.18.08
| 27 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.18.09
| 28 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.18.10
| 29 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.18.11
| 30 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.18.12
| 31 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.18.13
| 32 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.18.14
| 33 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.18.15
| 34 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.18.16
| 35 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.18.17
| 36 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.18.18
| 37 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.18.19
| 38 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.18.20
| 19 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) MAY 2016 ( 10 meetings) | 1.01.01.01.01.02.19
| 20 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.19.01
| 21 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.19.02
| 22 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.19.03
| 23 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.19.04
| 24 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.19.05
| 25 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.19.06
| 26 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.19.07
| 27 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.19.08
| 28 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.19.09
| 29 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.19.10
| 30 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.19.11
| 31 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.19.12
| 32 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.19.13
| 33 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.19.14
| 34 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.19.15
| 35 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.19.16
| 36 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.19.17
| 37 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.19.18
| 38 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.19.19
| 39 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.19.20
| 20 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) JUN 2016 ( 10 meetings) | 1.01.01.01.01.02.20
| 21 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.20.01
| 22 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.20.02
| 23 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.20.03
| 24 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.20.04
| 25 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.20.05
| 26 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.20.06
| 27 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.20.07
| 28 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.20.08
| 29 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.20.09
| 30 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.20.10
| 31 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.20.11
| 32 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.20.12
| 33 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.20.13
| 34 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.20.14
| 35 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.20.15
| 36 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.20.16
| 37 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.20.17
| 38 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.20.18
| 39 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.20.19
| 40 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.20.20
| 21 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) JUL 2016 ( 10 meetings) | 1.01.01.01.01.02.21
| 22 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.21.01
| 23 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.21.02
| 24 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.21.03
| 25 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.21.04
| 26 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.21.05
| 27 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.21.06
| 28 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.21.07
| 29 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.21.08
| 30 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.21.09
| 31 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.21.10
| 32 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.21.11
| 33 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.21.12
| 34 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.21.13
| 35 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.21.14
| 36 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.21.15
| 37 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.21.16
| 38 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.21.17
| 39 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.21.18
| 40 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.21.19
| 41 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.21.20
| 22 |  | Conduct in-person meetings (qty 10) to review Cybersecurity Issues (5.1.2) AUG 2016 ( 10 meetings) | 1.01.01.01.01.02.22
| 23 | 01 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.22.01
| 24 | 02 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.22.02
| 25 | 03 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.22.03
| 26 | 04 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.22.04
| 27 | 05 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.22.05
| 28 | 06 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.22.06
| 29 | 07 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.22.07
| 30 | 08 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.22.08
| 31 | 09 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.22.09
| 32 | 10 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.22.10
| 33 | 11 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.22.11
| 34 | 12 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.22.12
| 35 | 13 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.22.13
| 36 | 14 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.22.14
| 37 | 15 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.22.15
| 38 | 16 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.22.16
| 39 | 17 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.22.17
| 40 | 18 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.22.18
| 41 | 19 | Webcast on Cybersecurity Issues | 1.01.01.01.01.02.22.19
| 42 | 20 | Produce and Deliver Business Requirements Meeting Minutes | 1.01.01.01.01.02.22.20
1.01.01.02.02.01.01
1.01.01.02.02.01.01.01
1.01.01.02.02.01.01.02
1.01.01.02.02.01.01.03
1.01.01.02.02.01.01.04
1.01.01.02.02.01.01.05
1.01.01.02.02.01.01.06
1.01.01.02.02.01.01.07
1.01.01.02.02.01.01.08
1.01.01.02.02.01.01.09
1.01.01.02.02.01.01.10
1.01.01.02.02.01.01.11
1.01.01.02.02.01.01.12
1.01.01.02.02.01.01.13
1.01.01.02.02.01.01.14
1.01.01.02.02.01.01.15
1.01.01.02.02.01.01.16
1.01.01.02.02.01.01.17
1.01.01.02.02.01.01.18
1.01.01.02.02.01.01.19
1.01.01.02.02.01.01.20
1.01.01.02.02.01.01.21
1.01.01.02.02.01.01.22
1.01.01.02.02.01.01.23
1.01.01.02.02.01.01.24
1.01.01.02.02.01.01.25
1.01.01.02.02.01.01.26
1.01.01.02.02.01.01.27
1.01.01.02.02.01.01.28
1.01.01.02.02.01.01.29
1.01.01.02.02.01.01.30
1.01.01.02.02.01.01.31
1.01.01.02.02.01.01.32
1.01.01.02.02.01.01.33
1.01.01.02.02.01.01.34
1.01.01.02.02.01.01.35
1.01.01.02.02.01.01.36
1.01.01.02.02.01.01.37
1.01.01.02.02.01.01.38
1.01.01.02.02.01.01.39
1.01.01.02.02.01.01.40
|  |  | Conduct meetings to define further each approved use Case by the COR and Deliver to the COR the Meeting Minutes | 1.01.01.02.03
1.01.01.02.03.01
|  |  | Cycle 1 Further Definition Meeting Mtg #1 | 1.01.01.02.03.01.01
|  |  | Cycle 1 Mtg #1 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.02
|  |  | Cycle 1 Further Definition Meeting Mtg #2 | 1.01.01.02.03.01.03
|  |  | Cycle 1 Mtg #2 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.04
|  |  | Cycle 1 Further Definition Meeting Mtg #3 | 1.01.01.02.03.01.05
|  |  | Cycle 1 Mtg #3 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.06
|  |  | Cycle 1 Further Definition Meeting Mtg #4 | 1.01.01.02.03.01.07
|  |  | Cycle 1 Mtg #4 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.08
|  |  | Cycle 1 Further Definition Meeting Mtg #5 | 1.01.01.02.03.01.09
|  |  | Cycle 1 Mtg #5 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.10
|  |  | Cycle 1 Further Definition Meeting Mtg #6 | 1.01.01.02.03.01.11
|  |  | Cycle 1 Mtg #16 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.12
|  |  | Cycle 1 Further Definition Meeting Mtg #7 | 1.01.01.02.03.01.13
|  |  | Cycle 1 Mtg #7 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.14
|  |  | Cycle 1 Further Definition Meeting Mtg #8 | 1.01.01.02.03.01.15
|  |  | Cycle 1 Mtg #8 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.16
|  |  | Cycle 1 Further Definition Meeting Mtg #9 | 1.01.01.02.03.01.17
|  |  | Cycle 1 Mtg #9 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.18
|  |  | Cycle 1 Further Definition Meeting Mtg #10 | 1.01.01.02.03.01.19
|  |  | Cycle 1 Mtg #10 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.20
|  |  | Cycle 1 Further Definition Meeting Mtg #11 | 1.01.01.02.03.01.21
|  |  | Cycle 1 Mtg #11 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.22
|  |  | Cycle 1 Further Definition Meeting Mtg #12 | 1.01.01.02.03.01.23
|  |  | Cycle 1 Mtg #12 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.24
|  |  | Cycle 1 Further Definition Meeting Mtg #13 | 1.01.01.02.03.01.25
|  |  | Cycle 1 Mtg #13 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.26
|  |  | Cycle 1 Further Definition Meeting Mtg #14 | 1.01.01.02.03.01.27
|  |  | Cycle 1 Mtg #14 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.28
|  |  | Cycle 1 Further Definition Meeting Mtg #15 | 1.01.01.02.03.01.29
|  |  | Cycle 1 Mtg #15 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.30
|  |  | Cycle 1 Further Definition Meeting Mtg #16 | 1.01.01.02.03.01.31
|  |  | Cycle 1 Mtg #16 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.32
|  |  | Cycle 1 Further Definition Meeting Mtg #17 | 1.01.01.02.03.01.33
|  |  | Cycle 1 Mtg #17 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.34
|  |  | Cycle 1 Further Definition Meeting Mtg #18 | 1.01.01.02.03.01.35
|  |  | Cycle 1 Mtg #18 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.36
|  |  | Cycle 1 Further Definition Meeting Mtg #19 | 1.01.01.02.03.01.37
|  |  | Cycle 1 Mtg #19 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.38
|  |  | Cycle 1 Further Definition Meeting Mtg #20 | 1.01.01.02.03.01.39
|  |  | Cycle 1 Mtg #20 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.40
|  |  | Cycle 1 Further Definition Meeting Mtg #21 | 1.01.01.02.03.01.41
|  |  | Cycle 1 Mtg #21 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.42
|  |  | Cycle 1 Further Definition Meeting Mtg #22 | 1.01.01.02.03.01.43
|  |  | Cycle 1 Mtg #22 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.44
|  |  | Cycle 1 Further Definition Meeting Mtg #23 | 1.01.01.02.03.01.45
|  |  | Cycle 1 Mtg #23 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.46
|  |  | Cycle 1 Further Definition Meeting Mtg #24 | 1.01.01.02.03.01.47
|  |  | Cycle 1 Mtg #24 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.48
|  |  | Cycle 1 Further Definition Meeting Mtg #25 | 1.01.01.02.03.01.49
|  |  | Cycle 1 Mtg #25 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.50
|  |  | Cycle 1 Further Definition Meeting Mtg #26 | 1.01.01.02.03.01.51
|  |  | Cycle 1 Mtg #26 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.52
|  |  | Cycle 1 Further Definition Meeting Mtg #27 | 1.01.01.02.03.01.53
|  |  | Cycle 1 Mtg #27 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.54
|  |  | Cycle 1 Further Definition Meeting Mtg #28 | 1.01.01.02.03.01.55
|  |  | Cycle 1 Mtg #28 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.56
|  |  | Cycle 1 Further Definition Meeting Mtg #29 | 1.01.01.02.03.01.57
|  |  | Cycle 1 Mtg #29 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.58
|  |  | Cycle 1 Further Definition Meeting Mtg #30 | 1.01.01.02.03.01.59
|  |  | Cycle 1 Mtg #30 Deliver Use Case Technology Meeting Report | 1.01.01.02.03.01.60